## Slide 1: ITER Integration
Akira Yamamoto (KEK)
presented at
ECFA-LC2013, DESY, May 28, 2012

## Slide 4: 1

## Slide 12: ITER Construction - Plant System Integration -
Provided by Eisuke Tada
JAEA Naka Institute
and
ITER: Japanese Domestic Agency

## Slide 13: ITER Tokamak Structure
Cryostat
24 m high x 28 m dia.
Vacuum vessel
9 sectors
Shielding blankets
440 modules
Divertor
54 cassettes
Center solenoid
Nb3Sn, 6 modules
TF coils
Nb3Sn
PF coils
Nb-Ti
Total weight: ~ 23400 t
Major radius: 6.2 m
Plasma volume: 840 m3
Plasma current: 15 MA
Fusion power: 500 MW

## Slide 14
Key Technology Development
in the EDA Phase
CENTRAL SOLENOID MODEL COIL
Radius 3.5 m
Height 2.8m
Bmax=13 T
0.6 T/sec
REMOTE MAINTENANCE OF DIVERTOR CASSETTE
Attachment Tolerance ± 2 mm
DIVERTOR CASSETTE AND PFCs
20 MW/m2
Height 4 m
Width 3 m
Bmax=7.8 T
TOROIDAL FIELD MODEL COIL
Double-Wall,
± 5 mm
VACUUM VESSEL SECTOR
HIP Joining Tech
BLANKET MODULE
4 t blanket sector ±0.25 mm
REMOTE MAINTENANCE OF BLANKET
Notes: A lot of R&D has also been done on the manufacturing of these components…during the EDA

## Slide 15
ITER - International Cooperation
IO: Management & integration (Nuclear operator)
DAs: In kind contribution & procurement
Construction & operation by the ITER Organization (IO) with support of the Domestic Agencies (DAs) of the seven parties
Notes: Seven participants - the ITER parties - are involved in the construction of the world´s largest fusion device. This international joint venture is coordinated by the International ITER Organization based in Cadarache, in the south of France, app. 70 km north of Marseille.

## Slide 17
Construction Sharing
Complex plant system with advanced technology
Sharing: EU 5/11, other six parties 1/11 each
90 % in kind procurement
Cooling Water
System 4.9 %
Cryostat & Thermal
Shield 3.5 %
Cryoplant &
Distribution 3.2 %
Fuel Cycle
4.1 %
Assembly & Remote
Handling 6.8 %
Diagnostic &
CODAC 6.2 %
Heating System 7.7 %
Vacuum
Vessel 7.9 %
Power supplies &
Distribution 7.2 %
Blanket &
Divertor 8.4 %
Buildings
13.4 %
Magnet
System 26.6 %
ITER Plant System

## Slide 18: Procurement In Kind
  Involvement of the parties in key fusion technology areas
  A fair sharing of the cost of the device by ‘value’ and not by currency
  Interfaces management and integration by IO

## Slide 22: General Roles & Responsibilities for Construction
ITER Organization (IO)
  Planning/Design
  Integration / QA / Safety / Licensing / Schedule
  Global transportation & Installation
  Testing + Commissioning
  Operation
Parties - Domestic Agencies (DAs)
  Detailing / Designing
  Procuring
  Delivering
  Support installation
IO and DAs plus Fusion Community work together on exploitation of ITER. ITER IO coordinates and participates in the program (e.g. Test Blanket Module program for power generation).

## Slide 24: ITER Baseline Structure
Technical scope
Schedule
Cost
Management
Council
Division
Group
ITER
DG

## Slide 25: Integral Management
Project Plan and Resource Estimate (Council level doc.)
Overall project schedule & construction schedule
Management systems for the project execution
Work plan and resources for construction
MQP (Management level doc.)
Cost & Schedule Management (Earned Value Management)
Configuration Management – change control
Procurement management – in-kind procurement by DAs
Risk Management – avoidance, reduction and mitigation
Quality Assurance – graded approach based on importance
Detailed Procedures & PA (Department level doc.)

## Slide 26: Systems Integration
System
Components
Parts
ITER System Engineering plan to define engineering processes and clarify roles & responsibilities for integration. It focuses on needs and functionality in the early stage and then integration and verification.

## Slide 27
Type or specifications
- Functional: DA for preliminary design based on conceptual design by IO
- Detailed: DA for final design based on preliminary design by IO
- Build-to-print: DA for manufacturing design based on final design by IO
Sharing of Work between IO and DA
Work sharing defined by frame chart
・ Construction：IO/DAs depending on the type of specifications
・ Transportation：IO to coordinate a global transportation
・ On-site installation/testing：IO in support of DAs
・ Project management & integration: IO

## Slide 28: Configuration Management
Main process:
Identification
Implementation
Monitoring
Review & audits
Procedures:
Requirements
Changes
Documents
Assessments
Interfaces
Database
PA
Configuration Management is the process for establishing and maintaining consistency of a product’s performance, functional and physical attributes with its requirements, design and operational information throughout its life.
Notes: 28

## Slide 29: Management of Design Requirements
The PS defines the operational features and performance required to fulfil the ITER mission.
The PR translates the top level mission requirements into engineering terms.
The SRDs define the requirements for the systems.
PS : Project Specification
PR : Project Requirement
SRD: System Requirement Document
PR
SRD
System RQs
(S-RQ)
DOORS
Project RQs
(P-RQ)
PS
Design Documents
Compliance

## Slide 30: Design Change Management
Level 3
Changes categorize and approved depending on the level of impact:
Level 0: ITER Council
Level 1: ITER DG
Level 2: ITER DDGs
Level 3: TROs
Level
0, 1 & 2
Change request (PCR) to be generated and reviewed in terms of impact on scope, schedule and cost
Changes to be managed by Configuration Control Board (CCB)

## Slide 31
ICDs
ISs stored in subfolder of ICD
Linked with a cell of ICT
Interface Management
SRD：System Requirement Documents
ICT：Interface Control Table
ICD：Interface Control Document
IS：Interface Sheet
SRD
ICT
ICD
IS
Management
per each PBS

## Slide 32
Interface Management: CMM
Examples of CMM
Simplified 3D Model based on baseline, representing space, geometry and interfaces
Layout and interface management
Tolerance analysis for different operating temperatures

## Slide 33: Risk Management
Primary Objective of the ITER Risk Management is to provide a sustainable and consistent process for the management of cost, schedule, technical, and operational uncertainty on the project.
Hazard
Schedule
Financial
Operational
Possible Risk Areas
Procurement
Vessel
Internal Components
Diagnostics & HC
Plant & Fuel Cycle
Electrical Power Supply
CODAC and IT
Civil Construction
Project Integration
Magnets
People
Technology
Process
5. Monitor, Report & Dispose
4. Develop
Response & Mitigation Plans
3.
Determine
Handling
Strategy
2.
Assess & Measure Risks
1.
Identify
Risks
Compliance
Execution Components
Managing Risk

## Slide 34: RAMI: Reliability, Availability, Maintainability & Inspectability
RAMI: Technical Risk Control program for the success and availability of ITER. The ITER RAMI program is declined in 4 stages:
  A classical Functional Analysis to identify the main functions and their possible Failures.
  An analysis of the failure modes, their cause & effects and the establishment of a Critical List according to their importance with respect to the machine operation availability (FMEA).
  Evaluation of Severity, Occurrence and Detectability levels of main failure mode causes: Criticality = S.O.D (FMECA).
  As a function of this criticality level, the risk of a failure can be considered as acceptable or not. When the risk level is too high, measures are to be taken for improvement of Design, Fabrication and Testing to reduce the risk level, and/or for an optimized Preventive Maintenance Plan and an adapted Spare Part Strategy.
Notes:   It begins with a classical Functional Breakdown to identify the main functions and their possible Failures.
  The second stage concerns the analysis of the failure modes, their effects for the system and the establishment of a List according to their importance with respect to the machine and pulse operation availability (FMEA).
  By evaluating their severity, occurrence and detectability levels, it is then possible to allot a criticality value for each failure mode (FMECA).
  As a function of this criticality, the risk of a failure can be considered as acceptable or not. The Risk level of Critical Failure Modes could be progressively reduced by providing recommendations for Design, Fabrication, Testing, and more especially, by preparing an efficient machine operation with an optimized Preventive Maintenance Plan and an adapted Spare Part Strategy.

## Slide 35
1st Confinement System
Vacuum vessel
VV extensions
etc
2nd Confinement System
Port cells
Vaults
etc
Dynamic Systems
Vent & cleanup system
etc
Vacuum vessel
Port cell &vault
Basic Safety Approach
- Confinement of Radioactive Material -
Based on the unique safety features, the safety goal will be achieved by a combination of enclosure containing radioactive material and vent/clean-up system for mitigating the consequence in case of failure of enclosure.

## Slide 36
Governmental Acts:
  Pressure equipment
  Nuclear pressure equipment
  Nuclear quality
1
2
3
4
2. Codes:
  RCC-MR (vacuum vessel)
  ASME (Sec VIII, B31.1, etc.)
  EN13445
  EUROCODE (building)
3. Standards:
  ASTM
  EN
  ISO
  ANSI, EJIMA
4. Technical specifications:
defined in Procurement
Arrangement
Codes and Standards Application
Internationally recognized codes & standards can be applied for construction but the compliance with nuclear regulation should be justified for the safety important components.