      Report from the Technical Board
        Roman Pöschl
        LAL Orsay
From FNAL to UTA
Developments since CALICE TB Review Meeting at FNAL
CALICE Collaboration Meeting Arlington/TX March 2010

---
The Corner Stones
- Concluding the “Physics Prototype Phase” - Phase CALICE I - with completion
  of the US-DHCAL and combined test beam at FNAL with the SiW Ecal and TCMT
  Roadmap issue of TB Review meeting
  NEW: Physics Prototype of W-HCAL
- Preparing/Realising the “Technological prototype phase” - Phase CALICE II
  Several prototypes moving towards construction phase
   - SiW Ecal
     New: Common effort with ScintEcal
   - SDHCAL-GRPC
   - SDHCAL with Micromegas
   - AHCAL
- Generic R&D on DECAL/MAPS

---
Towards the US-DHCAL
- US-DHCAL needs to construct 1 m2 layers with new components and newly
   developed manufacturing techniques
 - Large GRPC including resistive painting
   Reliable painting still seems to be an issue!
 - New Chip DCAL III – Mass test successful all Chips at Hand
 - New FE Boards adapted to needs of 1m2 layers
   In Test phase before mass production, 120 FE needed
 - Mastering the manufacturing process (Building of frames, Gluing of different components
   Good Progress: infrastructure settled for RPC assembly, trained staff
   Cassette integrated into Calice stack at FNAL
 - Integration of DAQ and s/w into existing calice scheme
   Intensively discussed – Modifs to trigger and timing module to handle
   event busy flag from CALICE DAQ
- First layer not yet realised but gets in sight
- TB asked for a time plan on the mass production of 120 Chambers to
  make up the 40 Layers needed
  Current goal is to have 40 layers by end of April. Challenging!!!!
- TB strongly recommended a 1st Layer integration
  Test will be done after April 1 . Requires Paul, DESY colleagues and maybe R.P. an site
   at FNAL
- Integration of the GEM structures fell a bit out of focus

---
Combined test beam – Detector Status and Constraints
- SiW Ecal
  Investigation of reason for dead areas during summer09
  on LLR test bench.
  Dead zones not reproducible)
  SiW Ecal is ready at any time to be put back into the test beam
  N.B.: In order to save travel money test beam have to be conducted
  with minimal man power on site
  Shifts via remote control room -> to be established in France
  Definition of beam test program would however need input
  from SiWEcal <-> AHCAL combined tests
- TCMT
  - Currently no funding for TCMT available
  - Detector would be run by DESY collegues with local support by NIU
    TCMT is however operational
- Beamline/Trigger
  - Commissioning by DESY with support from other testbeam participants
- Two important issues to be mentioned
   1) The stage at FNAL is unused since June 2009
   2) Due to customs regulations the stage has to be transported
       back to Europe by April 2011

---
First Steps on the Roadmap – Towards the Technological Prototypes
The aim is to build and operate prototypes as close as
   possible to what we would like to have for the ILC
- How well do the ongoing projects meet this requirement?
- What steps are needed to complete the prototypes
- Where can we act as a collaboration?
- Roadmap for technological prototype as issue of FNAL meeting
- Agreed by Steering Board at Collaboration Meeting at Lyon
  TB Review Document can found under
  http://flc.web.lal.in2p3.fr/poeschl/tb-review.doc

---
Timelines for (HCAL) Detectors - Roadmap
DHCAL
Production Phase
Testbeam Phase
1m2 “Phase”
Towards the full scale
prototype
Production and system
Check
How many layers of
each species?
Final DAQ Commissioning
During that time we
need to develop a working
interface online - offline
Large Scale Testbeam
Technological Program
to be defined
Physics Program
to be defined
Data taking rate
O(100Hz)
from VFE
Issues for
continous operation
Operation
pf 1st 1m2 in
Testbeam
Decision of Chips
in Testbeam
Check out of
Electronics
Final Layout of
Mechanics
First power pulsing
SiW Ecal enters
the game
1/7/09
1/7/10
1/7/11
AHCAL
Towards Full Module
Full Layer Phase
Prototype System
Vertical Stacking to
allow small physics
running with electrons
Running in ILC mode?
Final DAQ Commissioning
Mechanics test
Production of full module
SiPM, SPIROC et al.
First power pulsing?

---
SDHCAL GRPC and Micromegas – Towards a 1m3 protoype
GRPC
Micromegas
- successful tests with 1m2
  prototypes in 2009
  Tests with HRI, HRII
- Chamber construction under
  control
- Very interesting results with
  semi conductive glass
  -> High Rates ~100kHz/cm2
- 2010 continuation of 1m2 tests
  Power pulsing on the agenda
- Step from USB based DAQ to
  “EUDET DAQ”
- Less successful year 2009 in
  terms of beam tests
  DAQ Problems, Spark problems
- Beam tests for 2010 with 1m2
  planned
  - DIRAC or HARDROC?
- Mechanics for Chamber
  construction under control
- Flexibility for installation
  in existing or new Calice
  stack
Close collaboration at DAQ Level – DIF and beyond
Number of layers to be produced in 2010 for each variant of sensitive material
        left to committees organised in France
        (Distribution of existing funding for french contribution to SDHCAL)
        Consultance by Technical Board if desired

---
SDHCAL - Self-Supporting Structure
In agreement with recommendation of TB Review Document
Mechanical structure, parameters:
44 slots to can implement 44 MICROMEGAS or GRPCs.
Structure compose of only 2 different kinds of pieces. Attached between by M8 screws, 11+11 bolts by layer.
plus base support pieces and the manipulation fixations (By 2 bolts of M20), only can be fixed elements to the bar pieces.
Extrapolation of the m3 module philosophy for the ILD (One Proposal!!!)

---
AHCAL – Towards a Technological Prototype
Mech.
structures
horizontal
vertical
Status and Planning:
- First HCAL HBU in DESY Testbeam
- Full slab end of 2010
- “Vertical Test” in 2011
   Stack will be equipped vertically for tests with electrons (DESY?)

---
 W-HCAL
- Hadronic Calorimeter using Tungsten Absorber
  Driven by High energy needs
- Will use sensitive parts from existing analogue (steel) Hcal and
   Micromegas
- So far no monitoring in Calice-TB
  Plans only presented at Collaboration Meeting
  Regular reports to calice-tb will start after UTA Meeting
- Plan for considerable testbeam in September 2010 at CERN PS

---
SiW Ecal
Composite Part
with metallic inserts
(15 mm thick)‏
Prototype of VFE
Thickness : 1 mm
FEV5
- Progress in VFE Electronics
  SKIROC Chip sent(?) to foundry
  Corean partners for FEV8 board
  Tests with SPIROC
  and FEV7 (ASU by end of 2010)
- Progress in DAQ.
  Communication to DIF via LDA
  Next step communication with
  actual VFE
- SiW Ecal Layers mid 2011?
- Testbeam late 2011 early 2012
   should plan for progressive
   tests
550 mm
1510 mm
182,1 × mm
182,1 × mm
7,3
9,4
550 mm

---
        Demonstrator 2009
- Detector module realised (from mechanical point of view)
- Demonstrator subject to a thermal test
1300mm

---
Collaboration SiW-Scint Ecal
Initiated by TB-Review Meeting
Composite Part
with metallic inserts
(15 mm thick)
Heat shield: 100+400 µm
(copper)‏
PCB: 1200 µm
PCB: 1200 µm
Thickness : 1 mm
glue: 100 µm
glue: 100 µm
Kapton ® film:
100 µm
wafer: 325 µm
wafer: 325 µm
ECAL W/Scin
Heat shield: 100+400 µm
(copper)
Wstruct
Composite Part
(2 mm thick)‏
PCB: max. 1200 µm
(with FE embedded)
- Alveolar structure applicable for both
  Ecal proposals
- Details on integration are currently
   worked out.
   Communication SiW Ecal-ScintEcal-DESY
- Schedule to be precised in coming months
MPPC
Wslab
« X » strip
2000 µm
« Y » strip
2000 µm
545 mm
186 mm
182×7,3 mm
182×9,4 mm

---
Reducing the Cost of the (ILC) Ecal
The CALICE TB endorses to use the years 2010 and 2011 for the R&D of wafers at lower prices and extensive
studies of the Si market. This is also vital for the realisation of a SiW calorimeter for an ILC detector.
- Hybrid Ecal might be one solution to master cost of Ecal w/o performance
  penalty
- Still silicon cost need to be controlled
  - Forging closer contacts with industry
    LETI France
    Hamamatsu Japan
More details by JCB

---
MAPS – DECAL - Spider
Since TB Review DECAL is regularly on the agenda of CALICE TB
SPIDER
Silicon Pixel Detector R&D
Remnants of CALICE-UK DECAL group and LCFI
“Generic” pixel detectors for future colliders
Struggle a lot with disastrous funding situation in UK
DESY Testbeam March 2010
- Efficiency for different sensor variants
- Shower densities in electromagnetic showers
- Program after April 2010 entirely uncertain

---
Status of DAQ for Technological Prototypes

---
Status of DAQ for Technological Prototypes
- Hardware provided by UK groups – Now start of operation
  So far it looks alright, but devil is in the details
  Drop out of UK groups essentially caught by french groups
  Transfer of information works smoothly (still clearly deplorable situation)
  Remarkable effort of UK groups to remain in business
- SDHCAL DAQ: first working chain running in may/early summer of 2010
   Stress tests during summer early autumn 2010.
    1m2 prototypes of the SDHCAL are read out by USB based DAQs
    need to complete step towards Ethernet/HDMI DAQ
- New Groups for DAQ Tasks?
  Though impressive progress, SiW Ecal is at risk (depends on one person)
  Slow control for Ecal (and other prototypes)?
- Which s/w frame for DAQ piloting to choose?
  DOOCS. XDAQ, Tango?
Decisions to be taken until Easter!!!!
m

---
Status of FEE
Production Run March 2010
Reticle : 22 x 18 mm2, 50 reticles per wafer
25 wafers produced,
- SKIROC for Ecal is integrated
  => Back in phase with other chips <-> Compliant with TB Review
More details in Electronics Session

---
CALICE Software
- New Software Coordinator Angela Lucaci-Timoce
  Proven already to be very competent
- Contacts for subdetectors (CALICE I):
  SiW Ecal: K. Krastev, R.Poeschl
  ScintEcal: Cotera (?)
  AHCAL: Angela herself
  (S)DHCALS: ??? (Fate of task force initiated by Niels)
  TCMT: K.Francis?
  Tracking: P. Dauncey, D. Jeans (?)
  Simulation/Mokka: G. Musat
- Data Processing: Support by A. Kaplan, N.Feege, L. Weuste and S. Lu
   Lack of man power for mass production
   Data processing on request
- CALICE s/w needs to be put on broader basis
  Efficient s/w group is essential for publishing physics results

---
Towards s/w for Technological Prototypes
Readout reassembly simulation
  - Uses SystemC + low-level routines
1 ROC
“f” frames
And Then?
   Interface
online/offline?
Data Format
Ideas for SDHCAL
LCIO
ROC
Data
Events
ROC
chains.
ODR
pkts
Scheme by D.Decotigny (LLR)
Needs tight communication between DAQ team, CALICE Software Team
        and ILC Coresoftware Team
        Considerable Task for 2010

---
Testbeam planning for 2010
CALICE Requests for 2010 to FNAL
No dedicated request or MOU so far
Further steps depend largely on readiness of DHCAL Phys. Prototype
CALICE Requests for 2010 to CERN
GRPC SPS 2 weeks July and November Test of 1m² Chambers H2(Magnet)/H4/H6 PS 2 weeks May T9 beamline
Mmegas 2 weeks June/July Test of 1m² Chambers H2/H4 beamline
W-Hcal PS 2 weeks 4th quarter 2010 Hadron Calo 1m³, 1 ton?? T9 beamline
(Spider June/July (preferred) Pixel Ecal Calo 30x30x30cm³ H6B (EUDET Tel.!))
- Not entirely happy with preliminary CERN response
  CERN beamlines are very crowded!!!
- 2 main issues
 - Solve situation for 2010 quickly
  - Prepare planning for 2011 and beyond now!!!
    Tight communication with CERN on CALICE/LC needs to/about to be established
    Topic at today's TB Meeting

---
Testbeam Planning beyond 2010
Table published in DESY-PRC Report (also arXiv: 1003.1394 phys.ins-det, hep-ex)
 - No Activity
 x Small Activity
xx Large Scale Testbeam
- Large Scale 2011/1 – 2012/2, SDHCAL/AHCAL+ECAL at CERN (most likely)
  Needs several weeks/months steady occupation of beam line
  Table does not take W-HCAL into account (also large scale TB)
- Other LC Detector Components
  TPC do also plan large hadron testbeams, preferrably also at CERN
- Need good coordination among ourselves, with other LC projects
  and facility managers (not only CERN).
- Key issue in LCTW09 document and at today's TB Board

---
Summary and Conclusion
- CALICE continues to have a rich R&D program and enters
  a phase in challenging technologies for (I)LC faces their realisation
  It is explicitly in the interest of CALICE to investigate several detector
  technologies
- Landscape is very heterogeneous
  8 different Technologies (Absorber or Sensitive Medium)
  Up to six large scale prototypes which will be employed
  Yet, nice examples for collaboration in R&D beyond “boundaries”
  However, also counter examples
- Many items addressed at the TB Review meeting are transformed into action
- TB will continue to monitor all efforts and streamline activities
- TB will be in first line to realise longer term planning
  - Availability of Testbeam lines
  - All beam test efforts should be launched via TB (or at least TB needs to be informed)
- TB will support steps towards DBD
   - Priority list
   - Prepare judgement on maturity of detector technology
     Need charge by steering board on exact measures
It should be CALICE who decides which technology is mature and which is not