## Slide 1: Cryomodule Test Bunker for ILC Technology Network (Cryogenic systems)
K.Nakanishi, K.Hara, T.Honma, S.Kessoku, H.Nakai, H.Shimizu
(refrigerator group)

## Slide 2: What is ITN.
ITN:ILC technology network
The ILC project has not started yet.
Technological development should be continued.
ITN is an international initiative comprised of many bilateral collaborations.
For WP1 and 2, one cryomodule will be built and that performance will be measured.
From AFAD2023

## Slide 3: Step of ILC development
The ILC project will be done in the following steps.
ITN 8cavities 1 cryomodule 5 years  New!!
Prelab 120cavities 4~6cryomodules 5 years
ILC construction 8000cavities 900cryomodules 10years
⇨ILC operation
ITN
1 cryomodule including 8cavities will be made.
A low-temperature experimental facilities will be established to measure the cryomodule.
Prelab
40 cavities and 1~2cryomodules will be made in Japan.
4~6cryomodules including foreign cryomodules will be tested.
1cavity/week, 1~2cryomodules/year  easy!
ILC construction
The first 5% of cryomodules will be inspected in Japan.
1/3 of cryomodules made in Japan are inspected at random.  totaly140cryomodules
2500cavities will be made in Japan. More than 2500 times of VT should be done.
5~cavities/week , 1~2cryomodules/month(In case of 100% inspection 8cryomodules/month)
Not very difficult. But efficient operation should be realized.

## Slide 4: Schedule of ITN
 | 2023 | 2024 | 2025 | 2026 | 2027
CE(LN2 tank) replace | Done |  |  |  | 
Helium purifier |  | 〇 |  |  | 
Control system update |  | 〇 | 〇 | 〇 | 
Change HPGS category. (He Liquefier) |  |  |  | 〇 | 
Liquid helium transfer line |  | design | 〇 | 〇 | 
2K refrigerator |  | design | 〇 | 〇 | 
Pump (warm compressor) | Done |  |  |  | Add?
CM test

## Slide 5
Pumps arrived
CE was upgraded
New bigger CE
Installed He buffer tank (used)
Old CE
(liquid nitrogen tank)
Vacuum pump for 2K refrigerator:
Tests will be conducted.
(noise, vibration, mass flow …)

## Slide 6: Items to be done
CE (liquid Nitrogen storage tank) upgrade
Add a helium tank
Control system update for liquefier and 2K refrigerator
Prepare helium purifier
Change the category of HPGS of Helium refrigerator
(General  Refrigerator)
Build liquid helium transfer line (TRT)
Build 2K refrigerator
Prepare vacuum pump for 2K refrigerator
(Regulation on Safety of General High Pressure Gas)

## Slide 7
Schematic view of the 2K refrigerator
FM : Flow Meter
Transfer Line

## Slide 8: Layout of COI building
3
1
Candidates of pump site
The root of transfer line was decided.
The pump site for 2K refrigerator is not decided.
Helium purifier
(if possible)
2
Transfer line and return line.
The length is about 100m
CTB should be established here due to the floor strength.

## Slide 9
4 pipes are contained in the transfer line.
One pair(outside) is for cooling the radiation shield.
Another pair(inside) is for handling the liquid helium.
This is based on the KEKB’s TRT design.
Since liquefied nitrogen is not used, the pipes for shielding are larger. And the supply pipe is not in contact with the shield.
Chart: Position[m]
Chart: Position[m]
Flow rate = 3g/s
80K
300K
He transfer line design
Calculated its characteristics.
Gas velocity and pressure are acceptable.
Temperature distribution at the start of cooling
TRT: The design is almost complete.

## Slide 10: Transfer line
40K Supply
80K Return
LHe(5K) Supply
8K Return
150A(O.D.=165.2mm)
O.D.≒100mm
80K:the surface area is about 30m2.
If more than 10 layers of SI are installed, the heat load is about 70W
5K:heat load is about 10W.(less than 0.1W/m)
Crane girder

## Slide 11
40~80K shield
Cavity (2K)
5K shield
We negotiated with the manufacturer of the He refrigerator.
The logic that controls the turbine has not been exposed.
The manufacturer want to keep the control of three valves.
Valves used for turbine control
Control system update
For precooling

## Slide 12
Control system update
Refrigerator control system
(manufacturer’s (OS:VxWorks))
EPICS base control system
(KEK’s (OS:Linux))
Accelerators are controlled by EPICS.
These control system use same platform.
They can be merged.
FY2024:Programming test ☺
FY2025:Construction
FY2026:Operation test
Our refrigerator control system at cERL

## Slide 13
The HPGS category of the refrigerator dewar and buffer tank must be changed.
Our local government(Ibaraki-ken) only requires pressure test and Airtightness test.
Devices which managed by different categories of HPGS can not be connected. STF and ITN-CTB system must be separated.
HPGS category will be changed

## Slide 14
Refrigerator
LR280
(300L/h
or
600W)
Max:190kg
Gas bag
Max:190kg
Recovery Compressor
Dewar
(3000L)
(=380kg)
Cryostat for vertical test
Purifier
Gas bag
Purifier
Dewar
ITN
Pure He
Dirty He
Cut here in FY2026
Cryomodule for ILC
Buffer tank
(100m3)
190kg
The HPGS categories of STF accelerators and ILCs are different.
Under Japan law, devices of different categories cannot be connected, so ITN should be separated from STF.
The red frame shows equipment that uses liquid nitrogen.
Pump
Refrigerator TCF200
Buffer tank
(46m3)
50kg
STF
Installed
To purchase in FY2024
STF Accelerator
Separation of ITN cryogenic system from STF
The red frame indicates equipment that uses liquefied nitrogen.

## Slide 15
Refrigerator
Purifier
Pure He
Buffer tank
100g/s
95g/s
5g/s
It should be used before operating the helium refrigerator.
The buffer tank has a capacity of 100 m3 and is filled with about 1.0 MPa.
The impurity concentration decreases by e^(-t/τ).
If the flow rate is 5 g/s, the time constant(τ) is about 12 hours.
Dirty He
This device will be purchase in FY2024
Helium purifier
HPGS for refrigerator does not allow to use gas bag and recovery compressor.
Middle pressure purifier should be installed.

## Slide 16: Cooling capacity
When 40K gas is used 20g/s, the cooling capacity becomes half. Thus, the capacity of this cooling mode is 40g/s. We called that cooling mode parasitic mode.
Assuming a temperature rise of 40 K, the cooling capacity per 1 g/s is 200 W.
Capacity of refrigerator:
Parasitic mode : 40g/s
→40×200=8kW
Refrigerator mode:
600W
→Maximum 4K heat load is 600W
Liquefier mode:
250L/s 0.7J/L : latent heat 0.9 : wetness at just after JT valve
→ Maximum 2K heat load is 150W
250×0.7×0.9≒150W

## Slide 17: Summary
Cryomodule test station is being prepared.
CE (liquid nitrogen tank) and He buffer tank were extended.
Liquid Helium transfer line and 2K refrigerator is being designed and will be prepared from 2025.
The test station will be operated in 2027

## Slide 18: Cooling capacity
Heat load:
12W@2K 12/150=8%
16(CM)+10(TRT)W@5K 26/600=5%
134+70W@40K 204/8000=3%
Total 16％
If the estimation of heat load is correct, the refrigerator is powerful enough.

## Slide 19: Cold mass and heat load
40~80K region
Aluminum 320kg, Stainless 2500kg
In TDR, Static:75W, Dynamic:59W, cooling capacity : 8kW(Parasitic mode)
5K
Stainless 200kg
Static:11W, Dynamic 5W, cooling capacity : 600W(refrigerator mode)
2K
Stainless 750kg, Niobium250kg, Titanium 150kg, Cupper 420kg
Static:1.3W, Dynamic 10W, cooling capacity : 200W(liquefier mode)
The heat loads of TRT are smaller than the static heat loads of a cryomodule at 40K and 5K, respectively.