## Slide 1
ILC CFS & GLOBAL SYSTEMS MEETING
CONVENTIONAL FACILITIES
AND SITING GROUP
CFS Status Report
V. Kuchler, J. Osborne, A. Enomoto

## Slide 2
Overview
  Update from Previous Meeting
  CFS Planning Toward the DESY AD&I Meeting
  CFS and the EDMS System
  CLIC 09
  Summary

## Slide 3
Update from Previous Meeting
  AD&I Central Region Layout
    A New Machine Layout has been Developed and Provided to the CFS Group by N. Collomb
    A Preliminary 2D Enclosure Layout has been Developed at FNAL and Initially Reviewed for Accuracy
    In the Current Layout, the Main Linac Dumps and Fast Aborts Point Away from the Damping Ring
    While the Beamline Layout will Remain Unchanged, the CFS Group is Investigating Repositioning the Service Tunnel to the Damping Ring Side of the BDS Tunnel
  Klystron Cluster and DRSF Alternatives
    Each Region has Developed a Preference for the RF System that is More Appropriate for the Regional Application
    This, as Well as Other Factors, will Affect the Details of the CFS Enclosure and Cavern Layout in Each Region

## Slide 4
CFS Planning Toward the DESY AD&I Meeting
  The CFS Group at FNAL is Leading the Analysis of the New Beamline Layout with E. Paterson and M. Ross
  A New 2D Drawing is Being Developed, Based on the New Beamline Layout, at FNAL
  When Finalized, the New 2D Enclosure Drawing will be Made Available to the Area System Representatives for Review
  Each Region will Develop a 2D Layout that Reflects Local Geologic Configurations, Life Safety Criteria and RF System Preference
  Each Region will Develop 3D Enclosure Layouts, but the European Region will Provide the 3D Enclosure Information for the Overall 3D Machine Drawings Being Developed at DESY
  FNAL (M+W Zander) will Provide the 3D Drawings for the Mechanical and Electrical Support Systems for the Overall 3D Machine Drawings

## Slide 5
CFS EDMS Effort
  At ALCPG 09 a Parallel Session was Held to Review the Current Status of CFS Members w/Respect to Accounts and Needed Password Revisions
  Las Hagge is Currently Providing the Necessary Password Updates and Accounts that are Needed for the CFS Group
  The New Beamline Layout and CFS AD&I Layout will be the First Documents Posted into the EDMS System by the CFS Group
  Don Mitchell will Provide Help as Needed to the CFS Group for the Utilization of the EDMS System

## Slide 6
CLIC 09 Collaboration Meeting
  CLIC 09 Collaboration Meeting was Held at CERN Last Week
  Much of the Discussion Centered of the CLIC Design, However Tunnel Diameter, Life Safety and Egress and Ventilation Issues Remain Common to Both the CLIC and ILC CFS Design Solutions
  The European Region Continues to Prefer the Klystron Cluster RF Scheme

## Slide 7
Summary
  Work is Proceeding Toward the Development of a New CFS Enclosure layout Based on the Newest Version of the ILC Beamline Layout
  Once Established and Reviewed, the New Layout will be the Basis for the AD&I Proposal
  The New Layout will Also be Used to Develop Regionally Specific Layouts for Each Sample Site
  CFS will Continue to Utilize the EDMS System as the Review Tool for CFS Documentation