## Slide 1: SCRF WebEx Meeting focusing on Preparation for S1-Global
2009-11-11
Preparation for S1-Global (100 min)
SCRF general issues (20 min.)

## Slide 2: 1. S1-Global Cooperation and Preparation
Objectives of the Meeting, Today:
  Report the preparation and
  Confirm the work-sharing/cooperation
Agenda
  S1-Global General Plan (A.Y.)
  Cavity/cromodule preparation: FNAL, DESY, KEK, INFN
  Integration work at KEK and work-sharing plan: (E.K., N.O.)
  Q&A, and Further work-assignment

## Slide 3: 2. SCRF General
Preparation for the AD&I
  SB2009 document, and DESY meeting, Dec. 2-3,
  Cavity gradient (operational) to be re-evaluated by Quarter-1, 2009
Preparation for AAP Review
  at Oxford, Jan. 6-8, 2010,
Next SCRF meeting
  Dec. 9, 2009: last meeting before SB2009, AAP

## Slide 4: Global Plan for SCRF R&D
Year | 07 | 2008 |  | 2009 |  | 2010 |  | 2011 | 2012
Phase | TDP-1 |  |  |  |  |  | TDP-2 |  | 
Cavity Gradient in v. test to reach 35 MV/m |  Yield 50% |  |  |  |  |  |  Yield 90% |  | 
Cavity-string to reach 31.5 MV/m, with one-cryomodule |  | Global effort for string assembly and test (DESY, FNAL, INFN, KEK) |  |  |  |  |  |  | 
System Test with beam acceleration |  |  | FLASH (DESY) , NML (FNAL) STF2 (KEK, extend beyond 2012) |  |  |  |  |  | 
Preparation for Industrialization |  |  |  |  | Production Technology R&D |  |  |  | 

## Slide 5
Revised Schedule of Cavity Assembly
KEK
DESY
& FNAL
String
Assembly
String
Assembly
Tuner
Installation
Tuner &
Mag. Shield
Installation
TTF-3 Warm Coupler
Installation
STF-2 Warm Coupler
Installation
Nov. 10, 2009

## Slide 6
Cryomodule Tests Plan
Low RF Power Measurements
Slide-Jack Tuner stroke
Piezo tuner stroke
RF meas. (QL, Qt, QHOM)
HOM Qext
Frequency stability
Mechanical vibration modes
Pulse response by Piezo drive
etc.
High RF Power Measurements
RF meas. (QL, Qt, QHOM)
Cavity conditioning with 1.5 ms
Cavity conditioning with 0.6 ms
Mechanical vibration modes (5Hz)
RF feedback on/off by LLRF
Observation of Lorentz Detuning
Compensation of Lorentz Detuning
Dynamic RF loss measurement
4 Cavity operation with vector-sum
8 Cavity operation with vector-sum
Long time operation at 31.5 MV/m
etc.
Coupler conditioning
at room temp.
Nov. 10, 2009

## Slide 7
KEK visit of Jim Kerby (FNAL), 10th -12th, Nov.
Video/Webex meeting for S1-G preparation
pm.10:00~12:00 in 11th, Nov. at KEK,
in participation of DESY and FNAL colleagues
Main topics on discussion;
(Share of collaboration works for S1-G)
. Cavity string assembly
. Tuner & mag. shield assembly
. Tuner testing
. Input coupler assembly (warm parts)
. Conditioning of input coupler at room temp.
. etc.
Meeting for S1-G preparation

## Slide 9: Cavity- and Cryomodule-String Program (S1G, S2) at KEK, Japan
C. Year | 2008 | 2009 | 2010 |  | 2011 |  | 2012 |  | 2013 |  | 2014
Cavity String (S1-Global) | Cavity | >> | Ins | Test |  |  |  |  |  |  | 
Cryomodule String Test (S2) | *High Pressure Code Regulation/Stamp to be applied |  |  |  |  |  |  |  |  |  | 
Quant. Beam* (Compact L.S.) |  | Cavity | >> |  | Inst. | Test |  |  |  |  | 
Cryomodule 1* |  | Cavity | >> |  | >> |  |  | Ins & T |  |  | 
Cryomodule 2,3* |  |  | Cavity |  | >> |  | >> |  |  | Ins | Ins & T
 | Technical Design Phase |  |  |  |  |  |  |  | Development to be continued |  | 
R&D/Prepare for Industrialization

## Slide 10
Contract.
KEK-STF: Long Term Plan
S2 (STF-Phase2)
EBW
2009
2010
2011
2012
2013
2014
Jacketing
Op
VT
HPC-Ins.
Ass
9 Cac. Fab.
Fab.
Installation, Assembly
CY
Cab. Fab.
Cav. Product. R&D
(by Ind. & KEK)
(EBW parameter，etc.)
2015
CM1
V. Test
Ass
8 cav. Fab.
CM2
V. Test
4+5 cav. Fab.
CM3
Op.
運転
S1 Global
Q. Beam
運転
Jacketing
Op.
VT
Ass
2 Cav. Fab.
VT
Op
Ass
Pilot Plant
GDE-TDP2
Ass.
Op.