## Slide 1: S1G Experiment Schedule Plan
02102010 H. Hayano

## Slide 2
Assembly work after cavity arrival
（１）check the listed component
（２）review the assembly procedure with arrived components
（３）cavities connection in clean-room, leak check
（４）He pipe welding at outside clean-room, leak check
（5）Tuner and mag. shield assembly at outside clean-room
（6）Cavities installation into cold-mass
（7）Temp. sensor, RF cables
（８）thermal anchor, super-insulator, installation into vacuum vessel
（９）Installation into STF tunnel
8 weeks
Module C (INFN module)
Module A (KEK module)
9 weeks
2010.01~2010.02
2010.03~2010.04
same procedure as phase1 cavities
Connection work of Module C (INFN module) and Module A (KEK module)
in STF tunnel
4 weeks
2010.05
Start immediately after clean-room available

## Slide 3
S1G overall schedule
6
7
8
9
10
11
12
1
2010
2011
cryomodule connection
Module-C
coupler + cavity process
(one-by-one)
S1G experiment term1
Cryogenics
regular maintenance
S1G experiment term2
Module-A
coupler+
cavity process
（one-by-one）
Module-A
coupler RF process
（one-by-one）
11 weeks S1G main experiment
warm-up
cool
down
cool down
Module-C
coupler RF process
(one-by-one)
heat load meas.
(1week)
cavities:
low-power check
(6weeks)
Parallel operation of RF power
station #1 and #2
Only LN2 will be Continuous full day operation.
LHe operation will be daytime only.
Monday : 2K cool-down,
Tuesday – Friday : 12:00 – 19:00
7hours for S1G experiment at 2K.
heat load meas.
(2weeks)
4 weeks
7 weeks
4 weeks
ICHEP2010
July21-28,Paris
Domestic Accelerator Meeting
Aug 2010
IPAC2010
May23-28, Kyoto
LINAC2010
Sep12-17, Tsukuba
cryomodule
disassemble
setting of power
distribution
warm-up
DRFS test.
(1week)
coupler&
cavity
process
coupler RF
process
vector-sum
(4weeks)
cavity setup
(4weeks)

## Slide 4
June 2010
July 2010
cool down
warm-up
cavity: low-power check
cavity: low-power check
cavity: low-power check
cryomodule: heat-load meas.
cavity: low-power check
warm-up
S1G schedule 1
cavity: low-power check
cavity: low-power check
Mon
Tue
Wed
Thu
Fri
Sat
Sun
Mon
Tue
Wed
Thu
Fri
Sat
Sun

## Slide 5
Aug. 2010
Sep. 2010
coupler RF process (room-temp.)
cool down
cool down
coupler RF process (room-temp.)
coupler RF process (room-temp.)
coupler RF process (room-temp.)
Cryogenics
regular inspection
coupler+cavity RF process
coupler+cavity RF process
coupler+cavity RF process
coupler+cavity RF process
S1G schedule 2
Mon
Tue
Wed
Thu
Fri
Sat
Sun
Mon
Tue
Wed
Thu
Fri
Sat
Sun

## Slide 6
Oct. 2010
Nov. 2010
cavity performance study, LD compensation
cavity performance study, LD compensation
cavity performance study, LD compensation
cavity performance study, LD compensation
Vector-sum operation
Vector-sum operation
Vector-sum operation
Vector-sum operation
Cryomodule Heat-load meas.
S1G schedule 3
Mon
Tue
Wed
Thu
Fri
Sat
Sun
Mon
Tue
Wed
Thu
Fri
Sat
Sun

## Slide 7
Dec. 2010
Cryomodule Heat-load meas.
Cryomodule Heat-load meas.
DRFS test
warm-up
warm-up
S1G schedule 4
Mon
Tue
Wed
Thu
Fri
Sat
Sun

## Slide 8
1. : Low power measurement of each 8 cavities. (cavity people)
measurement and set up of cavity; Q-values, frequency, main coupler coupling
mechanical tuner response, piezo tuner response, mechanical vibratino mode, HOMs, etc.
2. : Heat load measurement （static） (N. Ohuchi and H. Nakai)
6 weeks (2010.06-07)
1 week (2010.07)
S1G experiment term1 : 7 weeks
before summer shut-down

## Slide 9
1. : Main coupler RF process of one by one. (cavity people)
#1 Klystron will be connected to Module-C cavities one-by-one (DESY cavity, FNAL cavity)
#2 Klystron will be connected to Module-A cavities one-by-one (MHI cavities)
Parallel coupler processing one + one /week; total 4 weeks.
4 weeks (2010.07.26-08.27)
Cryogenic system in maintenance and yearly inspection,
KEK also has 2 days yearly electronic system maintenance
( 2 days AC power off laboratory-wide)
Summer holiday season.
S1G experiment term summer shutdown : 8 weeks
2. : Main coupler + Cavity RF process of one by one. (cavity people)
#1 Klystron will be connected to Module-C cavities one-by-one (DESY cavity, FNAL cavity)
#2 Klystron will be connected to Module-A cavities one-by-one (MHI cavities)
Parallel coupler+cavity RF processing one + one /week; total 4 weeks.
at room temperature
at 2K temperature
4 weeks (2010.09.06-10.01)

## Slide 10
(0) Optimization of Waveguide distribution (power distribution ratio) (HLRF group）
(1) Set-up of FF-table, preparation of vector-sum circuit （LLRF group）
2. : Vector-sum operation
Set-up of vector-sum, high gradient operation by vector-sum LLRF control
1. : cavity performance study, set-up of LD compensation for each cavity
3. : Cryomodule Heat-load meas.
Static and dynamic heat-load
4 weeks (2010.10)
4 weeks (2010.11)
2 weeks (2010.12)
1 week(2010.12)
gradient check, LD measurement and compensation
4. : DRFS test
Connect 1 small klystron to two cavities in tunnel, LLRF also in tunnel.
S1G experiment term2 : 11 weeks

## Slide 11: Proposed WG Layout for S1 Global
module-C
(DESY,FNAL cavities)
module-A
(KEK cavities)

## Slide 12
DRFS Demonstration
DRFS Demonstration test is approved for 1 week period. 1 unit of DRFS is
Planned to be manufactured in FY2009.

## Slide 13
overall control configuration of S1Global module
RF signal generation
timing generation
Modulator
cavity
PIEZO HV driver
Tuner motor driver
Vacuum,
Temp, RF monitors
Digital LLRF
klystron
klystron
driver amp
RF-SW on/off control
(RF amplitude reference)
(RF phase reference)
scopes
STF-net
cryomodule Temp
monitors
cryomodule
PIEZO signal
generation

## Slide 14
cavity
PIEZO HV driver
Tuner motor driver
Vacuum,
Temp, RF monitors
cryomodule Temp
monitors
cryomodule
digital LLRF
LAN (STF-net)
Klystron#2 station
(surface)
S1G cryomodule
in tunnel
Temp
Feed-through
for Temp
Feed-through
Feed-through
T-tube extension
RF power meter
RF monitors
tuner motor
tuner PIEZO
RF cables
PIEZO signal
generation
vector sum
control
pulse motor drive wire
PIEZO HV coaxial cable
RF cables
control racks in surface
control racks in tunnel
pulse motor drive wire
HV coaxial cable
*black indicates
KEK coverage

## Slide 15
END