## Slide 1: Single cell coordination

## Slide 2
Single Cell Cavity Activity Outline
ANL EP optimization (TE1AES005)
R&D cavities A. Tumble, 2 cavities (TE1ACC004, NR-6, TE1CAT001, TE1CAT002) B. Laser re-melting, 2 cavities (TE1ACC003) C. CMP process, 1-2 cavities D. ECS investigation, 2 cavities (TE1ACC005, TE1ACC006) E. manufacturing optimization, 2 cavities F. Atomic Layer Deposition (ALD) cavities
  G. Traveling wave cavity, 2 cavities (TW1AES001, TW1AES002)
Vendor qualification RRCAT Collaboration, 2 cavities (TE1CAT001, TE1CAT002)
ABLE EP 2 cavities (NR-4)
Infrastructure support Furnace verification, 1 cavity. (completed) Diode T-map and second sound development 1 cavity (TE1ACC001) ANL HPR water verification 1 cavity (TE1ACC001)
Basic R&D
A. EP cavity Q-slope studies
B. General Q-slope studies (TE1AES002)

## Slide 3
Number | Current location | Main purpose | Latest Activity | Current status | Notes
TE1AES004 | ANL | Equator quenching, T-map |  | In queue for HPR/assy. | 
TE1AES005 | ICB | CMP, EP, ABLE |  | To be HF rinsed | 
TE1ACC001 | ICB |  |  |  | 
TE1ACC002 | CABOT | CMP |  | RF test done, to be polished at CABOT | 
TE1ACC003 | A0 | laser remelting | RF test | A0 2nd sound, surface molding | 
TE1ACC004 | ICB | Tumbling | Inspected/replicated | To ABLE EP | 
TE1ACC005 | ICB | Eddy current scanning | Molding | Optical inspection and one final EP (40micon) | 
TE1ACC006 | ICB | Eddy current scanning | Molding | To be progressive EP | 
NR-1 | ANL | ANL RF commissioning | RF tested |  | 
NR-4 | ABLE | ABLE EP | RF tested | One more RF test for Q-disease study | 
NR-5 | FNAL/ICB | E-beam remelting on Pit |  | inspected, to be processed | 
NR-6 | FNAL/ICB | Tumble | Tumble polishing | In queue for EP | 
TE1PAV001 | PAVAC |  |  | three inside weld | This wk
TE1PAV002 | PAVAC |  |  |  | 
TE1PAV003 | PAVAC |  |  |  | 
TE1PAV004 | PAVAC |  |  | Three normal weld | 
TE1PAV005 | PAVAC |  |  |  | 
TE1PAV006 | PAVAC |  |  |  | 
TE1CAT001 | ICB | RRCAT collaboration | Tumble polishing | In queue for EP | 
TE1CAT002 | ICB | RRCAT collaboration | RF test | Visual inspection | 
TW1AES001 | ICB | Traveling wave prototype |  | Cavity inspection, Tooling design for BCP | 
TW1AES002 | IB1 | Traveling wave prototype |  | Cavity Inspection | 
Single cell list

## Slide 4: For two weeks
TE1ACC003 (Laser)
  Create a low field quench pit, test before & after laser re-melting.
TE1ACC005&006 (ECS)
  Replica done, brief inspection, then in queue for EP (ANL)
TW1AES001&002 (traveling wave)
  TW2 scheduled for RF test(IB1)
  TW1 optical inspection
TE1CAT001/NR-6 (Tumble Polishing)
  In queue for 40 µm EP, H-bake, 20 µm EP, RF test
TE1CAT002 (RRCAT collaboration)
  Tumble polishing
TE1AES004 (basic SRF)
  in queue for HPR/Assy. after shutdown (ANL)
NR-4 (ABLE electropolishing)

## Slide 5: Cavity performance
ANL furnace

## Slide 6: ANL spoke resonator example
Hydrogen bake out in that furnace improved the cavity Q
ANL furnace