## Slide 1: Accelerator Systems TAG Leaders Meeting 21.05.2010
News from Project Management
  Recent PAC review Ewan
  R&D Plan for TDP-2 Nick
  Planning for BAW-I (09.2010) Akira
  Planning for BAW-II (01.2011) Marc
TAG status reports
  Positron source Jim
  BDS/MDI Andrei
  Simulations Kiyoshi
ADI meeting schedule
AOB

## Slide 2: TDP-2 R&D Plan
Goal: Updated R&D Plan for TDP2 to be released end of June
  Rel 5 will be a major revision
PM:
  Understanding primary goals and identifying themes
  Focus now strongly on TDR (see next slide)
  Updating resource tables
  Identifying critical areas where additional resources are needed
TAG leaders
  Review/revise critical R&D milestones
  Review/revise Appendix B sections
For AS propose to set-up 1-1 WebEx meetings to work though these
(over next weeks)

## Slide 3: Six Themes to Develop
SCRF Technology
Regional expertise, global Industrialisation
Average accelerating gradient
AD&I (CFS)
Consolidation of baseline(s)
Design choices (parameters, layout etc.)
Cost & Schedule
ICET (schedule tool)
TDR Risk
Cost (cryomodule, mass-production models)
Design work (documentation)
Justification
R&D (and engineering) beyond 2012
Impact (design, cost, schedule)
Mitigation (fall-back solutions)
Traceable, defendable
R&D (General)
Sources
DR (e-cloud)
BDS / MDI
>2012
Remains special case
Project Implementation Plan
Industrialisation
in-kind contribution models
Site requirements
Project Schedule
Remaining Technical activities

## Slide 4: Comments on TDR
Themes probably reflect TDR outline
Major difference to RDR will be inclusion of R&D
  not just a design report!
Updated design elements including updated cost estimate
  Driven by AD&I effort (requirements for CFS)
  For AS needs documentation milestones
    what documents when
    EDMS
Cost Update
  Expected to be focused on SCRF (industrialisation models) and CFS update (AD&I)
  However this is only 70% of the RDR cost
  Needs plans to update where possible the AS RDR cost basis
    Focus on what has changed (RDR → TDR)
    Consolidating the documentation and link to cost estimate
    Scope of this activity will be severely resource limited
Notes: Understanding from AS perspective how much we can do will be subject of 1-1 interactions. Note lack of “Technical Groups” that we had in RDR.

## Slide 5: 1st BAW Announcement distributed, May 3, 2010
Date: Sept. 7 – 10, 2010
Place: KEK
Subjects:
  Single tunnel HLRF systems (Sept. 7 – 8)
  Accelerating gradient (Sept. 9-10)
Announcement
  Distributed to GDE mailing list including physics/detector executive members,
URL and Indico Agenda including registration
  To be prepared in cooperation with GDE secretariat and KEK LC-office,

## Slide 6: Subjects to be discussed Accelerating Gradient
Strategy for gradient improvement (R. Geng, H. Hayano, and collaborators)
  Material, fabrication, surface process, instrumentation & reparing,
  Strategy to overcome ‘quench’ and ‘field emission’,
  Improvement of gradient and successful production yield,
Strategy for accelerating gradient in ILC (Experts TBD and A. Yamamoto)
  Overview of the production yield progress and prospect including gradient spread
  Specification of Gradient, Q0, emitted radiation, resulting in cryogenic0load, in the cavity vertical test,
  Specification for cryomodule test including cavity/cromodule operational margin
  Specification in beam acceleration, including RF and beam operation margin
  Strategy to control ‘emitted radiation’
  Strategy for tuning and control including tolerances and availability margin, (<< advices from R.
  Impact on other accelerator system CFS, RF cryogenics and cost,

## Slide 7: Preparation for the 1st BAW
May 7: SCRF webex meeting and homework assignment
May 26: AD&I meeting
June 2: SCRF webex meeting and progress report from each collaborator,
June 23: AD&I meeting
June 30: SCRF webex meeting and preliminary draft report to be distributed
July 21: AD&I meeting
July 28: SCRF meeting and draft report to be distributed,
Aug. 25: SCRF meeting and the final report (prior to the 1st BAW) to be distributed

## Slide 8: Subjects to be discussed Single tunnel HLRF systems
KCS
  Tolerance on RF amplitue and phase within a cluster
  Operational margin of RF power, and tuning and control strategy
DRFS
  Assembly, sorting, and installation strategy including tolerances
  R&D requirement in TDP including radiation shielding
Backups
  Ordinal RF system in RDR, in single tunnel, as the final backup

## Slide 9: Baseline Assessment Workshop #2:
Reduced beam parameter set
Positron source relocated to the end of the linac
To include key stakeholders – especially Physics and Detector groups
  Notices to be mailed soon
SLAC, Kavli Auditorium
18-21 January, 2011
  (Monday, 17 January, 2011 is a US holiday)
~75 attendees expected;
  Reserved 40 guest–house rooms

## Slide 10: AD&I Meetings
Primary meeting for discussion of design and integration
  as name suggests
  SB2009 and beyond
Integrated activity including CFS
  core design team cuts across established PM TA
  Note also CFS workshop at Daresbury 12-13 July and SLAC (??)
Main focus for 2010 will be work required for TLCC
  Baseline Assessment Workshops
Attempt to identify themes in advance and prepare work
  Next week’s meeting may be used for this planning
  Following meeting on June 23 already earmarked for 10Hz low-energy operation
Notes: Don’t have dates in my calendar for SLAC CFS meeting.

## Slide 11: October ILC-CLIC Workshop
October 18-22
Next major GDE workshop
Together with ECFA Physics & Detector
  Important milestone in the TLCC process (BAW-II)
Joint ILC/CLIC meeting will mean differences from past workshops
  historically structures of CLIC and GDE meetings are different
  Compromises will need to be made
  Possibly less parallel time and more plenary
  AS WGs expected to be joint with CLIC groups
    large overlap in topics/people
  Despite joint nature it is important make sure we get our (ILC) necessary work done
Planning starts now!
(Next GDE-only meeting: ALCPG 19-23 2011 in Oregon)