JRA3 DAQ Task Status report
Vincent Boudry
Matthew Wing
EUDET Final Annual meeting
DESY, 30/09/2010

---
DAQ Task goal
- “Generic” DAQ based AMAP on commercial boards
  - Extensible for Large Detectors
- Provide the digital readout of CALICE embedded front end (ROC* chips)
  - All calorimeters seen through standard Detector InterFace board (DIF)
    - Pass configuration; fast commands; clocks;
    - Receives Data; Busy
  - 1 (opt. 2) Concentrator cards level
  - 1 Clock and Control Card (CCC) for the fast signal distribution and collection
  - Advanced Off-detector receiver (FPGA based event builder)
  - All signals on 1 cables; add-hoc communication protocol
    - 8b/10b coding
- 3 CALICE prototypes en route:
  - SDHCAL : ~400.000 ch; digital → 2b/ch,
  - ECAL : ~22.000 ch; Energy,
  - AHCAL : ~52.000 ch: Energy & time

---
CALICE DAQ2 scheme
N ×

---
Detector interfaces
~10 cm
AHCAL
SDHCAL
ECAL

---
Was used as DIF-Master (devt of LAPP)
Aka also sending hard-coded commands to DIF directly
DIF readout done by USB

---
Requires add-hoc protection
(contrains, chocs, physicists)
REM: ”Happy end” of a long saga

---
Beam InterFace card
Basis:
- CALICE chips use auto-trigger
  - Readout can be triggered by single event using external trigger (e.g. beam hodoscope)
    → “Single event” mode
    History of Chip is usable (e.g. in case of selective ext. trigger)
  - Readout triggered by environmental internal or extern trigger
    - Chip full
    - ILC-like mode (end-of-spill)
- Require some device to radout the beam line parameters
  - Scintillators; Cherenkov PM (coding of CEDAR bits)
  - Time of event (⊃ rec for wire chambers)
    within a 5 MHZ clock period
Implementation
- 2 solutions
  - Add-hoc card for interfaces with a CALICE ROC (SPIROC ?) + 1 DIF
  - Small adaption (buffers) card on a DIF + “simulation” of a digital ROC in the FPGA
    - Part of the coding can be “tricky”
- Both offer full compatibility with CALICE DIF for the DAQv2.
- To be implemented for 2nd version of CALICE beam test
- One of the task of AIDA (WP8.6.2)
  - For “standalone” CALICE tests
  - Functionnalities ⊃ in JRA1 TLU

---
HW status
- DIFs
  - ECAL DIF ready and working; 22 ready; mat for 40 in total (CAM)
  - DHCAL DIF: 165/170 cards tested & ready (LAPP)
  - AHCAL DIF: proto exist, in design, prod in NIU → 4 unit
- CCC: 10 cards ready; 4 in use in 4 labs; 3 more shipped → LLR
- DCC: 3 prototypes ready; 2 prod cards being tested (✔) → 20 end of october
- LDA: 25 main board scheduled (½ done; ½ to be done)
  - 5 v1 + 15 v2 Ethernet mezzanine : ✔
  - 6 CCC mezzanine ✔
  - 20 HDMI Mezzanine: faulty connectors on 8 → in repair
- ODR + PC
  - 8 ODR ready ; network card being used instead (debugging, ease of use)
  - 6 PC available: 1 in LLR ; 3 other ready; OS needs to be upgraded
- BIF: none (to be developped in AIDA)
~ No more basic problem with HW
Reliability of HDMI connectors mechanics ?

---
Integration tests
@UCL
PC +ODR
- Systems available @ UCL, LLR and now Cambridge
- Whole chain established :
  DAQ PC with ODR  LDA  DIF and CCC source
- Multiple (9, maybe 10) DIF  LDA links established
- FastTrig and Busy signals functional.
ECAL
DIFs
LDA
CCC
@ LLR :
PC(ODR)  LDA  DCC DIFs  (soon : ASU)

---
Python Test toolkit
Interactive hardware test software (GUI)
Each HW test easily scriptable: simple user-friendly python API: each function defined ↔ 1 graphical pane with “Run” button
Intensively used by Franck/Remi
Available to anyone working with USB/RS/Ethernet devices
C libraries implementing the complete DIF Task force protocole
https://svn.in2p3.fr/calice/online-sw/trunk/pyserdiag/

---
Reliability tests
Stress tests using pseudo-random generator
- 9×DIF → 1×DCC → 1×LDA → PC
  - 4 DIFs generate pseudo random data
- Results
  - Direction DIF → LDA ✔
  - Maximum DCC → LDA link occupancy (40Mbps) ✔
  - Up to 5.6 TB transferred (2 weeks), no error
End-to-end test: FIFO write/read
- PC ↔ 1×LDA ↔ 1×DCC ↔ 1×DIF
  - Tests both fast-commands and block transfer “read” requests
- Results:
  - PC ↔ LDA Ethernet OK with built-in delais (1 ms)
    - fixed 2 wks ago for Block transfer (Config),
      still issues when interleaving Fast Commands
  - Still to be fixed Buffer overflow on non-connected links

---
CCC←→LDA Fast signals tests
(from 29/09/2010 15:45!)
FastTrig-IN on LDA-CCC-Adapter
FastTrig input on HDMI Board
FastTrig/Busy at end of HDMI cable
Busy at LDA-CCC-Adaptor

---
FW status
LDA+CCC comm
Much delay due to cut and leave from key
Enginneer in 2009
Reuse MUX from DCC [?]
	LDA	DCC	DIF's
Ethernet	✔ at full speed
CCC	Clk; Trig; Busy	Clk; Trig; Busy	Clk; Trig; Busy
Nlinks up	9/10 conn. no MUX	9	1
Fast Commands	✔	✔	✔
Block transfert	✔	✔	✔
Data1)	✔ (< 50 MHz)	✔ (< 50 MHz)	✔ (<50 MHz)
ROC			Structure ✔ Adapt SDHCAL USB Code on going...
Generic code for all DIFs
FW have been advancing rather fast during the last 3 months
Many progresses recently
End of October for first full minimal usable chain ?

---
Performances
- Rather low demanding in term of bandwidth
  - SDHCAL : ~ 20MB/s in Spill
  - ECAL: ~100MB/s
  - AHCAL: ~ 300 MB/s
- Data limited by ASICs readout
- Some code (System C, by D. Decotigny) exists for simulation of full chain
- Many other studies...

---
Software: XDAQ framework
XDAQ vs DOOCS vs TANGO vs …
Some developpements done in DOOCS
lacks of manpower & expertise
“killed” in the transition region
- devts started @IPNL for electronics test using XDAQ in 2008
  - Ch. Combaret
  - Gained (a lot of) impulsion with involvment of L. Mirabito
    (resp. of DAQ SW for CMS tracker)
- Ran for ≥ 1 year in TB, Cosmics & Electronics test
  - USB readout
  - Interface to old LabView program
- Recent development
  - Writing of LCIO data in RAW format
  - versatile online analysis framework (root histos)
    → Marlin Based

---
SW status
- Missing critical elements
  - Configuration DB (being worked on)
  - DAQ2 interface ←→ XDAQ being worked on
- Missing utilities
  - Semi-automatic noisy channels spotting
    & correcting (moniting) ←←←
  - Clean Slow control
  - interface to CondDB;
  - event display
    (most probly DRUID)
  - interface to the GRID
  - interface to the machine
    (⊃ in AIDA WP8.6.2)
Part of XDAQ
✔
✔
✔
✔
✔
×
×
×
×
×
×
~
~
~
 USB ✔
DAQv2 ×

---
Documentation
- EUDET Memos's
- Most of Code, Manual and HW description is available on CALICE twiki: https://twiki.cern.ch/twiki/bin/view/CALICE/CALICEDAQ
- Some part's of FW is still scattered on various SVN servers
Delivery
- HW ready to be delivered to labs
  - CCC already in use in 4 labs
- Wait another 1.5–2 months for v0 of complete FW and SW integration
  - Preparatory work on specific FW and SW can already start (≤1 month)

---
Installation
- mechanics
  - mod. VME crate for
    - DCC
    - CCC
  - Special box for LDA
  - Support for cables
- Final set-up not yet known:
  - stand alone SDHCAL
  - stand alone ECAL
  - Stand alone AHCAL
  - Combined test
- → 5 m long HDMI cables
  - halogen free;

---
Conclusions
- Technological prototypes of CALICE are getting close
  - All use 2nd version of ROC chips
  - Being integrated in large prototypes → extensive TB in 2011
    - 1 m³ SDHCAL in Spring; some ECAL slabs in cosmics & beam; some AHCAL slab in beam.
- The DAQ will be ready for TB
  - All HW elements available
  - FW & SW almost ready
  - SW: XDAQ survived natural selection (←→ DOOCS)
- Combined (with other system) ≥ 2012
  - Prepare HW and SW beforehand
    - SW & HW ←→ TLU & EUDAQ first
Big effort for CALICE!!
~15++ individuals from:
 • UK: CAM, MAN, UCL,	RHUL, Imperial
 • FR: LLR, LAPP, IPNL
 • DE: DESY