## Slide 1: AD & I Meeting – 02 Feb, 2011
BAW Wrap-Up
TDR Preparation meetings – 2011 / 2012
  e+ next week at Daresbury
ALCPG11
Cost Engineer staff

## Slide 2: 2010 Baseline Assessment: wrap-up
3rd and 4th TLCC proposals submitted to Project Director Barish 31 January, 2011
EDMS links:
Reduced Parameter Set:
http://ilc-edmsdirect.desy.de/ilc-edmsdirect/document.jsp?edmsid=*940545
Relocation of the Positron Source:
http://ilc-edmsdirect.desy.de/ilc-edmsdirect/document.jsp?edmsid=*940575
Thanks to all !

## Slide 3: TLCC Proposal – Reduced bunch number
post – BAW question: Does the KCS require an even number of klystrons?

## Slide 4: TLCC Proposal – Reduced bunch number (2)
post-BAW checks & changes: power, heat and cryo load definitions (updated presentations to be posted)

## Slide 5: 2010 Baseline Assessment:
Barry is expected to convene ‘Change Evaluation Panel’
CEP should be ready for ALCPG11
As with TLCC 1 and 2, should expect “with considerations”

## Slide 6: Preparation for writing the TDR
Begins at ALCPG11 Eugene, OR –
  19-23 March, Saturday - Wednesday
  (19 March 16:00-17:30 GDE Plenary)
TDR Planning Goal for ALCPG11:
  Documentation plan
  Draft schedule for 2011 – 2012 including:
    TDR Preparation Review Meetings
    Plenary Meetings (biannual GDE)
  Milestones and target dates
  to be done in parallel sessions

## Slide 7: TDR Prep Review Meeting Goals:
Review the TDP R & D and summarize progress and plans.
Review the system design
  including a change control procedure so that key design changes can be discussed openly
  The updated baseline will be used for the TDR plan and cost estimate.
Review the system cost
  For SCRF and CFS, additional meetings, parallel sessions etc are also required.
Review system interface criteria;
  for example, requirements to CFS
Review supporting documents for inclusion in the EDMS
Discuss TDR preparation plans.
  Upon the completion of the review, we should be able to publish a plan for producing that part of the TDR; resources, milestones, etc
The review to be accessible to the community

## Slide 8: e+ source / EDMS meeting
10 – 11 February, 2011 Daresbury, UK
review the e+ source layout work
  Norbert Collomb
begin organizing the design documentation into ILC-EDMS.
e+ source will be an example node of the ILC-EDMS Document Breakdown Structure which will be presented at ALCPG11

## Slide 9: e+ source / EDMS meeting (2)
Daresbury Meeting 11-10th Feb: an example TDR Preparation Review Meeting
Thursday 10th - System-wide review
review the layouts, parameters and existing source documentation
review of CFS requirements and possibly costs (tbd).
walk through the existing design documentation
  reasonable and consistent
identify what's missing, and to make sure that the state of CAD models is well documented into ILC-EDMS.
Friday 11th - ILC-EDMS
consolidate design documents into a structure in ILC-EDMS
structure will be developed, keywords established and mandatory document list developed

## Slide 10: TDR Preparation Review Meeting Scheme
each meeting to include document discussion and sign-off
  drawings, specifications and spreadsheets with parameters and costs
  relatively small, compared to BAW
  each key participant can understand their immediate tasks and responsibilities.
the meeting to also include more general summary wrap-up talks, as needed.

## Slide 11: Preparation Review Meetings
meet with TAG’s, group by group.
5 to 6 meetings in the next 12 to 15 months.
start with the Accelerator Systems –
  Source
  DR
  BDS
Work on the AS systems:
  scope is understood,
  but there will be questions and changes
remaining resources are directed toward completion of specific tests –
  CesrTA, ATF2 and source technology development.
TDR Preparation Review Meeting Scheme (2)

## Slide 12: Schedule constraints and concerns:
Each review should last two days
Comprehensive costing for only SCRF and CFS TAG’s
SCRF industrialization study to be launched this month; expected ~ 1 year
CFS contracts and HLRF (DRFS) costing work is expected to be ready in late 2011.
Limit the total number of reviews to six, to take place between mid 2011 and early 2012.
Try to achieve regional balance and etc

## Slide 13: Preparation Review Meetings
CFS representatives to participate in every one of the AS meetings.
costing engineers also.
(SCRF group leaders are not required to participate)
Physics and Detector representatives required for MDI-related meetings; welcome at others
SCRF and CFS meetings toward the end of 2011 or in early 2012
  consistent with our schedule
reasonable and necessary set of meetings. required to close-out the TDP.
TDR Preparation Review Meeting Scheme - participation

## Slide 14: Topics for System Design Review
Review the TDP R & D and summarize progress and plans.
Review the system design
  including a change control procedure so that key design changes can be discussed openly
Example topics:
Cavity pairing – Power Distribution System.
Marx modulator
RDR HLRF fallback
RTML RF design and civil design.
Tunnel diameters
Power dissipation in the tunnel
DRFS components
Optimization of Positron production parameters:
  undulator length and field;
  polarization collimator space

## Slide 15: ALCPG11 WG Charge
1) Review and discuss ongoing R&D to understand how it is to be included in the TDR. Special focus should be given to those changes which could substantially impact system interfaces and/or project cost.
2) Evaluate the potential of R&D on alternates and upgrades to be carried out after the TD phase. This fits well with the emphasis on the 1 TeV upgrade and cost containment.
3) Develop a schedule for the next 12 months that leads to the start of the actual writing and editing of the TDR and allows the collection of key supporting documents.

## Slide 16: Upcoming GDE Plenary meetings
For the next two years we foresee that one of the two annual GDE plenary meetings will be a joint meeting with the CLIC Study and the other (e.g. this meeting, ALCPG11), will be for the GDE.
Because of this, we should emphasize ILC-specific aspects of linear collider design, especially superconducting RF technology, at the latter. – at the meetings which are NOT joint with the CLIC study
The next GDE plenary meeting, LCWS11, to be held jointly with the CLIC Study annual meeting, will be in late September 2011 in Granada, Spain.

## Slide 17: Reassignment of Peter G. – adding to the challenge of Costing for the TDR –
Fermilab Today ‘Director’s Corner’, 18 Jan, 2011
Pier Oddone:
“Office of Program and Project Support (OPPS). …. OPPS … strategic planning, project and program planning from …, human resources planning, integration …development plan with the strategic plan, and … “
“We are very fortunate that Peter Garbincius has agreed to head the new OPPS.”
Peter is to make this transition fairly quickly

## Slide 18: Costing for the TDR (2)
Search for replacement ‘Americas’ cost engineer underway
Tetsuo and Wilhelm: Asia and EU cost engineer
Peter will be accessible

## Slide 19: Director's wisdom
(FALC meeting report)
“An important item of discussion was establishing what should follow the ILC Global Design Effort when the Technical Design Report for the ILC is finished in 2012.”
"It is likely that the case for the ILC will take longer to be established, certainly if the case were in the affirmative."