## Slide 1: Special ATF Session - ATF/ATF2 day on 28th September -
Nobuhiro Terunuma
KEK
9/26/2011 LCWS11

## Slide 2: Special ATF Session on 28th
9/26/2011 LCWS11
Target of ATF/ATF2; R&D for ILC
    Generation of 2 pm-rad low emittance beam
    Demonstration of ILC Final Focus optics (ATF2 Goal-1)
      37 nm vertical beam size at IP
    Stabilization of 37 nm beam (ATF2 Goal-2)
Goal of this session
  Review/understand the present status of ATF and ATF2 after the great earthquake in details.
  Discuss the machine schedule and planning for the goal-1 in this Fall and by end of this year.
This session is composed by Joint with AWGs
    Damping Rings (WG2), Beam Delivery (WG5), Low Emittance Beam Dynmacis (WG7), Instrumentation and Technical Systems (WG8)

## Slide 3: Schedule: Special ATF Session
9/26/2011 LCWS11
8:30- 10:30 | Understanding ATF machine status and planning runs in this fall (WG2+WG5) |  |  |  |  | 
30 | Status of ATF/ATF2 and machine schedule in this Fall | N. Terunuma |  |  | KEK | 
30 | IPBSM status ( for a key devise ) | J. Yan (webex) |  |  | KEK/Tokyo | 
30 | Planning for the goal-1 | P. Bambade |  |  | LAL | 
30 | Discussion on the planning, following P.Bambade's talk | T. Tauchi |  |  | KEK | 
11:00- 13:30 | Status Report of beam tuning and Instruments (WG2+WG5+WG8) |  |  |  |  | 
30 | Overview of ATF beam diagnostics |  |  | N. Terunuma |  | KEK
30 | ATF2 lattice matching and beam tuning for ATF2 lattice v4.5 |  |  | G. White |  | SLAC
30 | Study of ATF2 multipoles and their influence of the nominal and reduced beta optics |  |  | S. Bai (webex) |  | IHEP
30 | OTR R&D at ATF2 |  |  | A. Faus-Golfe |  | IFIC
30 | Latest results on laser wire developments. |  |  | L. Corner |  | Oxford
15:00- 16:30 | – continued - |  |  |  |  | 
30 | Cavity BPM system at ATF2 |  | S. Boogert (webex) |  |  | Holloway
20 | High power laser wires using fibers |  | L. Corner |  |  | Oxford
20 | Update on FONT R&D |  | P. Burrows |  |  | Oxfort
17:00- 18:30 | Study for future plan (WG2+WG5+WG7) |  |  |  |  | 
10 | Tolerances for ATF3 QF1 from beam dynamics |  | H. Garcia Morales |  |  | CERN
20 | Sorting magnets for ATF2 nominal and ultra-low beta* |  | E. Marin |  |  | CERN
20 | A new QF1 magnet for ATF3 |  | A. Vorozhtsov |  |  | JINR
20 | Feed-forward of measured ground motion in ATF2 |  | Y. Renier |  |  | CERN
5 | Concluding |  | A. Seryi |  |  | JAI

## Slide 4: Brief report of ATF after the Great East Japan Earthquake
9/26/2011 LCWS11

## Slide 5: Impact of the earthquake on ATF
Photo: 2011/March/11 15:55

## Slide 6
Recovery History for Test Beam
Mar 11 | 14 | 21 | 28 | Apr 4 | 11 | 18 | 25 | May 2 | 9 | 16 | 23 | 30 | Jun 6 | 13 | 20 | 27 | Jul 4
 | KEK MW |  | 1.7 | 2 / 5 MW (day/night) |  |  |  |  |  | 24 MW |  |  |  |  |  |  | 20
Power line recovery
Rough Alignment (LINAC)
RF
Blackout
½ power
Vacuum
ATF2 Shield
Cooling Water
(BT)
(DR)
Summer Shutdown
Test Beam
KEK
Requested
Standby
at Home
Power
Distri-bution
ATF Shield
Radiation Safety

## Slide 7: Main Power Lines
Recovered in April

## Slide 8: Beam Transport
Fallen Pb blocks were cleared.
Ceramic of the CT monitor and a bellows were exchanged.
Repaired in April.

## Slide 9: ATF2 FD/IP shield works: re-positioning
Big work! 3 weeks

## Slide 10: Alignment of the beamline - continued work -

## Slide 11: A test beam passes all beamline
2011/5/25
Injector
2011/5/26
LINAC
5/31
DR 1st turn
Single bunch, 0.78 Hz, 0.3 x 1010 e/bunch DR&ATF2
5/27 BT end
6/2
DR storage
6/2 MS1X
6/3 MS1FF
6/3 MS2FF
6/3 MSPIP
2011/06/03
N.Terunuma

## Slide 12: Stored beam in DR (x1010 e/bunch) A stored beam was delivered to the dump of ATF2. No critical damage on the accelerator was found.
6/1
6/3
6/8
6/10
6/13
6/17
6/24
6/30
0.5x1010
1.0x1010
3 trains
XSR ready
Compton
2-mirror
FONT
3 trains
Cavity BPMs
FFTB mover
HAPS
Freq. Adjust
V-emittance (XSR) ~30pm
DR rough alignment for checkout was continued in daytime.
Inspection of the radiation safety

## Slide 13
ATF Schedule (draft for discussion)
Sep.26 | Oct. 3 | 10 | 17 | 24 | 31 | Nov. 7 | 14 | 21 | 28 | Dec. 5 | 12 | 19 | 26
 |  |  | Beam |  |  |  |  |  |  |  |  |  | 
DR
Checkout of beam instruments
EXT-FF
Low emittance,
Compton and Others
ATF
R&D
ATF2
R&D
Alignment
DR survey
ATF2 &TB
meeting
Recovery of
10 pm (DR)
Recovery of
300 nm
Goal-1 and others
extraction
survey
survey

## Slide 14: Measurement of the vertical beam size at ATF2
Example:
A beam size measured (2010/May/20)
  Modulation Depth = 0.87 @ 8.0 deg. mode
  sy = 310 +- 30 (stat.) +0-70 (syst.) nm
A smaller beam size, 37 nm, is one of the target of Goal-1.
The reached size was 300 nm before the Great East Japan earthquake.
Recover 300nm again, then continue the tuning down to 37 nm.