## Slide 1: TDR Part 2: 3.7 Cavity and cryomodule test (?? pages)
H. Hayano

## Slide 2
3.7 Cavity and Cryomodule test
3.7.1 Cavity test procedure
3.7.2 Cryomodule test procedure

## Slide 3
Cavity Test Procedure consideration
(He tank-on test)
Cavity Fabrication
Inspections/
optical inspection
Bulk-EP (150µm)
800C heat treatment
optical inspection
cell RF tuning
surface repair 2
fine EP (20µm)
120C baking
He tank welding
install pick-up antenna,
HOM coupler tuning
2K field test
OK
if defect found
surface repair 1
if defect found
4 Cavities Test
in one cool-down
> 28MV/m
< 28MV/m
2nd pass
remove pick-up antenna, HOM antenna
with He Tank
in 2nd pass
with He Tank
in 2nd pass
skip
in 2nd pass
to cryomodule
Cavity test facility
Laboratory?
or
Industry?
~80%
~20%
OK
~96%
~4%
Laboratory
~20%
HPV qualification

## Slide 4
Cavity treatment change: proposal
(1) Include surface inspection and local repair, before and after bulk-EP
(2) Tank-on delivery, ready to do field test
(3) Apply 2-nd pass treatment, if the gradient less than 28MV/m,
( no more 3-rd treatment )
(4) Field Test Facility is the laboratory responsibility
Need to cost estimate for industry 2-nd pass or laboratory 2-nd pass
Existing Lab cryogenics has cost benefit for laboratory field test facility.
Follow XFEL procedure.
Give-up quench location identification assuming surface inspection effectively work.
Minimize industry/laboratory transportation.
Visible, clear defects can be identified and easily removed before costly field test.
By automated inspection and repair-robotics, man-power cost reasonably low.
Assuming 1-st pass ~80% yield extrapolated and expected from cavity gradient data-base,
Another >80% yield for 2-nd pass, makes >96% yield in total.

## Slide 5
Coupler Fabrication
clean-up
pair assembly
pumping/120C baking
RF power process (RoomTemperature)
disassembly
in clean room
Assembly cavities and couplers,
and into cryomodule
RF power process
(Room Temperature)
RF power process with cavity (2K)
Coupler Procedure
Cryomodule Procedure
cryomodule assembly
cryomodule test facility
in tunnel
RF power process
(Room Temperature)
RF power process with cavity (2K)
Accelerator Operation
Coupler test facility
2x peak RF power process
Move to Tunnel and install into Accelerator
cavities
couplers
Initial 20% to go cold-test
The rest, 10% sampling
for cold-test
100% power test
20hrs
for pair of couplers
Cryomodule parts

## Slide 6
Coupler test, cryomodule test: proposal
(1) 100% coupler power test done by industry
According to specification table, rf process should be;
>1200kW up to 400µs pulse width, >600kW for 400 ~ 1600µs
>600kW for 1600µs.
After process, cold part should be disassembled and packed in clean-room.
High peak power process is strongly recommended
for ceramics window process, whisker process and out-gass process.
not good for in-situ process to avoid contamination into cavity.
120C baking is also required for surface water removal,
not good for in-situ baking to avoid contamination into cavity.
So that, automated Coupler Test Facility for 100% coupler process
should be considered.
To make fabrication feedback easy, industry should do rf process.

## Slide 7
(2) Average 30% cryomodule cold test done by laboratory
Existing Lab cryogenics (Lab operated cryogenics) and Lab high power RF system
has cost benefit for cryomodule test facility.
Laboratory should have responsibility for the final test of cryomodule,
because of final check point of accelerator performance before tunnel installation.
Only average 30% of 1824 cryomodule production
( ~ 547 cryomodule -> 182 cryomodule/region ) are tested.
Initial every ~120 cryomodule (20%) are tested,
then only 10% of the production are tested by sampling.
In start-up 3 years, cavity performance degradation issue should be addressed and solved before production.
~1.5 months/cryomodule assembly term makes 24 cycles assembly, then 24 times feedback process is enough to address vaious issues to solve.

## Slide 8
Cryomodule production in RDR
Initial 20% cold-test
10% sampling for the rest
Average 30% cryomodule cold-test
red bar shows
30% cold test

## Slide 9
Cryomodule Test flow
Cryomodule assembly facility
remove transport jigs
cryogenics/vacuum/WG connection
slow pump
RF power process (RoomTemperature)
cool-down to 2K
Cryomodule test facility
cavity/coupler/WG tuning
RF high power test
cavity tuner release
slow vent/disconnect/install transport jigs
warm-up
transport
transport
tunnel or stock-yard
*start-up test in tunnel is similar to this flow.
RF low-power test
CT to coupler
WG connection again