## Slide 1: ML & SCRF Baseline Technical Review Summary
Akira Yamamoto
Feb. 1, 2012
ILC-GDE ML & SCRF Baseline Technical Review, held at KEK,
Jan. 19-20, 2012

## Slide 2: Progress in SB2009 toward TDR, and Baseline Technical Reviews
 | Technical Area | Place and Dates
SB2009 |  | Proposed Dec. 2009
BAW-1 | 1. Acc. Gradient, 2. Single tunnel, | KEK, Sept. 7-10, 2010
BAW-2 | 3. Reduced RF Power, 4. e+ source location | SLAC, Jan. 17-21, 2011
BTR-1 | DR | INFN, July, 7-8, 2011
BTR-2 | RTML, Sources, BDS/MDI | DESY, Oct. 24-28, 2011
BTR-3 | ML & SCRF | KEK, Jan. 19-20, 2012
BTR-4 | CFS | CERN, March 22-23, 2012

## Slide 3: ILC Design: RDR to TDR (SB2009)
RDR2007  SB2009  TDR w/ mountain site
Motivation: Cost containment
Single accelerator tunnel
Smaller damping ring
e+ target location at high-energy end,
SCRF: Gradient variation of 31.5 MV/m +/- 20 %,
HLRF: KCS and DRFS with RDR-RF-unit as backup

## Slide 4: High-Level RF Solutions
Klystron Cluster Scheme, KCS (SLAC)
Distributed RF Sources, DRFS (KEK)
2×35 10MW MB klystrons
~4000×800kW klystrons

## Slide 5: Studies made for 8 cases
DRFS RF unit:
2 cavities operated by 800 kW Klystron
RDR RF unite :
3 Cryomodule (9+8+9 = 26 cavity),
operated by using 10 MW Klystron

## Slide 6: A Proposal Revised
Keep the concept of 9+8+9 cavity sting unit
9 4 + Q +4 9
8 8 Q 8
8 4 + Q +4 8

## Slide 7: Technical Change Decisions Proposed
Tech. Area | Main Subjects | Description
ML Integration | Parameters and beam dynamics Single tunnel-layout CM and Q periodicity: ML tunnel length Possible tilting of the tunnel | Low-Power design as TDR baseline (SB2009), and alignment tolerance Circular tunnel in flat-land, and Kamaboko tunnel in mountain CM and Q periodicity: >> Stay at 9+4Q4+9 Reserved tunnel-extension of 400 m w/o or w/ utility ? >> More precise discussions for purpose required New request from CFS: possible < 0.5 % tunnel tilting
RF power | HLRF Configuration LLRF operational overhead | KCS in flat-land site RDR-RF unit in mountain site (DRFS to be withdrawn) ≥ 12% RF operational overhead at gradient variation of +/20 % and in RDR-RFunit <33.3 MV/m> in Klystron
Cryomodule | Envelope/interface String Unit 5 K radiation shield | Piping interface with flange?, inter-connect condition, etc, Stay at 9 +4Q4+9 (withdraw 8+4Q4+8) Simplification and accessibility for active components such as tuners
Cryogenics | Unit capacity | Stay at 5 units per linac Limit of tilting angle in ML tunnel
Cavity integration and Cavity/CM test | Envelope, baseline, compatibility Test conditions | Tuner type, coupler warm-flange, beam pipe flange, magnetic shield (inside/outside), LHe tank etc. Test plan and fraction of CM to be tested (how much fraction?)
Cavity performance | Yield Gradient spread Degradation in CM module | New recipe and cost-base scope: 1st pass: 60% and 2nd pass: 70% ? (Assume ~ 1/10 cavities to degrade dG = ~ 20 % or more, and ) >> Adopt a statistical approach to cavity degradation; <> and rms
Cost | Cost containment Exchange rate and conversion | Technical design base on SB2009 (updated) compared with RDR cost

## Slide 8: ILC-ML SCRF Cavity Gradient Specifications Update
Cost-relevant design parameters for TDR | ML cavity gradient Specification | R&D Milestone
9-cell Cavity Gradient in vertical test | 35 MV/m, average - Spread: 28 – 42 MV/m (+/- 20 % or less) | 35 MV/m at 90 % yield including 2nd pass, (eq. > 38 MV/m, average)
Cryomodule Operational Gradient | 34 MV/m, average CM Obs. G. Limit = 3 % | 
Accelerator Operational Gradient | 31.5 MV/m, average Op. G lim = 1.5 MV/m Cntrl margin = 3 %** | 
Required RF power overhead for control | 10-15% | 

## Slide 9: DESY + S1-G statistics
Mean: -8% ±16% RMS
correlation coeff. -0.27
14 assemblies
108 data points
Note: measurement error? Assume 10% → 13% degradation spread (rms)

## Slide 10: Kyushu/Sefuri area

## Slide 12: Tunnel Tilting Effect in Sefuri Site
0.8 % tilting enables to save access tunnel length from 22 km to 14 km

## Slide 13: Technical-change Decisions Concluded
ML: lattice design based on the cavity-string of {9+4Q4+9} = 26 (in KCS) or 1.5x 26 = 39 in RDR-like RF,
HLRF: KCS w/ flat-land geology, and RDR-like w/ mountain geology
Cryomodule: RDR-like (9+4Q4+9) w/ conduction cooled SCQ at center, and w/ simplification of 5 K shield
Cryogenics: 5 plants / linac allowing a limited tilting w/ reasonable variation (20%) of spacing b/w plants,
Cavity Integration: Cavity; Tesla + Blade tuner, magnetic shield inside,
Cavity gradient: Updated recipes and production yield definition,
Cryomodule tests: in reasonable rate (1/3 ~ ¼) and reasonable cost-balance,
ML-CFS: tunnel-extension to keep energy overhead up to ~ 1.4 % (~150 m) in addition to the current overhead of 3 % (i.e.: assuming 35 to 34 MV/m degradation already in cavity gradient design
  Corresponding 2 x SB2009-RDR-RF units, 2 x 39 cavities per side , (+ 150 m tunnel / linac),
  If tunnel tilting required, additional length of ~ 100 m / 0.5 % required, and the energy overhead not available,
  the ML length to be fixed under constraint of balance of timing issues b/w electron and positron,
  This to be well discussed with detector/physic community and

## Slide 14: Home-Works by Korea Meeting
ML Integr. | ML lattice with 9+4Q4+9 cryomodule unit, Energy overhead (1.4%) for operational availability, and add. length Total numbers of CM including ML, RTML, e-source (add. CMs to be fixed) Q magnet + corrector magnet design, and energy dependent design? Strategy for full power upgrade at 500 GeV, and scenario for 1 TeV (Q configuration, FDFD up to 500 GeV, and FFDD at 1 TeV?)
HLRF | Cost saving of PDS, Klystron, Marx Generator and …
CM and Crogenics | CM slot length fixed to be 11,734.5 +850 mm in RDR, or new number 11,830+850 mm from Chicago mtg (2008) Access-ability and maintenance of active components (tuner motors), Cryo-line unit length, additional length of Cold-box for phase-separation, to adapt new RDR-like RF unit and/or tilting tunnel and effect on add. length
Cavity Integr. | Cavity-slot length to be well fixed (to be 1326.7 mm) Reality of magnetic shield inside Lhe tank at central region and outside at inter-connect
Cavity Gradient | Update fabrication process and recipe (such as including tumbling), Re-definition of production yield

## Slide 15: backup

## Slide 16: Main Linac Layout
Kamaboko RFU: 39 cavities / klystron
  4.5 cryomodules
  Always consider x2 as “atom” → 9 cryomodules
  DE ~2x 1.27 = 2.54 GeV (1%)
  235/2.54 = 93: 186 RFU-39 or 837 cryomodules
  0.4% energy margin
  TBR: Add 2 RFU-39 as overhead
  188 RFU-39 → 1.4% energy margin
KCS (RDR – 26 cavities / “klystron”)
  Similar analysis yields 3 CM less per linac
  1.0% energy margin.

## Slide 17: Cryo Layout (Kamaboko)
Question for Tom Peterson
RDR (KCS)
  2.5 cold-box every 4 RFU or 12 cryomodules
Kamaboko
  Atomic unit = 9 cryomodules (2x klystrons)
  Need to move cold box to
    every 9 modules (more tunnel length / cold boxes)
    every 18 cryomodules (shorter but problem for cryo?)

## Slide 18: Summary of Numbers of CMs as of Jan. 2012 (by N. Walker)

## Slide 19: Quadrupole Cross-Section
LHe tank for current leads connections
Beam pipe
Iron yoke
V. Kashikhin, FNAL Review, March 2, 2010

## Slide 20: CM4’ Length checked at KEK

## Slide 21: Total Unscheduled downtime vs enrergy Overhead (slide from E. Elsen, ML/SCRF-BTR)

## Slide 22: Two Candidate Sites in Japanese mountainous locations
SEFURI
- GDE-CFS group visited two candidates sites,
Oct. 14 and 15, 2011