## Slide 1: TDR Preparation Status
J. Carwardine
30 May 2012

## Slide 2: Revisions to TDR2 Outline (SCRF)
Motivation: to help guide the reader who wants to follow the design for one specific site, while still allowing the text to flow
 |  | Part II: The ILC Baseline Reference | 327 |  | 
1 |  | Introduction and overview | 5 |  | Paterson
2 |  | General parameters and layout | 15 |  | [Editor]
3 |  | SCRF Linac Technology | 39 |  | Yamomoto
3 | 1 | Main linac top-level parameters and general layout |  | 2 | Adolphsen
3 | 2 | Cavity performance and production specifications |  | 10 | Yamamoto
3 | 3 | Cavity integration (couplers, tuners etc.) |  | 10 | Hayano
3 | 4 | Cryomodule design including quadrupole and cryogenic systems |  | 10 | Perini
3 | 5 | RF power source |  | 3 | Fukuda
3 | 6 | Low-level RF control concept |  | 2 | Carwardine/Michizono
3 | 7 | Cavity and cryomodule testing |  | 2 | Hayano
4 |  | Main linac layout for a flat topography | 7 |  | 
4 | 1 | Layout |  | 2 | Adolphsen
4 | 2 | Klystron cluster scheme RF power distribution system |  | 4 | Nantista?
4 | 3 | LLRF control for KCS |  | 1 | Carwardine/Michizono
5 |  | Main linac layout for a mountain topography | 7 |  | 
5 | 1 | Layout |  | 2 | Adolphsen?
5 | 2 | Distributed Klystron scheme power distribution system |  | 4 | Fukuda
5 | 3 | LLRF control for DKS |  | 1 | Carwardine/Michizono
Are there any areas where clarifications are needed with regard to reorganizing the text?

## Slide 3: Deadlines
First-draft sections | 27 April *
Progress report to GDE Director | 12 July
Complete edited draft | 22 October (ILCWS 12)
Final draft (for PAC) | 15 November
PAC review | 15-16 December
GDE drop-dead deadline
Revision of Nick’s slide from KILC
Editors’ tasks prior to 22 October: checking entire content for technical consistency, revising text for a consistent style, consolidate content to meet page counts, validating references to TDD and external publications, checking figures,…
Editors’ deadline

## Slide 4: Already we are well behind
Total sections in TDR outline: 121
Sections not submitted: 92
Sections without author promise dates: 73
This makes Editorial planning very difficult
Issues in writing the draft text…
Still finalizing design details, still working on costing
What else…?
Might the editors help prepare the first draft, eg where text is largely updates of the RDR?

## Slide 5
…Forge resources available
…SCRF submission status
Discussion