Scenario for design and construction of the LCTPC at the Japanese ILC site

(Note that all points of this scenario will be open for discussion.)

Timeline for this exercise:  Approval of the ILC in 2015, installation of the TPC in 2024

(…in agreement with the TDR and Yasuhiro Sugimoto’s personal view)

That means we have the following breakdown of tasks:

- 1 – 2 years to design

- 1 – 2 years for designing

- 6 years for manufacturing, testing, commissioning of components of the LCTPC

- 1 – 2 years to design

①

For the LP R&D, verify correction procedures, single-point, 2-hit, dE/dx resolutions

②

Engineer the endplate, fieldcage, gating device, improve module design (add gate, minimize edge distortions)

- 1 – 2 years for designing

③

Decide the technology for the preliminary design of the LCTPC

④

Continue designing details of the LCTPC

⑤

The R&D of electronics, power-pulsing, cooling, etc. should be pushed in parallel to the R&D and the designing, remembering that it will be several years left before the electronics must be ready and that the decision on the electronics should be made not too early.  It should also not be later than around 4 years before installation since a large effort will be needed to fabricate, test and mount the electronics.

- 6 years for manufacturing, testing, commissioning of components of the LCTPC

Manufacture will not be necessarily be done by the LCTPC collaboration, which is only mandated for the R&D and design.  However the collaboration might be asked by ILD to organize/oversee its construction and testing, which might also include the formation of a new collaboration/mandate for this task.

We will need staging areas for testing and assembling the components.  One possibility for example would be to have a hall in KEK where everything could be gathered, tested, assembled.  The complete TPC could be shipped to the Japanese site and installed in ILD.

Another idea would be to make a pre-assembly at KEK and the final assembly at a building near the mountain site.  Other ways are of course imaginable, and this can be decided in about three years.

Components/Jobs:

- Two Endplates

- Modules (mechanics + voltage services)

- Modules (electronics + cooling)

- Inner Fieldcage  (cylindrical mechanics + potential strips)

- Outer Fieldcage (cylindrical mechanics + potential strips + central membrane)

- Testing/commissioning of all components

- Assembly in a lab at KEK or at the mountain site

- Insertion into ILD