## Title
Change Request Register
Benno List
Version |  | 4.8 | 2015-11-05
EDMS ID |  |  | D00000001056505
Revision History:
Version | Date | Author | Remark
0.1 | 2014-05-06 | BL | First Version
0.2 | 2014-05-27 | BL | New Formatting
0.3 | 2014-05-27 | NW | Revision of initial status flags. Added sorting.
0.4 | 2014-05-29 | NW+BL | Added additional date fields. Final review of initial list before distributing.
1.0 | 2014-09-09 | BL | Added CR-0002
1.1 | 2014-09-10 | BL | Added EDMS numbers and due dates for ILC-CR-0001 and 0002
1.2 | 2014-09-12 | NW | Added description of impact flags and change sheet name to info,
1.3 | 2014-09-24 | NW+BL | Renamed "Due Date" to "Next deadline" and moved to col. L. Updated CRRs.
1.4 | 2014-09-24 | NW | Added IR BPM (row 33) as "under consideration" (BDS/MDI)
1.5 | 2014-09-26 | BL | Updated status of CR-0001 and 2 after CMB meeting
1.6 | 2014-10-03 | BL | Updated status of CR-0001 and 2 after 1st CMB meeting on 25.9.14
1.7 | 2014-10-03 | BL | Changed Style to LCC colors
1.8 | 2014-10-07 | BL | Added ILC-CR-0003
2.0 | 2014-10-22 | BL | Updated to reflect results of 2nd CMB meeting on 9.10.14
3.0 | 2014-12-19 | BL | Updated to reflect results of 3rd CMB meeting on 20.11.14, and inclusion of new CR-0004
4.0 | 2015-01-15 | NW | Updated to reflect results of 4th CMB meeting, separated active and future requests
4.1 | 2015-02-03 | NW | Applied modifications to "Possible requests" following TB review on 27.01.15
4.2 | 2015-03-31 | NW | Changed owner on CR-003. Changed state and owner on CR-004
4.3 | 2015-04-27 | NW | Updated after ALCW 2015
4.4 | 2015-06-14 | NW | Updated after 8th CMB meeting
4.5 | 2015-06-15 | BL | Added CR-0007
4.6 | 2015-10-07 | NW | Updated status of many CRs. Added "Cryo surface relocation", "ML shield wall" and "DR top-level parameters update" to Active Requests as "in preperation"
4.7 | 2015-10-09 | BL | ILC-CR-0010 submitted
4.8 | 2015-11-05 | BL | ILC-CR-0011 submitted, reflect situation at LCWS2015

## Active Requests
No. | Creation Date | Last Modified | Creator | Primary WGs | Title | Description | State | Owner | Impact | Document ID | Next deadline | Remark
ILC-CR-0001 | 2014-09-01 | 2014-10-09 | K. Yokoya | PS / BDS / RTML | Add return dogleg to target by-pass | Add additional lattice to bring BDS beamline on axis with main linac, to accommodate future >1 TeV beam energies. | Rejected | NA | 1 High | D*1082395 |  | Rejected at 2nd CMB meeting on 9.10.2014
ILC-CR-0002 | 2014-09-02 | 2015-10-07 | G. White | BDS / MDI | Adopt equal L* for both detectors | Find solution for single L* value for BDS and both detectors. | Accepted / Implementing | Change Request Implementation Team | 1 High | D*1082495 | LCWS15 | Lattice has been designed. Awaiting inclusion in EDMS and final report for close-out.
ILC-CR-0003 | 2014-10-07 | 2014-03-31 | K. Buesser | MDI / CFS | Detector hall with vertical shaft access | Consolidated solution for IR hall / layout which supports surface construction of the detectors. | Completed | NA | 1 High | D*1084745
ILC-CR-0004 | 2014-12-18 | 2015-10-07 | N. Walker | ADI | Extension of the electron and positron Main Linac tunnels by about 1.5km | Lengthen Main Linac tunnels by about 1.5km, to (i) fulfill the Global Timing constraint and (ii) add margin for total beam energy as risk mitigation to ensure 500GeV CME. | Accepted / Implementing | Change Request Implementation Team | 1 High | D*1092915 | LCWS15 | CIT implementation report in preperation.
ILC-CR-0005 | 2015-04-22 | 2015-06-15 | N. Walker | ADI | Update top-level parameters | Correct errors in reported luminosity for 500 GeV baseline and 1 TeV (b) parameters. | Completed | NA | 4 Administrative | D*1100895
ILC-CR-0006 | 2015-05-12 | 2015-10-07 | G. White | BDS / MDI | Add BPM downstream of QD0 | Add a BPMs immediately downstream of the QD0s to facilitate beam capture and construction of a "virtual IP BPM". | Accepted / Implementing | Change Request Implementation Team | 2 Medium | D*1102185 | LCWS15 | Effectively completed as part of CR-002
ILC-CR-0007 | 2015-06-11 | 2015-10-07 | M. Harrison | ML | Adoption of the Asian design as sole baseline | Only the Asian version of the TDR designs will be the basis for further developmen; the baseline HLRF distribution scheme will be DKS, the CFS planning will be based on the mountainous topography design. | Accepted / Implementing | Change Request Implementation Team | 4 Administrative | D*1107065 | LCWS15 | In progress
ILC-CR-0008 |  | 2015-10-07 | M. Woodley | Machine-wide | Formal release TDR-2015a lattice | Complete set of matched lattices reflecting TDR design | Accepted / Implementing | Change Request Implementation Team | 4 Administrative | D*1110885 | LCWS15 | In progress
ILC-CR-0009 |  | 2015-10-07 | A. Yamamoto | CRYO / ML | Relocate cryo components to surface | Move compressors and helium storage to surface sites (requires long transfer line). | In preparation | Change Requestor | 1 High |  | LCWS15 | CR expected before LCWS15
ILC-CR-0010 | 2015-10-08 | 2015-10-09 | N. Walker | RTML / ML | Move Bunch Compressor to Main Linac | The Bunch Compressor formally becomes a part of the Main Linac instead of the RTML. | Submitted | Change Administrator | 4 Administrative | D*1119175 | LCWS15
ILC-CR-0011 | 2015-11-01 | 2015-11-01 | W. Gai | PS | CFS design compatible with both undulator and e driven positron source | The CFS design in the central region shall provide the space and infrastructure necessary to install an e driven source if necessary | Submitted | Change Administrator | 2 Medium | D*1121535 | LCWS15
|  | 2015-10-07 | M. Harrison | CFS / ML | Reduce the width of Kamaboko shield wall | Reduce the width of the ML tunnel shield wall by adopitng no access durinng beam-on operation. | In preparation | Change Requestor | 1 High |  | LCWS15 | Plans and scope of CR to be discussed at LCWS.
|  | 2015-10-07 | D. Rubin | DR | Update to Damping Ring top-level parameter tables | Cross-check of parameter tables and associated CFS requirements. Includes parameter set for 10-Hz high-current lumi operation (physics scope change) | In preparation | Change Requestor | 2 Medium |  | LCWS15
|  | 2015-11-05 | T. Okugi | BDS / Sources / MDI / CFS | Adopt Kamaboko-style solution for BDS / central region | Replace separate service tunnel with Kamaboko-style solution | Under consideration | Change Requestor | 1 High |  |  | Major scope. Will likely drive many smaller CRs.

## Possible requests
No. | Creation Date | Last Modified | Creator | Primary WGs | Title | Description | State | Owner | Impact | Document ID | Next deadline | Remark | Flag
|  | 2015-04-27 | G. White | BDS / CFS | Updates to BDS lattice | Release of new lattice after review and subsequent development. | Under consideration |  | 2 Medium |  |  | Many changes expected towards new release of baseline lattice, in particular implementation of CR-003 as well as central region consolidation. | 2
|  | 2015-04-27 | G. White | BDS / CFS | Include beta matching section | Add a dedicated beta matching lattice section to aid tuning (similar to ATF2) | Under consideration |  | 2 Medium |  |  | Part of the above request? | 2
|  |  | N. Walker | ML | Increase bandwidth of extraction lines in BC | Review operational requirements of fast extraction lines and dumps and re-design appropriately. | Under consideration |  | 2 Medium |  |  | Current design bandwidths driven by nominal beam energy spread. Being re-evaluated as part of Solyak's Failure Mode appraisal. | 2
|  | 2015-04-27 | Wei Gai | ES / PHYS | Increase e- polarisation at IP to 95% (?) | Adopt strained cathode with higher polaristion. | Under consideration |  | 2 Medium |  |  | Discussed at ALCW2015. | 2
|  | 2015-04-27 | B. Parker | BDS / MDI / CFS | Reduce IR crossing angle | Develop hilghly-compact SC FD to allow for smaller crossing angle. | Under consideration |  | 1 High |  |  | Change status back to under consideration after ILC feedback via K. Buesser. | 3
|  |  | N. Walker | BDS / MDI | Alternative FF scheme removing strong sextupoles from FD | Consider alternative FF schemes which would remove the strong sextupole magnets from the FD. | Under consideration |  | 1 High
|  |  | N. Walker | MDI | Integrate laser wire(s) into IR region (detectors) | Incorporate one or more laser wire system in into the detectors ± some distance from the IP to facilitate accelerator tuning. | Under consideration |  | 1 High
|  |  | N. Solyak | SRF / ML | Implement cost-effective PDS | Update current PDS design to a cheaper simpler alternative | Under consideration |  | 1 High |  |  | Requires R&D. Left over from TDR, since PDS is very expensive. Resource limited!
|  | 2015-04-27 | M. Kuriki | PS / CFS / PHYS | 300-Hz e-driven source | Add 300-Hz e-driven positron source to baseline | Under consideration |  | 1 High |  |  | Place holder for very high-level CR. Text modified after discssions at ALCW2015
|  | 2015-01-12 | LCB | ML / CFS | Implement design for energy staging. | Effectively develop lattice / CFS design for first-stage 250 GeV cm operations. | Removed |  | 1 High |  |  | 250 GeV first stage dropped by LCC decree.
|  | 2015-01-12 | G. White | BDS / MDI | Move FFBK kicker downstream of QD0 | Locate intra-beam FFBK downstream of QD0 (inside detector), to effectively increase FD vibration tolerance correction range. | Removed |  | 1 High |  |  | Initial studies showed no benefits.
|  | 2015-02-03 | H. Hayano | SRF | Adopt Saclay-like tuner as baseline | Adopt LCLS-2 tuner and associated helium tank and flange solution. | Under consideration |  | 2 Medium |  |  | Impact changed to Medium (from Low) at A. Yamamoto's request following TB meeting on 27/01/15
|  |  | E. Paterson | PS | Add timing adjustment chicance system | Implement a timing adjustment chicane in the positron injection system to allow for fine path-length adjusment. | Under consideration |  | 2 Medium |  |  | Has become part of CR-0004 implementation
|  | 2015-01-12 | E. Paterson | DR | Modify circumference of DR | Adjust circumference of damping ring to accommodate global timing constraint | Removed |  | 2 Medium |  |  | This will be made redundant by an acceptance of CR-0004.
|  |  | N. Walker | DR | Add RF and wiggler for high current 10Hz operation | Configure DR designs to accommodate 100ms dampng time with 2625 bunches to allow for 10-Hz collisions after the luminosity upgrade. | Under consideration |  | 2 Medium |  |  | Make sure baseline design can be upgraded
|  | 2015-01-12 | N. Walker | ML / CFS | Change in average gradient specification in ML | Adjustment of baseline average accelerating gradient in the main linacs. | Under consideration |  | 2 Medium |  |  | Linked to CR-0004. Additional tunnel gives us margin to add more linac if necessary. Hence reduced impact status.
|  | 2015-01-12 | N. Walker | ML | Modify lattice for staged implementation | Lattice design for the first-stage 250 GeV machine. | Removed |  | 2 Medium |  |  | 250 GeV first stage dropped by LCC decree.
|  | 2015-01-12 | H. Yamamoto | ML / CFS | Extend max. energy reach | Extend maximum energy range of the machine to 550 GeV centre of mass. | Under consideration |  | 2 Medium |  |  | Linked to CR-0004. (Note achievable gradient and tunnel length all link to this).
|  |  | Wei Gai | PS | Extend undulator length to 230m as baseline | Remove need for 10-Hz production mode at 250 GeV centre-of-mass energy | Under consideration |  | 2 Medium
|  |  | Wei Gai | PS | Alternative target design | Adopt alternative photon target design | Under consideration |  | 2 Medium |  |  | Place holder for whatever is decided with the target. R&D needed.
|  | 2015-02-03 | H. Hayano | SRF | Magnetic shield inside helium tank | Place magnetic shielding inside helium tank to simplify string / cryomodule assembly. | Removed |  | 3 Low |  |  | Removed following TB meeting 27/01/15. Technically mag. shield inside tank is already TDR baseline (although this still requires development work).
|  |  | D. Rubin | DR | Reduce number of BPMs | Reduce the compliment of BPMs in the DR lattice | Under consideration |  | 3 Low |  |  | Result of on-going value engineering
|  |  | D. Rubin | DR | Loosen multipole tolerance specs. | Update magnet specifications to reflect allowable looser tolerances on magnet multipoles. | Under consideration |  | 3 Low |  |  | Result of on-going value engineering
| LCWS2015 | 2015-11-05 | T. Okugi | PS | Update positron source lattice | Update positron source lattice, including upstream shift of 5GeV booster, booster extension, new energy compressor scheme, new spin flip |  |  | 2 Medium |  |  | Result of review of PS lattice, also in conjunction with CR to allow e-driven positron source
| LCWS2015 | 2015-11-05 | T. Okugi | ES | Relocation of the e- source 5GeV booster | * Shift of the electron source booster upstream to avoid spray from BDS collimators |  |  | 2 Medium |  |  | Result of design work for central region
| LCWS2015 | 2015-11-05
| LCWS2015 | 2015-11-05 |  | CFS / Cryo | New cryogenic distribution in central region | Movement of 5GeV boosters may trigger different supply scheme, from Main Linac rather than IP |  |  | 2 Medium
| LCWS2015 | 2015-11-05 | T. Sanuki | CFS / MDI | Relocation of IP | New IP location with new layout of surface assembly yard |  |  | 2 Medium |  |  | CR would not entail review of access tunnel situation, because precise IP location itself is not yet part of baseline
| LCWS2015 | 2015-11-05 | T. Markiewicz | CFS / MDI | Large (5000t) gantry crane | Increase capacity of gantry crane for detector installation to 5000t |  |  | 2 Medium |  |  | Was raised at LCWS2015
| LCWS2015 | 2015-11-05 |  | CFS / PS | Cavern for positron source target | Positron target needs remote handling infrastructure, review necessary cavern size and access requirements |  |  | 1 High |  |  | Would be part of consolidated central region design
| LCWS2015 | 2015-11-05 |  | CFS | Cavern design for 14MW tuneup and main dumps | Large 14MW dumps (tune-up and main) need caverns with provisions to contain radioactivity. Review necessary cavern size and access requirements |  |  | 1 High |  |  | Would be part of consolidated central region design
| LCWS2015 | 2015-11-05 |  | CFS / ES | Infrastructure for electron source injector | Electron source gun / injector complex needs laser equipment. Review space and access requirements. |  |  | 1 High |  |  | 1 High
Note on D6: Nicholas Walker: Not always clear who this is when it's in one of the pre-CR states. Need to discuss.

## Info
Change Request States
State
Pre-CR | Under consideration | Place-holder / capture for upcoming ideas being discussed by ad hoc groups.
| In preparation | In transition to a formal CR (i.e. CR document being prepared for submission)
Formal CM | Submitted | CA has formally received mandatory CR document and assigned a number.
| CMB Review | Formally being discussed by CMB
| Deferred to review panel | CRP formed by CMB and charged to review CR.
Escalated to LCC Directorate
| Accepted / Deferred | Accepted but implementation deferred until a more convenient time.
| Accepted / Implementing | Accepted and change is to be immediately implemented.
Closed | Rejected | Assumed closed.
| Completed | If accepted, change has been fully implemented.
| Removed | Special state for under consideration CR's that have been removed from list.
Owners
Change Requestor
Change Administrator
Change Management Board
Change Review Panel
Change Request Implementation Team
NA
Desciption
| Impact | Does not change the physical layout of the accelerator, only matters of organization and documentation
| 4 Administrative | Detailed change design (or addition)
| 3 Low | Performance related, impacts risk.
| 2 Medium | Cost driver, Impact on physics or dectors, CFS driver
1 High
| Explanation of date fields | Date CR was formally created (CR document received, number generated etc.)
| Creation date | Date of last change in register (normally due to a change of State, Owner or in some cases comment)
| Date modified | The date set for the next "action", explained in comment field. For example, the date the CR will be discussed by the CMB. Exact meaning varies depending on state.
Next deadline