## Slide 1
Ideas on TPC Assembly
Volker Prahl, Thomas Schörner-Sadenius
Paris, 8/9 October 2015

## Slide 2
Outline
Some basic considerations
Horizontal / vertical TPC assembly (in the AH?)
A first shot at the various possible TPC project plans
TPC insertion in the DH

## Slide 3
Some basic assumptions – all to be argued
No (long) transport of full TPC, field cage or fully equipped end-plates  need to assemble TPC at IP campus
Our assumption here: TPC assembly in the AH. Compatible with Yasuhiro’s overall plan assuming realistic TPC time scales?
Then space in AH necessary
Do it in research office building? But then where full TPC system test (gas!)?
No TPC assembly in DH.
No TPC assembly in DH – sufficient space and possibility to work in parallel with yoke construction, but probably bad timeslot?
Current scenario therefore:
  Horizontal or vertical assembly in AH hall (exact position tbd)
  Space requirement: 100 m2 (probably 60 m2 enough, but some contingency), plus storage space (for modules) and test area for modules
  Field cage delivered in one or two big pieces and assembled in AH
  Necessity to create grey-room / ISO7 characteristics around TPC assembly place

## Slide 4
Location in AH (from Yasuhiro’s yoke assembly plan)
Questions:
Grey-room quality after delivery of field cage and mounted end-plates?
Position of large door?
TPC Assembly horizontal - long
Door position?
Obsolete after yesterday’s discussion?

## Slide 5
Location in AH (from Yasuhiro’s yoke assembly plan)
TPC Assembly horizontal - long
Possible TPC assembly area approx. 25×8 m2 (half the length also ok, greyroom / ISO7 needed)
Obsolete after yesterday’s discussion?

## Slide 6
Endplate frame
Field-cage in cradle
Vertical procedure in a few steps

## Slide 7
Vertical procedure in a few steps

## Slide 8
Vertical procedure in a few steps

## Slide 9
Vertical procedure in a few steps

## Slide 10
Vertical procedure in a few steps

## Slide 11
Vertical procedure in a few steps

## Slide 12
Then
Cleaning of field cage
Construction of grey/clean room around TPC field cage (ISO 7)
Equipping of end-plates with tested modules using robot (petal-like structures in EP quadrant holes).
System test (in AH)
Vertical procedure in a few steps

## Slide 13
Horizontal procedure in a few steps
Note: – Greyroom / ISO7 with stable T and FFUs needed from start. – Access to greyroom through sliding gate with air lock
– Assumption that field cage self-supporting and first EP equipment
Length min. 12 m
Width min. 6 m
Trolley with self-supporting thorn (load 100 kg, sideview)
Platforms for inner vessel and field cage: (re)movable

## Slide 14
Horizontal procedure in a few steps
End-plate structures on trolleys and beginning of end-plate equipping (R); supporting star on inner-vessel platform

## Slide 15
Horizontal procedure in a few steps
Field-cage assembly

## Slide 16
Horizontal procedure in a few steps
Marriage of field-cage and end-plate R

## Slide 17
Horizontal procedure in a few steps
Set-up of inner vessel with cathode (“sail”)

## Slide 18
Horizontal procedure in a few steps
Marriage of inner vessel with cathode and field cage

## Slide 19
Horizontal procedure in a few steps
Marriage of inner vessel with cathode and field cage
Alternative: First fixing of inner vessel in field cage,
then installation / spanning of cathode.

## Slide 20
Horizontal procedure in a few steps
Marriage of inner vessel with cathode and field cage. Fixing the supporting “star” supporting the inner vessel and the sail

## Slide 21
Horizontal procedure in a few steps
Removing inner-vessel platform and finalisation of end-plate L

## Slide 22
Horizontal procedure in a few steps
Inserting end-plate L: approaching the field cage …

## Slide 23
Horizontal procedure in a few steps
Inserting end-plate L: approaching the field cage, supporting the inner vessel and removing the supporting star, …

## Slide 24
Horizontal procedure in a few steps
Inserting end-plate L: approaching the field cage, supporting the inner vessel + removing the supporting star, pushing in end-plate L

## Slide 25
Horizontal procedure in a few steps
Ready

## Slide 26
Alternative horizontal procedure
Assumptions: Similar as before, but …
EP equipment at the end with robot
Question of overall time planning (end-plate equipment the most time-consuming item

## Slide 27
Vertical procedure – time estimate

## Slide 28
Horizontal procedure – time estimate

## Slide 29
TPC insertion – mechanism?
Rails
Space?

## Slide 31
Rail

## Slide 36
Carbon bands

## Slide 37
Carbon bands
How many?
Size?
How about longitudinal strain?

## Slide 39
Veeeeery preliminary conclusions
Currently, more in favour of vertical assembly:
Space requirements
Time requirements
Ease of access / logistics
…
But many steps need thorough planning, and many engineering solutions are still missing.
Also for insertion of TPC into ILD, and for mounting and suspension
Nevertheless – best current guess:
Assembly requires one year after delivery of field cage
Space requirements: 100 m2 (ISO 7 / greyroom quality)
Plus space for module storage and testing, plus services

## Slide 40
Some near-future steps
Continue to work on the models, assumptions and their consequences
Principal procedures, needs and requirements
Some important topics:
  Support of TPC in ILC?
  Prevention of longitudinal movement?
  Cathode design?
  End-plate design?
  Space and infrastructure in DH (gas, power, electronic hut etc.)
To be decided soon: Where to assemble TPC?
AH or research office building?
If research office building, then still full TPC system test before lowering in AH?
Draw on previous experience
Specifically ALICE  meeting in November at CERN
Get in touch with global integration efforts
Hope to intensify contact to Yasuhiro