## Slide 1: ILD assembly timeline
2017/5/16
Yasuhiro Sugimoto

## Slide 2: Staging impact
Staging scenario starting from ECM=250 GeV is being discussed
Accelerator construction period could be shorter than 10 years
Can we make detector construction period shorter than 10 years?

## Slide 3: Original schedule
ILD will get ready before beam commissioning in Y10
AH ready
DH ready
SiD
lowering

## Slide 4: 0.5 year earlier commissioning
If occasional access to the detector during beam commissioning is possible, 0.5 year earlier beam commissioning is acceptable
AH ready
DH ready
SiD
lowering

## Slide 5: 1 year earlier commissioning
If the beam line is shielded (by SiD?) by the end of Y8, 1 year earlier beam commissioning is acceptable
AH ready
DH ready
SiD
lowering
Site ready

## Slide 6: Critical path
There is no way to shorten the detector construction period after DH completion
If land development is delayed by 1.5 y, completion of DH construction and ILD assembly would be delayed by 1.5 y (Accelerator construction will be also delayed)
Site ready
From slide by
Tokiko Onuki

## Slide 7: Conclusion
0.5 year earlier beam commissioning will give very little impact on ILD assembly scenario
1 year earlier beam commissioning would require earlier roll-in of SiD or dedicated radiation shield around the IP
Consistent timeline including CFS, accelerator (ML, DR, RTML), and detector assembly is necessary