## Slide 1: Update of Human Resource Estimate for ILC-250
A. Yamamoto and S. Michizono
Provided for discussions at KEK-ILC Int’l WG:
190526a
Updated: , 190602, 190618

## Slide 2: HR Estimates for 250 GeV Staging Opt. (C-->) A assuming a partly energy-scaling model
Area System | TDR Construct. + Install. [k p-hr] | TDR HR Sum [k p-hr] | Fraction unhanged | Fraction changed: Offset + E. Scaling | Staging 250-C [k p-hrs] (%) | Staring/TDR | Reduct. Ratio [%]
Common | 6,076 + 1,050 = | 7 ,126 | 0.3 | 0.2+ 0.5 x 0.490 | 5,309 | 74.5% | - 25.5 %
e- Source | 588 + 200 = | 788 | 1.0 | n/a | 788 | 100 | 0
e+ Source | 826 + 300 = | 1,126 | 1.0 | n/a | 1,126 | 100 | 0
Damping Rings | 996 + 1,000 = | 1,996 | 1.0 | 1.00 | 1,996 | 100 | 0
RTML | 1,318 + 250 = | 1,568 | 0.3 | 0.2 + 0.5 x 0.490 | 1,168 | 74.5 | - 25.5
Main Linac | 6,331 + 2,200= | 8,351 | 0 | 0.2 + 0.8 x 0.490 | 5,050 | 59.2 | - 40.8
BDS | 933 + 700 = | 1,663 | 1.0 | n/a | 1,633 | 100 | 0
IR | 123 + 0 = | 123 | 1.0 | n/a | 123 | 100 | 0
TOTAL | 17,192 + 5,700 = | 22,892 |  |  | 17,193 | 75.1 % | - 24.9 %
Notes; |  |  | 0.3*: not for ML | 0.2* : off set assumed 0.490 ** : (125x1.06 – 15) / (250x1.02-15) |  |  | 
Updated, 170725

## Slide 3: ILC250 Staff (HR) Annual Profile scaled from ILC500, originally 190602
Ay-190618
Some “zero” should be revised.

## Slide 4: ILC250 Staff (HR) Annual Profile adjusted/updated for smoothing Also, matched to MEXT-report-2018, on Acc/CFS/Manage.
Ay-190618

## Slide 5
Excel Reference: TDR-schedule-Labor-resource-180118(v1)-180114-190602, Sheet: Tech Sys (2-ay)(ILC250) (2)
Chart: ILC-250 Tech. System Staff (HR) Annual-Profile (TS-adustment included: 190602, Acc/CFS/Manage Balanced, 190618)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
CFS-Civil construction | 43.7101 | 43.7101 | 37.8775 | 18.8421 | 15 | 12 | 10 | 10 | 10
CFS-other | 2 | 3.0849 | 7.5633 | 21.2795 | 27.5062 | 14.7205 | 12.5299 | 11.0642 | 10
Survey and alignment | 2 | 4.2168 | 11.0879 | 37.2416 | 56.8045 | 53.8291 | 53.019 | 33.5793 | 32.2122
L-band Cavities and Cryomodules | 54.1541 | 94.9601 | 143.9601 | 180.4532 | 179.9601 | 171.7222 | 151.7555 | 131.1712 | 57.781
L-band HLRF | 49.5886 | 49.5886 | 49.5886 | 49.7244 | 49.5886 | 48.2429 | 47.2933 | 37.6948 | 30
Cryogenics | 43.2254 | 48.9557 | 34.117 | 34.2104 | 32.5926 | 24.9661 | 22.5525 | 21.3917 | 20
Magnets and Power Supplies | 5 | 0 | 93.5435 | 144.0214 | 194.1334 | 169.9826 | 152.3576 | 86.8595 | 26.2365
Integrated Controls and LLRF | 29.4768 | 21.9602 | 40.3632 | 54.4807 | 110.2579 | 104.3504 | 100.1819 | 71.5674 | 36.5616
Computing Infrastructure | 69.6897 | 69.6897 | 69.6897 | 69.8806 | 69.6897 | 69.6897 | 69.6897 | 54.8806 | 35.1241
Instrumentation | 2 | 7 | 44.8431 | 52.4814 | 68.5688 | 46.6048 | 31.1069 | 19.3491 | 6.7147
Dumps and Collimators | 3 | 5 | 21.9517 | 22.0119 | 25.8528 | 20.5212 | 16.7592 | 9.2664 | 1.6139
Vacuum | 3 | 4 | 4.7051 | 7.6088 | 13.5308 | 12.936 | 12.5163 | 7.496 | 5

## Slide 6
Excel Reference: TDR-schedule-Labor-resource-180118(v1)-180114-190602, Sheet: Tech Sys (2-ay)(ILC250) (2)
AY-190618
Chart: ILC-250 Overall Staff (HR) Annual Profile updated, 190618
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Tech-sys. (ILC-250) | 385 | 610 | 890 | 1050 | 1210 | 1100 | 1000 | 770 | 450
Installation (ILC-250) | 0 | 0 | 60 | 60 | 60 | 655 | 960 | 500 | 350

## Slide 7
Excel Reference: TDR-schedule-Labor-resource-180118(v1)-180114-190602, Sheet: Tech Sys (2-ay)(ILC250) (2)
Chart: ILC-250 Tech. System Staff (HR) Annual-Profile (TS-adustment included: 190602, Acc/CFS/Manage Balanced, 190618)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
CFS-Civil construction | 43.7101 | 43.7101 | 37.8775 | 18.8421 | 15 | 12 | 10 | 10 | 10
CFS-other | 2 | 3.0849 | 7.5633 | 21.2795 | 27.5062 | 14.7205 | 12.5299 | 11.0642 | 10
Survey and alignment | 2 | 4.2168 | 11.0879 | 37.2416 | 56.8045 | 53.8291 | 53.019 | 33.5793 | 32.2122
L-band Cavities and Cryomodules | 54.1541 | 94.9601 | 143.9601 | 180.4532 | 179.9601 | 171.7222 | 151.7555 | 131.1712 | 57.781
L-band HLRF | 49.5886 | 49.5886 | 49.5886 | 49.7244 | 49.5886 | 48.2429 | 47.2933 | 37.6948 | 30
Cryogenics | 43.2254 | 48.9557 | 34.117 | 34.2104 | 32.5926 | 24.9661 | 22.5525 | 21.3917 | 20
Magnets and Power Supplies | 5 | 0 | 93.5435 | 144.0214 | 194.1334 | 169.9826 | 152.3576 | 86.8595 | 26.2365
Integrated Controls and LLRF | 29.4768 | 21.9602 | 40.3632 | 54.4807 | 110.2579 | 104.3504 | 100.1819 | 71.5674 | 36.5616
Computing Infrastructure | 69.6897 | 69.6897 | 69.6897 | 69.8806 | 69.6897 | 69.6897 | 69.6897 | 54.8806 | 35.1241
Instrumentation | 2 | 7 | 44.8431 | 52.4814 | 68.5688 | 46.6048 | 31.1069 | 19.3491 | 6.7147
Dumps and Collimators | 3 | 5 | 21.9517 | 22.0119 | 25.8528 | 20.5212 | 16.7592 | 9.2664 | 1.6139
Vacuum | 3 | 4 | 4.7051 | 7.6088 | 13.5308 | 12.936 | 12.5163 | 7.496 | 5
Chart: ILC-250 Overall Staff (HR) Annual Profile updated, 190618
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Tech-sys. (ILC-250) | 385 | 610 | 890 | 1050 | 1210 | 1100 | 1000 | 770 | 450
Installation (ILC-250) | 0 | 0 | 60 | 60 | 60 | 655 | 960 | 500 | 350
AY-190618

## Slide 8: Appendix
Data before Adjustment
ILC250A and A’ Cryogenics Consideration,
Previous Study.

## Slide 9: ILC250 Staff (HR) Annual Profile adjusted/updated for smoothing but Acc/CFS/Management balance not consistent with Report to MEXT in 2018
Year | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | Total | Avg.
CFS-Civil construction | 43.7 | 43.7 | 37.9 | 18.8 | 15.0 | 10.0 | 10.0 | 8.0 | 5.0 | 192.1 | 21.3
CFS-other | 2.0 | 3.1 | 7.6 | 21.3 | 27.5 | 14.7 | 12.5 | 8.1 | 5.0 | 101.7 | 11.3
Survey and alignment | 2.0 | 4.2 | 11.1 | 37.2 | 56.8 | 53.8 | 53.0 | 33.6 | 32.2 | 284.0 | 31.6
L-band Cavities and Cryomodules | 54.2 | 95.0 | 144.0 | 180.5 | 180.0 | 171.7 | 161.8 | 142.2 | 62.8 | 1191.9 | 132.4
L-band HLRF | 49.6 | 49.6 | 49.6 | 49.7 | 49.6 | 48.2 | 47.3 | 38.7 | 30.0 | 412.3 | 45.8
Cryogenics | 43.2 | 49.0 | 34.1 | 34.2 | 32.6 | 25.0 | 22.6 | 20.4 | 20.0 | 281.0 | 31.2
Magnets and Power Supplies | 5.0 | 0.0 | 93.5 | 144.0 | 204.1 | 170.0 | 152.4 | 86.9 | 31.2 | 887.1 | 98.6
Integrated Controls and LLRF | 29.5 | 22.0 | 40.4 | 54.5 | 110.3 | 104.4 | 100.2 | 81.6 | 39.6 | 582.2 | 64.7
Computing Infrastructure | 69.7 | 69.7 | 69.7 | 69.9 | 69.7 | 69.7 | 69.7 | 64.9 | 47.1 | 600.0 | 66.7
Instrumentation | 2.0 | 7.0 | 44.8 | 52.5 | 68.6 | 46.6 | 31.1 | 19.3 | 6.7 | 278.7 | 31.0
Dumps and Collimators | 3.0 | 5.0 | 22.0 | 22.0 | 25.9 | 20.5 | 16.8 | 9.3 | 1.6 | 126.0 | 14.0
Vacuum | 3.0 | 4.0 | 4.7 | 7.6 | 13.5 | 12.9 | 12.5 | 7.5 | 5.0 | 70.8 | 7.9
Other HLRF | 3.0 | 4.0 | 4.7 | 10.7 | 10.6 | 7.9 | 5.9 | 0.0 | 5.0 | 51.8 | 5.8
Area system specific | 10.0 | 75.6 | 90.9 | 111.6 | 111.2 | 110.2 | 79.3 | 40.2 | 8.4 | 637.5 | 70.8
Laboratory Management | 56.5 | 169.5 | 226.0 | 226.6 | 226.0 | 226.0 | 216.0 | 200.6 | 144.0 | 1691.2 | 187.9
Simulations and Operations | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 6.6 | 76.7 | 8.5
Tech-System-Total (Updated, 190602) | 385.1 | 610.1 | 889.7 | 1049.9 | 1210.1 | 1100.4 | 999.7 | 769.9 | 450.2 | 7465.2 | 829.5
Installation | 0.0 | 0.0 | 59.5 | 59.6 | 60.5 | 655.0 | 959.8 | 500.4 | 350.4 | 2645 | 294
Year | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 
Tech-sys. (ILC-250) | 385 | 610 | 890 | 1050 | 1210 | 1100 | 1000 | 770 | 450 | 7465 | 829
Installation (ILC-250) | 0 | 0 | 60 | 60 | 60 | 655 | 960 | 500 | 350 | 2645 | 294
TOTAL (ILC-250A) | 385 | 610 | 950 | 1110 | 1270 | 1755 | 1960 | 1270 | 800 | 10110 | 1123
Excel Reference: TDR-schedule-Labor-resource-180118(v1)-180114-190602, Sheet: Tech Sys (2-ay)(ILC250)
AY-190602

## Slide 10
Chart: ILC-250 Tech. System Staff (HR) Annual-Profile (TS-adustment included: 190602)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
CFS-Civil construction | 43.7101 | 43.7101 | 37.8775 | 18.8421 | 15 | 10 | 10 | 8 | 5
CFS-other | 2 | 3.0849 | 7.5633 | 21.2795 | 27.5062 | 14.7205 | 12.5299 | 8.0642 | 5
Survey and alignment | 2 | 4.2168 | 11.0879 | 37.2416 | 56.8045 | 53.8291 | 53.019 | 33.5793 | 32.2122
L-band Cavities and Cryomodules | 54.1541 | 94.9601 | 143.9601 | 180.4532 | 179.9601 | 171.7222 | 161.7555 | 142.1712 | 62.781
L-band HLRF | 49.5886 | 49.5886 | 49.5886 | 49.7244 | 49.5886 | 48.2429 | 47.2933 | 38.6948 | 30
Cryogenics | 43.2254 | 48.9557 | 34.117 | 34.2104 | 32.5926 | 24.9661 | 22.5525 | 20.3917 | 20
Magnets and Power Supplies | 5 | 0 | 93.5435 | 144.0214 | 204.1334 | 169.9826 | 152.3576 | 86.8595 | 31.2365
Integrated Controls and LLRF | 29.4768 | 21.9602 | 40.3632 | 54.4807 | 110.2579 | 104.3504 | 100.1819 | 81.5674 | 39.5616
Computing Infrastructure | 69.6897 | 69.6897 | 69.6897 | 69.8806 | 69.6897 | 69.6897 | 69.6897 | 64.8806 | 47.1241
Instrumentation | 2 | 7 | 44.8431 | 52.4814 | 68.5688 | 46.6048 | 31.1069 | 19.3491 | 6.7147
Dumps and Collimators | 3 | 5 | 21.9517 | 22.0119 | 25.8528 | 20.5212 | 16.7592 | 9.2664 | 1.6139
Vacuum | 3 | 4 | 4.7051 | 7.6088 | 13.5308 | 12.936 | 12.5163 | 7.496 | 5
Excel Reference: TDR-schedule-Labor-resource-180118(v1)-180114-190602, Sheet: Tech Sys (2-ay)(ILC250)

## Slide 11
Chart: ILC-250 Overall Staff (HR) Annual Profile
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Tech-sys. (ILC-250) | 385 | 610 | 890 | 1050 | 1210 | 1100 | 1000 | 770 | 450
Installation (ILC-250) | 0 | 0 | 60 | 60 | 60 | 655 | 960 | 500 | 350
Excel Reference: TDR-schedule-Labor-resource-180118(v1)-180114-190602, Sheet: Tech Sys (2-ay)(ILC250)
AY-190602

## Slide 12
Chart: ILC-250 Overall Staff (HR) Annual Profile
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Tech-sys. (ILC-250) | 385 | 610 | 890 | 1050 | 1210 | 1100 | 1000 | 770 | 450
Installation (ILC-250) | 0 | 0 | 60 | 60 | 60 | 655 | 960 | 500 | 350
Chart: ILC-250 Tech. System Staff (HR) Annual-Profile (TS-adustment included: 190602)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
CFS-Civil construction | 43.7101 | 43.7101 | 37.8775 | 18.8421 | 15 | 10 | 10 | 8 | 5
CFS-other | 2 | 3.0849 | 7.5633 | 21.2795 | 27.5062 | 14.7205 | 12.5299 | 8.0642 | 5
Survey and alignment | 2 | 4.2168 | 11.0879 | 37.2416 | 56.8045 | 53.8291 | 53.019 | 33.5793 | 32.2122
L-band Cavities and Cryomodules | 54.1541 | 94.9601 | 143.9601 | 180.4532 | 179.9601 | 171.7222 | 161.7555 | 142.1712 | 62.781
L-band HLRF | 49.5886 | 49.5886 | 49.5886 | 49.7244 | 49.5886 | 48.2429 | 47.2933 | 38.6948 | 30
Cryogenics | 43.2254 | 48.9557 | 34.117 | 34.2104 | 32.5926 | 24.9661 | 22.5525 | 20.3917 | 20
Magnets and Power Supplies | 5 | 0 | 93.5435 | 144.0214 | 204.1334 | 169.9826 | 152.3576 | 86.8595 | 31.2365
Integrated Controls and LLRF | 29.4768 | 21.9602 | 40.3632 | 54.4807 | 110.2579 | 104.3504 | 100.1819 | 81.5674 | 39.5616
Computing Infrastructure | 69.6897 | 69.6897 | 69.6897 | 69.8806 | 69.6897 | 69.6897 | 69.6897 | 64.8806 | 47.1241
Instrumentation | 2 | 7 | 44.8431 | 52.4814 | 68.5688 | 46.6048 | 31.1069 | 19.3491 | 6.7147
Dumps and Collimators | 3 | 5 | 21.9517 | 22.0119 | 25.8528 | 20.5212 | 16.7592 | 9.2664 | 1.6139
Vacuum | 3 | 4 | 4.7051 | 7.6088 | 13.5308 | 12.936 | 12.5163 | 7.496 | 5
Excel Reference: TDR-schedule-Labor-resource-180118(v1)-180114-190602, Sheet: Tech Sys (2-ay)(ILC250)
AY-190602

## Slide 13: ILC250 AC Plug-Power Estimates to be updated, re-estimated by NW/BL (190531)
 | 500 (DKS) | 250A-Base L. 5Hz, 1312 L= 1.35E34 | 250A’ (RD) 5Hz, 1312 L = 1.35E34 | 250A 5Hz, 2625 L=2.7E34 | 500 @ 250 10Hz, 2625 L= 5.4E34 | 500 5Hz, 2625 L = ?
Gradient | 31.5 | 31.5 | 35 | 31.5 | 14.7 | 31.5
Qo | 1E10 | 1E10 | 1.6E10 | 1E10 | 1E10 | 1E10
ML-Egain | 470 | 220 | 220 | 220 | 220 | 470
E. Ratio | 1 | 0.47 | 0.47 | 0.47 | 0.47 | 1
ML | 104.1 | 48.0 | 47.3 | 61.1 | 100.4 | 130.6
e- Source | 4.87 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6
e+ Source | 9.32 | 10.2 | 10.2 | 10.2 | 10.2 | 10.2
DR | 15.72 | 13.6 | 13.6 | 21.5 | 30.3 | 21.5
RTML | 10.40 | 10.4 | 10.4 | 13.9 | 13.9 | 13.9
BDS | 12.38 | 9.3 | 9.3 | 9.3 | 9.3 | 12.4
Dumps | 1.21 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2
IR | 5.76 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8
Main Campus |  |  |  |  |  | 
General Margin |  |  |  |  |  | 
Total | 163.8 | 104.0 | 103.3 | 128.5 | 178.6 | 201.1
AY-190602
Excel Reference: ILC TDR AC Power Scaling CR018-b (190602)

## Slide 14: ILC250 AC Plug-Power Estimates to be updated Adjustment suggested by AY, refering Re-estimate by NW/BL (190602)
 | 500 (DKS) | 250A-Base L. 5Hz, 1312 L= 1.35E34 | 250A’ (RD) 5Hz, 1312 L = 1.35E34 | 250A 5Hz, 2625 L=2.7E34 | 500 @ 250 10Hz, 2625 L= 5.4E34 | 500 5Hz, 2625 L = ?
Gradient | 31.5 | 31.5 | 35 | 31.5 | 14.7 | 31.5
Qo | 1E10 | 1E10 | 1.6E10 | 1E10 | 1E10 | 1E10
ML-Egain | 470 | 220 | 220 | 220 | 220 | 470
E. Ratio | 1 | 0.47 | 0.47 | 0.47 | 0.47 | 1
ML | 104.1 | 49.4 | 48.5 | 62,6 | 103.0 | 133.8
e- Source | 4.87 | 5.6 | 4.8 | 5.6 | 5.6 | 5.6
e+ Source | 9.32 | 10.2 | 9.6 | 10.2 | 10.2 | 10.2
DR | 15.72 | 13.6 | 13.6 | 21.5 | 30.3 | 21.5
RTML | 10.40 | 10.4 | 8.4 | 13.9 | 13.9 | 13.9
BDS | 12.38 | 9.3 | 9.3 | 9.3 | 9.3 | 12.4
Dumps | 1.21 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2
IR | 5.76 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8
Main Campus |  | 2.7 | 2.7 | 2.7 | 2.7 | 2.7
General Margin |  | 3.3 | 3.1 | 4.0 | 5.4 | 6.2
Total | 163.8 | 111.5 | 106.9 | 136.7 | 184.5 | 213.2
AY-190603
Excel Reference: ILC TDR AC Power Scaling CR018-b (190602)

## Slide 15: LIC Labor-Matrix in TDR (500 GeV) & Staging (250 GeV) (Offset + Linear-Scaling – updated, 170725)
Area System | TDR (500GeV) Construct. + Install. [k p-hrs] | Scaling Factor (a model for 250 GeV) Unchange/offset + reduction, ratio | Staging (250 GeV) [k p-hrs] (%) |  | Reduct. Ratio [%]
Common | 6,076 + 1,050 = 7,126 | 0.3 + 0.2＊+ 0.5 x 0.490** = 0.745 | 5,309 |  | - 25.5 %
e- Source | 588 + 200 = 788 | 1.00 | 788 |  | 0 %
e+ Source | 826 + 300 = 1,126 | 1.00 | 1,126 |  | 0 %
Damping Rings | 996 + 1,000 = 1,996 | 1.00 | 1,996 |  | 0 %
RTML | 1,318 + 250 = 1,568 | 0.3 + 0.2* + 0.5 x 0.490** = 0.745 | 1,168 |  | - 25.5 %
Main Linac | 6,331 + 2,200 = 8,531 | 0.2* + 0.8 x 0.490 = 0.592 | 5,050 |  | - 40.8 %
BDS | 933 + 700 = 1,663 | 1.00 | 1,633 |  | 0%
IR | 123 + 0 = 123 | 1.00 | 123 |  | 0%
TOTAL | 17,192 + 5,700 = 22,892 | -- | 17,193 (75.1 %) |  | - 24.9 %
Notes; |  | 0.3 {=(22.89-7.13-8.53)/22.89)} + 0.2 = 0.5  ratio (non-ML) + offset (ML): (0.2 for Labor ** ML energy staging ratio: 0.2 : offset for the subject related the ML. (125x1.06 – 15) / (250x1.02-15) = 0.490 |  |  | 
TDR HR matrix: updated by GD, 2014-3-11
Updated, 170725

## Slide 16: TDR HR: Annual Profile (P-Hrs) (File: TDR Schedule-Labor-130118(v1))
 | Technical Systems | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | Total
 | CFS-Civil construction | 95.10554 | 95.10554 | 85.1901 | 47.64457 | 0 | 0 | 0 | 0 | 0 | 323
 | CFS-other | 0 | 5.244321 | 12.85757 | 42.84532 | 59.99215 | 38.25649 | 34.5325 | 2.932897 | 0 | 197
 | Survey and alignment | 0 | 9.62219 | 23.03445 | 78.10301 | 119.3178 | 112.5283 | 111.1512 | 78.16131 | 40.08175 | 572
 | L-band Cavities and Cryomodules | 32.29786 | 491.9682 | 491.9682 | 493.316 | 491.9682 | 477.9638 | 435.7843 | 436.9782 | 180.2834 | 3,533
 | L-band HLRF | 138.0417 | 138.0417 | 138.0417 | 138.4199 | 138.0417 | 135.754 | 134.1398 | 55.86098 | 0 | 1,016
 | Cryogenics | 73.48326 | 83.2247 | 83.2247 | 83.45271 | 80.63323 | 67.66827 | 63.56516 | 26.47097 | 0 | 562
 | Magnets and Power Supplies | 0 | 0 | 159.024 | 244.8363 | 429.245 | 362.6887 | 315.7261 | 204.5347 | 76.56634 | 1,793
 | Integrated Controls and LLRF | 50.11056 | 50.11056 | 81.39559 | 105.4304 | 261.3907 | 251.3479 | 244.2615 | 212.8194 | 102.1197 | 1,359
 | Computing Infrastructure | 159.0235 | 159.0235 | 159.0235 | 159.4592 | 159.0235 | 159.0235 | 159.0235 | 159.4592 | 118.9408 | 1,392
 | Instrumentation | 0 | 0 | 76.23333 | 89.21837 | 129.7314 | 92.39265 | 66.04613 | 46.09397 | 16.86104 | 517
 | Dumps and Collimators | 0 | 0 | 37.31793 | 37.42017 | 46.21967 | 37.15599 | 30.76059 | 18.029 | 3.682639 | 211
 | Vacuum | 0 | 0 | 7.998691 | 12.93493 | 26.46036 | 25.44918 | 24.73569 | 16.21067 | 5.610076 | 119
 | Other HLRF | 0 | 0 | 8.040918 | 18.14325 | 18.09368 | 13.37928 | 10.05276 | 0 | 0 | 68
 | Area system specific | 0 | 128.5999 | 154.5202 | 206.846 | 206.2808 | 206.2808 | 171.1677 | 85.58764 | 21.4133 | 1,181
 | Laboratory Management | 128.9237 | 386.771 | 515.6947 | 517.1076 | 515.6947 | 515.6947 | 515.6947 | 517.1076 | 385.7114 | 3,998
 | Simulations and Operations | 19.99218 | 19.99218 | 19.99218 | 20.04695 | 19.99218 | 19.99218 | 19.99218 | 20.04695 | 14.95305 | 175
 | TOTAL w/o installation |  |  |  |  |  |  |  |  |  | 
 | Installation | 0 | 0 | 135.7336 | 136.1055 | 135.7336 | 1305.71 | 1937.996 | 1161.28 | 620.7742 | 5,433
 | TOTAL |  |  |  |  |  |  |  |  |  | 22,448

## Slide 17: TDR HR: Annual Profile: FTE-Yrs (File: TDR Schedule-Labor-130118(v1))
 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | Total | Average
 | CFS-Civil construction | 55.94443 | 55.94443 | 50.11182 | 28.02622 | 0 | 0 | 0 | 0 | 0 | 190 | 21.1141
 | CFS-other | 0 | 3.084895 | 7.563279 | 25.20313 | 35.2895 | 22.50382 | 20.31324 | 1.725234 | 0 | 116 | 12.85368
 | Survey and alignment | 0 | 5.660112 | 13.54968 | 45.94295 | 70.18694 | 66.19312 | 65.38305 | 45.97724 | 23.5775 | 336 | 37.38562
 | L-band Cavities and Cryomodules | 18.99874 | 289.393 | 289.393 | 290.1859 | 289.393 | 281.1552 | 256.3437 | 257.046 | 106.049 | 2,078 | 230.8842
 | L-band HLRF | 81.20101 | 81.20101 | 81.20101 | 81.42348 | 81.20101 | 79.85532 | 78.90579 | 32.8594 | 0 | 598 | 66.42756
 | Cryogenics | 43.22545 | 48.95571 | 48.95571 | 49.08983 | 47.43131 | 39.80486 | 37.39127 | 15.57116 | 0 | 330 | 36.71392
 | Magnets and Power Supplies | 0 | 0 | 93.54351 | 144.0214 | 252.497 | 213.3463 | 185.7212 | 120.3145 | 45.03902 | 1,054 | 117.1648
 | Integrated Controls and LLRF | 29.4768 | 29.4768 | 47.87976 | 62.01788 | 153.7593 | 147.8517 | 143.6833 | 125.1879 | 60.07042 | 799 | 88.82264
 | Computing Infrastructure | 93.54322 | 93.54322 | 93.54322 | 93.7995 | 93.54322 | 93.54322 | 93.54322 | 93.7995 | 69.9652 | 819 | 90.98039
 | Instrumentation | 0 | 0 | 44.84314 | 52.4814 | 76.31261 | 54.34862 | 38.85066 | 27.1141 | 9.91826 | 304 | 33.7632
 | Dumps and Collimators | 0 | 0 | 21.95172 | 22.01187 | 27.18804 | 21.85647 | 18.09447 | 10.60529 | 2.166258 | 124 | 13.76379
 | Vacuum | 0 | 0 | 4.705113 | 7.60878 | 15.56492 | 14.97011 | 14.5504 | 9.53569 | 3.300045 | 70 | 7.803896
 | Other HLRF | 0 | 0 | 4.729952 | 10.6725 | 10.64334 | 7.870162 | 5.913388 | 0 | 0 | 40 | 4.425482
 | Area system specific | 0 | 75.64702 | 90.89425 | 121.6741 | 121.3417 | 121.3417 | 100.6869 | 50.34567 | 12.59606 | 695 | 77.16971
 | Laboratory Management | 75.83746 | 227.5124 | 303.3498 | 304.1809 | 303.3498 | 303.3498 | 303.3498 | 304.1809 | 226.889 | 2,352 | 261.3333
 | Simulations and Operations | 11.7601 | 11.7601 | 11.7601 | 11.79232 | 11.7601 | 11.7601 | 11.7601 | 11.79232 | 8.795913 | 103 | 11.43791
 |  | 409.9872 | 922.1787 | 1207.975 | 1350.132 | 1589.462 | 1479.75 | 1374.491 | 1106.055 | 568.3668 | 10008.4 | 1112.044
 | Installation | 0 | 0 | 79.8433 | 80.06205 | 79.8433 | 768.0648 | 1139.998 | 683.106 | 365.1613 | 3,196 | 
 | TOTAL | 410 | 922 | 1,288 | 1,430 | 1,669 | 2,248 | 2,514 | 1,789 | 934 | 13,204 | 1467.164

## Slide 18: TDR Technical Systems Annual Profile (FTE)
Chart: ILC TDR Explicit Labor profile, excluding Installation
CFS-Civil construction | 55.9444 | 55.9444 | 50.1118 | 28.0262 | 0 | 0 | 0 | 0 | 0
CFS-other | 0 | 3.0849 | 7.5633 | 25.2031 | 35.2895 | 22.5038 | 20.3132 | 1.7252 | 0
Survey and alignment | 0 | 5.6601 | 13.5497 | 45.9429 | 70.1869 | 66.1931 | 65.3831 | 45.9772 | 23.5775
L-band Cavities and Cryomodules | 18.9987 | 289.393 | 289.393 | 290.1859 | 289.393 | 281.1552 | 256.3437 | 257.046 | 106.049
L-band HLRF | 81.201 | 81.201 | 81.201 | 81.4235 | 81.201 | 79.8553 | 78.9058 | 32.8594 | 0
Cryogenics | 43.2254 | 48.9557 | 48.9557 | 49.0898 | 47.4313 | 39.8049 | 37.3913 | 15.5712 | 0
Magnets and Power Supplies | 0 | 0 | 93.5435 | 144.0214 | 252.497 | 213.3463 | 185.7212 | 120.3145 | 45.039
Integrated Controls and LLRF | 29.4768 | 29.4768 | 47.8798 | 62.0179 | 153.7593 | 147.8517 | 143.6833 | 125.1879 | 60.0704
Computing Infrastructure | 93.5432 | 93.5432 | 93.5432 | 93.7995 | 93.5432 | 93.5432 | 93.5432 | 93.7995 | 69.9652
Instrumentation | 0 | 0 | 44.8431 | 52.4814 | 76.3126 | 54.3486 | 38.8507 | 27.1141 | 9.9183
Dumps and Collimators | 0 | 0 | 21.9517 | 22.0119 | 27.188 | 21.8565 | 18.0945 | 10.6053 | 2.1663
Vacuum | 0 | 0 | 4.7051 | 7.6088 | 15.5649 | 14.9701 | 14.5504 | 9.5357 | 3.3

## Slide 19: ILC-250A HR: Annual Profile: P-Hrs (File: TDR Schedule-Labor-130118-v1)
 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | TOTAL | 
 | CFS-Civil construction | 74.30722 | 74.30722 | 64.39179 | 32.03159 | 0 | 0 | 0 | 0 | 0 | 245 | 
 | CFS-other | 0 | 5.244321 | 12.85757 | 36.17511 | 46.76047 | 25.02481 | 21.30082 | 1.809111 | 0 | 149 | 
 | Survey and alignment | 0 | 7.168531 | 18.84947 | 63.31077 | 96.56763 | 91.50947 | 90.13235 | 57.08488 | 238.3608 | 663 | 
 | L-band Cavities and Cryomodules | 24.0619 | 305.9322 | 305.9322 | 306.7704 | 305.9322 | 291.9278 | 257.9843 | 258.6911 | 106.7278 | 2,164 | 
 | L-band HLRF | 84.30056 | 84.30056 | 84.30056 | 84.53152 | 84.30056 | 82.01288 | 80.39868 | 33.4811 | 0 | 618 | 
 | Cryogenics | 73.48326 | 83.2247 | 57.99883 | 58.15773 | 55.40736 | 42.4424 | 38.3393 | 15.96595 | 0 | 425 | 
 | Magnets and Power Supplies | 0 | 0 | 159.024 | 244.8363 | 372.5267 | 305.9705 | 259.0078 | 147.6611 | 53.10209 | 1,542 | 
 | Integrated Controls and LLRF | 50.11056 | 37.33237 | 68.6174 | 92.61719 | 187.4385 | 177.3956 | 170.3093 | 138.6645 | 67.2547 | 990 | 
 | Computing Infrastructure | 118.4725 | 118.4725 | 118.4725 | 118.7971 | 118.4725 | 118.4725 | 118.4725 | 118.7971 | 88.61093 | 1,037 | 
 | Instrumentation | 0 | 0 | 76.23333 | 89.21837 | 116.567 | 79.2282 | 52.88167 | 32.89345 | 11.41493 | 458 | 
 | Dumps and Collimators | 0 | 0 | 37.31793 | 37.42017 | 43.94973 | 34.88605 | 28.49065 | 15.75283 | 2.743566 | 201 | 
 | Vacuum | 0 | 0 | 7.998691 | 12.93493 | 23.00237 | 21.99118 | 21.27769 | 12.7432 | 0 | 100 | 
 | Other HLRF | 0 | 0 | 8.040918 | 18.14325 | 18.09368 | 13.37928 | 10.05276 | 0 | 0 | 68 | 
 | Area system specific | 0 | 128.5999 | 154.5202 | 189.6403 | 189.1222 | 189.1222 | 134.7283 | 68.38198 | 14.31479 | 1,068 | 
 | Laboratory Management | 96.04814 | 288.1444 | 384.1926 | 385.2451 | 384.1926 | 384.1926 | 384.1926 | 385.2451 | 287.355 | 2,979 | 
 | Simulations and Operations | 14.89417 | 14.89417 | 14.89417 | 14.93498 | 14.89417 | 14.89417 | 14.89417 | 14.93498 | 11.14002 | 130 | 
 | TS-Adjustment |  |  |  |  |  |  |  |  |  |  | 
 | Installation | 0 | 0 | 101.1215 | 101.3986 | 101.1215 | 1111.749 | 1631.597 | 854.0416 | 391.6043 | 4,293 | 
 | Inst-Adjustment |  |  |  |  |  |  |  |  |  |  | 
 | TOTAL |  |  |  |  |  |  |  |  |  | 17,130 | 

## Slide 20: ILC-250A HR: Annual Profile: FTE-Yrs (File: TDR Schedule-Labor-190526:ay)
 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | Total | Average
 | CFS-Civil construction | 43.71013 | 43.71013 | 37.87752 | 18.84211 | 0 | 0 | 0 | 0 | 0 | 144 | 16.01554
 | CFS-other | 0 | 3.084895 | 7.563279 | 21.27947 | 27.50616 | 14.72048 | 12.52989 | 1.064183 | 0 | 88 | 9.749818
 | Survey and alignment | 0 | 4.216783 | 11.08792 | 37.24163 | 56.80449 | 53.8291 | 53.01903 | 33.57934 | 140.2122 | 390 | 43.33228
 | L-band Cavities and Cryomodules | 14.15406 | 179.9601 | 179.9601 | 180.4532 | 179.9601 | 171.7222 | 151.7555 | 152.1712 | 62.78103 | 1,273 | 141.4353
 | L-band HLRF | 49.58856 | 49.58856 | 49.58856 | 49.72442 | 49.58856 | 48.24287 | 47.29334 | 19.69476 | 0 | 363 | 40.36774
 | Cryogenics | 43.22545 | 48.95571 | 34.11696 | 34.21043 | 32.59257 | 24.96612 | 22.55253 | 9.391738 | 0 | 250 | 27.77905
 | Magnets and Power Supplies | 0 | 0 | 93.54351 | 144.0214 | 219.1334 | 179.9826 | 152.3576 | 86.85945 | 31.23652 | 907 | 100.7927
 | Integrated Controls and LLRF | 29.4768 | 21.96022 | 40.36318 | 54.4807 | 110.2579 | 104.3504 | 100.1819 | 81.56736 | 39.56159 | 582 | 64.6889
 | Computing Infrastructure | 69.6897 | 69.6897 | 69.6897 | 69.88063 | 69.6897 | 69.6897 | 69.6897 | 69.88063 | 52.12408 | 610 | 67.78039
 | Instrumentation | 0 | 0 | 44.84314 | 52.4814 | 68.56881 | 46.60482 | 31.10687 | 19.34909 | 6.714662 | 270 | 29.9632
 | Dumps and Collimators | 0 | 0 | 21.95172 | 22.01187 | 25.85278 | 20.52121 | 16.75921 | 9.266371 | 1.613862 | 118 | 13.10856
 | Vacuum | 0 | 0 | 4.705113 | 7.60878 | 13.5308 | 12.93599 | 12.51629 | 7.496 | 0 | 59 | 6.532553
 | Other HLRF | 0 | 0 | 4.729952 | 10.6725 | 10.64334 | 7.870162 | 5.913388 | 0 | 0 | 40 | 4.425482
 | Area system specific | 0 | 75.64702 | 90.89425 | 111.5531 | 111.2484 | 111.2484 | 79.25192 | 40.22469 | 8.420464 | 628 | 69.83202
 | Laboratory Management | 56.4989 | 169.4967 | 225.9956 | 226.6148 | 225.9956 | 225.9956 | 225.9956 | 226.6148 | 169.0323 | 1,752 | 194.6933
 | Simulations and Operations | 8.761277 | 8.761277 | 8.761277 | 8.78528 | 8.761277 | 8.761277 | 8.761277 | 8.78528 | 6.552955 | 77 | 8.521242
 | TS-Adjustment | 70 | -65 | -36 | 0 | 0 | -1 | 10 | 4 | -68 | (86) | 
 |  | 385.1049 | 610.0711 | 889.6718 | 1049.862 | 1210.134 | 1100.441 | 999.684 | 769.9449 | 450.2497 | 7,465 | 829.4626
 | Installation | 0 | 0 | 59.48326 | 59.64622 | 59.48326 | 653.9699 | 959.7629 | 502.3774 | 230.3555 | 2,525 | 
 | Inst-Adjustment | 0 | 0 | 1 | 0 | 1 | 1 | 0 | -2 | 119 | 120 | 
 | TOTAL | 385 | 610 | 950 | 1,110 | 1,271 | 1,755 | 1,959 | 1,270 | 800 | 10,110 | 1123.36