## Slide 1: Sources Subgroup Summary K. Yokoya, for IDT-WG2 Jan.18
Jan.11 8th Regular meeting
  Masao Kuriki, Hitoshi Hayano, Gudi Moortgat-Pick, Joe Grames, Kaoru Yokoya, Steffen Doebert, Shin Michizono, Jenny List, Andy Lankford, Sabine Riemann, Peter Sievers, Benno List, Angeles Faus-Golfe, R. Rimmer (Some are missing, perhaps)
  Indico https://agenda.linearcollider.org/event/9053/
Technical Preparation Document and the plan (Shin Michizono) (IDT-WG2-Sources20210111.pdf uploaded to indico)
  2 new topics
  Review of the Work Packages
    Review WPs in February or March
    Review team will consist of 9 people (3 from 3 regions) and will be appointed soon.
    Schedule: one day (2 hours) for each of SRF, DR/BDS, and Sources subgroup
    Check points
      Any missing items
      Contents of each WP
  Change of Pre-Lab timeline, in particular the shift of the positron scheme selection
    Present schedule: the selection at the end of 1st year (or beginning of 2nd year)
    New schedule: in the middle of the 3rd year
    This will make the proposed participation of US labs more realistic (USFY2023 and 2024)

## Slide 2
Discussion
  Schedule
    In the present schedule only simulations can be done before the selection. Mock-ups, when needed, can be built only in the 2nd year. So, the new schedule is welcome.
    When does the tunnel construction start?
      Right after Pre-Lab
    All members agreed to this new schedule
  Review
    Reviewers elected?  not yet. Earlier review in mid February
    At least 2 more subgroup meetings before the review
    Not open to public
    Collaborating labs: not a subject of the review. Decision by EB.
    Not a one-day meeting. 2 hours times 3 days. May be 3 hours for sources?
Next subgroup meeting
  Jan.25 (Mon), regular time. Prepare for the review.