## Sheet1
Milestone | Activity | When? | Who?
MS-0 | Set CC design specification | T0
MS-1 | Cavity EM design optimisation | T0 +
MS-2 | Coupler EM design optimisation (i.e. LOM, SOM and HOM) | T0 +
MS-3 | Tuner design and EM optimisation | T0 +
MS-4 | High power validation of prototype cavity? | T0 +
MS-5 | Cavity down-selection process? (Do we need prototype for this, if so cavity only or with couplers? Do we maybe down-select to 2 cavity options, then have a final down-select later?) | T0 +
MS-6 | Integrated 'dressed' cavity optimisation | T0 +
MS-7 | Crab CM design | T0 +
MS-8 | Prototype CM sub-component design, prototyping and qualification (i.e. dressed cavity, alignment, couplers, shields etc) | T0 +
MS-9 | Final Cavity down-selection (choose final solution)? | T0 +
MS-10 | Crab CM assesmbly design | T0 +
MS-11 | Assembly tooling development | T0 +
MS-12 | Prototype CM assembly | T0 +
MS-13 | Provision of all CM sub-components | T0 +
MS-14 | Acceptance verification of integrated CM | T0 +
MS-15 | High power test of prototype CM | T0 +
MS-16 | RF synchronisation of integrated 2-cavity CM cavities | T0 +
MS-17 | Design of CM transport system | T0 +
MS-18 | Manufacture of CM transport system | T0 +
MS-19 | Transportation validation (ship trans-atlantic and retest) | T0 +
Questions
What do we need to perform a technoogy down-selection?
Do we have a dual down-selection, one before and one during Cryomodule design?
What/when do we define as T0?
Do we have any activities which can start now, or do we wait for Pre-Lab to start?
What do we include within the scope for 4-yr Pre-Lab?
Do we have all activities covered by collaborator potential contributions?