## Specification
Parameter | Recent Spec (After TDR) |  |  | 10Hz Upgrade1,2 | 1 TeV CoM Spec 2 |  |  | Ref: | 1 CERN-ESU-004, Physics Briefing Book Input for the European Strategy for Particle Physics Update 2020, p168
Beam Energy (GeV) e- | 125 |  |  |  | 500 |  |  |  | 2 ILC250 accelerator, Shin Michizonono for US Snowmass AF-EF-meeting, June 2020, p6
Crossing Angle (mrad) | 14
Installation site (m from IP) | 14
RF Repetition Rate (Hz) | 5 |  |  | 10 | 4
Bunch Train Length (ms) | 727 |  |  | 363.5
Bunch Spacing (ns) | 554 |  |  | 366
Beam current (mA) | 5.8 |  |  | 8.75 | 7.6
Operating Temp (K) | 2 ?
Cryomodule installation length (m) | 3.8
Beam-pipe separation (m) | 0.197
Cavity Frequency (GHz) | 3.9 | 2.6 | 1.3 |  | 3.9 | 2.6 | 1.3
Total Kick Voltage (MV) | 0.615 | 0.923 | 1.845 |  | 2.5 | 2.769 | 7.4
Relative RF Phase Jitter (deg rms) | 0.069 | 0.069 | 0.023 |  | 0.069? | 0.069? | 0.023?
(fs rms) | 49 | 49 | 49 |  | 49? | 49? | 49?
Missing Parameters
Longitudinal impedance threshold (Mohm)
Trasverse impedance threshold (Mohm/m)
Cavity alignment tolerance (x, y and roll) (mm, mrad)
Minimum beam aperture size (mm)
Qext
Cavity bandwidth (Hz)
Input power (kW)
Cavity dynamic load (W)
Cryomodule static load (W)

## R&D Plan
Milestone | Activity | When? | Date | Duration (Months)? | Assumptions
MS-0 | Set CC design specification | T0 + 3m | 2021-06-23 | 3 | What do we set as T0?
MS-1 | Cavity EM design optimisation | T0 + 18m | 2022-09-23 | 12
MS-2 | Coupler EM design optimisation (i.e. LOM, SOM and HOM) | T0 + 18m | 2022-09-24 | 12
MS-3 | Dressed cavity mechanical design with tuner (concept) | T0 + 18m | 2022-09-25 | 6
MS-4 | Prelim cavity down-selection process (2off) - Agreed | T0 + 18m | 2022-09-26 | Decision 1