## ADI
ADI
Area systems | Subjects | Items | Deliverables | Related area and technical systems
| Lattice Integration | Integrate design contribustions from accelerator areas | Integrated lattice; central lattice repository; treaty point list; overall accelerator foot print; subsystem specifications; overall accelerator parameters | ADI/Source/DR/RTML/ML/BDS
| Beam dynamics | Evaluate the beam dynamics of the ILC accelerator | Start-to-end simulations | ADI/Source/DR/RTML/ML/BDS
| Availability and operations | Determine the expected availability of the accelerator | Availability estimate; operations and maintenance concept; availability specifications for subsystems and components | ADI/Source/DR/RTML/ML/BDS
| Commissioning | Plan the comissioning of the accelerator | Comissioning concept | ADI/Source/DR/RTML/ML/BDS
| Accelerator integration management | Manage the AD&I effort during the Prelab phase | Accelerator design EDR | ADI

## DR
Damping Rings
Work packages | Subjects | Items | Deliverables | Related area and technical systems
| WP-12 | DR cell design, based on present ILC optics (WP-12) | Beam optics design | DR(WP-12)
|  | DR cell design (further small emittancs) (WP-12) | Beam optics design | DR(WP-12)
|  | Dynamic aperture survey (WP-12) | Beam optics design; Performance specification | DR(WP-12)
|  | SC wiggler magnets (WP-12) | Component design; costing; power, cooling water | DR(WP-12)/SCmagnet
|  | Design of PM (WP-12) | Component design; costing; power, cooling water | DR(WP-12)/PMmagnet
|  | PM prototyping (WP-12) | Performance specification | DR(WP-12)/PMmagnet
|  | NC magnets (WP-12) | Component design; costing; power, cooling water | DR(WP-12)/Magnet
| WP-13 | Ion trapping and fast ion instability (WP-13) | Performance specification | DR(WP-13)
|  | Electron cloud instability (WP-13) | Performance specification | DR(WP-13)
|  | Fast FB system design (WP-13) | System design; costing | DR(WP-13)/Instrumentation
|  | Fast FB test (WP-13) | Performance specification | DR(WP-13)/Instrumentation
|  | Vacuum chambers to reduce SEY for positrin DR (WP-13) | Performance specification | DR(WP-13)/Vacuum (basic design was in TDR )
| WP-14 | System design of fast injection/extraction system (WP-14) | System design; | DR(WP-14)
|  | Fast kicker devices (WP-14) | Component design; costing; | DR(WP-14)
|  | Fast kicker power supplies (WP-14) | Component design; costing; power, cooling water estimation | DR(WP-14)
|  | System design of injection kicker for E-driven PS (WP-14) | System design; | DR(WP-14)
|  | Injection kicker device for E-driven PS (WP-14) | Component design; costing; | DR(WP-14)
|  | Injection kicker power supplies for E-driven PS (WP-14) | Component design; costing; power, cooling water estimation | DR(WP-14)/Source
Area systems | Subjects | Items | Deliverables | Related area and technical systems
| DR optics design and system integration | DR cell design, based on present ILC optics (WP-12) | Beam optics design | DR(WP-12)
|  | DR cell design (further small emittancs) (WP-12) | Beam optics design | DR(WP-12)
|  | DR straight section optics design (for WP-14) | Beam optics design | DR
|  | System design of the beam diagnostics | Beam optics design | DR
|  | ILC lattice integration | Beam optics design | ADI/DR
|  | Contact part with ADI for the beam optics issues | Beam optics design | DR/ADI
|  | Integration of the hardware components in DR | Component counts; costing; power, cooling water estimation | DR/TechnicalSystems
| DR beam dynamics and tuning | Dynamic aperture survey (WP-12) | Beam optics design; Performance specification | DR(WP-12)
|  | Small emittance tuning | Performance specification | DR
|  | Tolerance evaluation for each device | Performance specification | DR
|  | Ion trapping and fast ion instability (WP-13) | Performance specification | DR(WP-13)
|  | Electron cloud instability (WP-13) | Performance specification | DR(WP-13)
|  | Spece charge effects | Performance specification | DR
|  | Impedance driven instability | Performance specification | DR
|  | Tune shift by quadrupole wake for E-driven PS | Performance specification | DR/Source
|  | Contact part with ADI for the beam dynamics and tuning | Performance specification | DR/ADI
| DR Injection/extraction system | System design of fast injection/extraction system (WP-14) | System design; | DR(WP-14)
|  | Fast kicker devices (WP-14) | Component design; costing; | DR(WP-14)
|  | Fast kicker power supplies (WP-14) | Component design; costing; power, cooling water estimation | DR(WP-14)
|  | System design of injection kicker for E-driven PS (WP-14) | System design; | DR(WP-14)
|  | Injection kicker device for E-driven PS (WP-14) | Component design; costing; | DR(WP-14)
|  | Injection kicker power supplies for E-driven PS (WP-14) | Component design; costing; power, cooling water estimation | DR(WP-14)/Source
Technical systems | Subjects | Items | Deliverables | Related area and technical systems
| DR instrumentation (Hardware) | Fast FB system design (WP-13) | System design; costing | DR(WP-13)/Instrumentation
|  | Fast FB test (WP-13) | Performance specification | DR(WP-13)/Instrumentation
|  | Beam position monitors | costing | Instrumentation/DR
|  | Beam current monitor | costing | Instrumentation/DR
|  | Tune monitor | costing | Instrumentation/DR
|  | Beam size/profile monitors | costing | Instrumentation/DR
|  | Slow orbit FB | Component design; costing | Instrumentation/DR
|  | Polarimeters | Component design; costing | Instrumentation/CFS/DR
|  | Cabling and monitor station | Component counts; costing; power, cooling water estimation | Instrumentation/CFS/DR
| DR RF system (Hardware) | SC cavities, cryostat, He transfer | Component design; costing | SCRF/DR
|  | RF source, waveguide | Component design; costing; power, cooling water estimation | HLRF/DR
|  | LLRF | Component design; costing | LLRF/DR
| DR magnets (Hardware) | SC wiggler magnets (WP-12) | Component design; costing; power, cooling water estimation | DR(WP-12)/SCmagnet
|  | Cryostat, He transfer | Component design; costing | SCmagnet/DR
|  | Power supplies, and cabling for SC magnet | Component counts; costing; power, cooling water estimation | SCmagnet/DR
|  | Design of PM (WP-12) | Component design; costing; power, cooling water estimation | DR(WP-12)/PMmagnet
|  | PM prototyping (WP-12) | Performance specification | DR(WP-12)/PMmagnet
|  | NC magnets (WP-12) | Component design; costing; power, cooling water estimation | DR(WP-12)/Magnet
|  | Power supplies, and cabling for NC magnet | Component counts; costing; power, cooling water estimation | Magnet/DR
|  | Magnet support | System design; costing | Alignment/Magnet/DR
| DR vacuum system (Hardware) | Vacuum chambers to reduce SEY for positrin DR (WP-13) | Performance specification | DR(WP-13)/Vacuum (basic design was in TDR )
|  | Regular vacuum components (pump etc.) | Component counts; costing; cooling water estimation | Vacuum/DR
|  | Impedance calculations | Performance specification | Vacuum/DR
|  | Photon stopper from wigglers | Component design; costing; cooling water estimation | Vacuum/CFS/DR
| DR CFS ans others | Cooling water system and distribution | System design; costing; cooling water estimation | CFS/Magnet/Vacuum/HLRF/DR
|  | Magnet power supply station | System design | CFS/Magnet/DR
|  | System design of device installation procedures | System design | CFS/SCRF/SCmagnet/Magnet/DR
|  | Cryogenics | System design; costing; power, cooling water estimation | Cryo/CFS/SCRF/SCmagnet/DR
|  | System design of DR alignment system | System design | Alignment/CFS/DR
|  | System design of emergency abort | System design | ADI/CFS/DR

## RTML
RTML
Area systems | Subjects | Items | Deliverables | Related area and technical systems
| RTML optics design and system integration | Optics design of RTML | Beam optics design | RTML
|  | Optics design of LTR, RTL beamline | Beam optics design | RTML
|  | Optics design of tuning dump line | Beam optics design | RTML
|  | Spin rotator in LTR | Beam optics design | RTML/Source
|  | Spin rotator in RTML end | Beam optics design | RTML (basic design was in TDR )
|  | System design of the beam diagnostics | System design | RTML
|  | System design of the orbit FB/feed forward at turn around | System design | RTML
|  | ILC lattice integration | Beam optics design | ADI/RTML
|  | Contact part with ADI for the beam optics issues | Beam optics design | RTML/ADI
|  | Integration of the hardware components in DR | Component counts; Costing; Power, cooling water estimation | RTML/TechnicalSystems
| RTML beam dynamics and tuning | Low emittance transport (alignment, space charge, SR, CSR, wake) | Performance specification | RTML
|  | Tolerance evaluation for each device | Performance specification | RTML
|  | Effect of the stray/external field | Performance specification | RTML
|  | Effect of the ground motion | Performance specification | RTML
|  | Beam polarization preservation | Performance specification | RTML/MDI
|  | S2E simulation (RTML part) | System design; Performance specification | ADI/RTML
|  | Contact part with ADI for the beam dynamics and tuning | Performance specification | ADI/RTML
Technical systems | Subjects | Items | Deliverables | Related area and technical systems
| RTML instrumentation (Hardware) | Beam position monitors | Costing | Instrumentation/RTML
|  | Beam current monitor | Costing | Instrumentation/RTML
|  | Beam size/profile monitors | Costing | Instrumentation/RTML
|  | Orbit FB/feed forward (turn around) | System design; Costing | Instrumentation/RTML
|  | Polarimeters (?) | System design; Costing | Instrumentation/ADI/MDI/CFS/RTML
|  | Cabling and monitor station | Component counts; costing; power, cooling water estimation | Instrumentation/CFS/RTML
| RTML magnets (Hardware) | SC solenoid magnet and cryostat for spin rotators | Component design; costing; power, estimation | SCmagnet /RTML
|  | He transfer | Component counts; costing | SCmagnet /RTML
|  | Power supplies, and cabling for SC magnet | Component design; costing; power, cooling water estimation | SCmagnet /RTML
|  | NC magnets | Component design; costing | Magnet/RTML
|  | Power supplies, and cabling for NC magnet | Component design; costing; power, cooling water estimation | Magnet/RTML
|  | Magnet support | System design; costing | Alignmet/Magnet/ADI/CFS/RTML
| RTML vacuum (Hardware) | Chamber, vacuum pump etc. | Component counts; costing | Vacuum/RTML
|  | Chamber support | System design; costing | Alignmet/ADI/CFS/RTML
| RTML CFS and others | Cooling water system and distribution | System design; costing; cooling water estimation | CFS/Magnet/Vacuum/RTML
|  | Magnet power supply station | System design | CFS/Magnet/RTML
|  | System design of device installation procedures | System design | CFS/Magnet/SCmagnet/RTML
|  | Cryogenics | System design; costing; power, cooling water estimation | Cryo/CFS/Magnet/SCmagnet/RTML
|  | System design of RTML alignment system | System design | Alignment/CFS/RTML
|  | System design of emergency abort | System design | ADI/CFS/RTML
|  | Tuning beam dump | Component design; costing; cooling water estimation | Beam dump/CFS/ADI/RTML

## ML
ML
Area systems | Subjects | Items | Deliverables | Related area and technical systems
| ML optics design | Optics design of BC | Beam optics design | ML
|  | Optics design of ML (crymodule) | Beam optics design | ML
|  | Optics design of ML (NC section) | Beam optics design | ML
|  | Optics design of tuning dump line | Beam optics design | ML
|  | System design of the beam diagnostics | System design | ML
|  | ILC lattice integration | Beam optics design | ADI/ML
|  | Contact part with ADI for the beam optics issues | Beam optics design | ML/ADI
|  | Integration of the hardware components in DR | Component counts; Costing; Power, cooling water estimation | ML/TechnicalSystems
| ML beam dynamics and tuning | Low emittance transport of BC | Performance specification | ML
|  | Low emittance transport of ML | Performance specification | ML
|  | Tolerance evaluation of BC RF phase | Performance specification | ML
|  | Tolerance evaluation for each device | Performance specification | ML
|  | Effect of the earth curvature | Performance specification | ML
|  | Effect of the ground motion | Performance specification | ML
|  | System design of the RF phase tuning | Performance specification | ML/LLRF/ADI
|  | Beam polarization preservation | Performance specification | ML/MDI
|  | S2E simulation (RTML part) | System design; Performance specification | ADI/RTML
|  | Contact part with ADI for the beam dynamics and tuning | Performance specification | ADI/RTML
Technical systems | Subjects | Items | Deliverables | Related area and technical systems
| ML instrumentation (Hardware) | Beam position monitors | Costing | Instrumentation/ML
|  | Beam current monitor | Costing | Instrumentation/ML
|  | Beam size/profile monitors | Costing | Instrumentation/ML
|  | Cabling and monitor station | Component counts; costing; power, cooling water estimation | Instrumentation/CFS/ML
| ML RF system (Hardware) | SC cavities, cryostat, He transfer | Component design; costing | SCRF/ML
|  | RF source, waveguide | Component design; costing; power, cooling water estimation | SCRF/HLRF/ML
|  | LLRF | Component design; costing | SCRF/LLRF/ML
| ML magnets (Hardware) | SC magnets, He transfer | Component design; costing; power, estimation | SCRF/SCmagnet /ML
|  | Power supplies, and cabling for SC magnet | Component design; costing; power, cooling water estimation | SCRF/SCmagnet /ML
|  | NC magnets | Component design; costing | Magnet/ML
|  | Power supplies, and cabling for NC magnet | Component design; costing; power, cooling water estimation | Magnet/ML
|  | NC magnet support | System design; costing | Alignmet/Magnet/ADI/CFS/ML
| RTML vacuum (Hardware) | Chamber, vacuum pump etc. | Component counts; costing | Vacuum/ML
|  | Chamber support | System design; costing | Alignmet/ADI/CFS/ML
| RTML CFS and others | Cooling water system and distribution | System design; costing; cooling water estimation | CFS/Magnet/Vacuum/ML
|  | Magnet power supply station | System design | CFS/Magnet/ML
|  | System design of device installation procedures | System design | CFS/Magnet/SCmagnet/ML
|  | Cryogenics | System design; costing; power, cooling water estimation | Cryo/SCRF/CFS/Magnet/SCmagnet/ML
|  | System design of BC and ML alignment system | System design | Alignment/CFS/ML
|  | System design of emergency abort | System design | ADI/CFS/ML
|  | Tuning beam dump (BC) | Component design; costing; cooling water estimation | BeamDump/CFS/ADI/ML

## BDS
Beam Delivery System
Work packages | Subjects | Items | Deliverables | Related area and technical systems
| WP-15 | Optics design of final focus beam line (WP-15) | Beam optics design | BDS(WP-15)
|  | Correction of higher order optics aberration (WP-15) | Performance specification | BDS(WP-15)
|  | Beam tuning study with machine learning technique (WP-15) | Performance specification | BDS(WP-15)
|  | ATF3 beam test (WP-15) | Performance specification | BDS(WP-15)
|  | Short range static wakefield effect (WP-15) | Performance specification | BDS(WP-15)
|  | Short range dynamic wakefield effect (WP-15) | Performance specification | BDS(WP-15)
|  | System desing of the intra-train orbit FB (WP-15) | Performance specification | BDS(WP-15)
|  | Cavity BPMs (WP-15) | Performance specification; Costing | BDS(WP-15)/Instrumentation
|  | IP intra-train FB (WP-15) | Performance specification; Costing | BDS(WP-15)/Instrumentation
|  | Upstream intra-train FB (WP-15) | Performance specification; Costing | BDS(WP-15)/Instrumentation
|  | Wakefield minimization for vacuum components (WP-15) | System design; Performance specification; Costing | BDS(WP-15)/Vacuum
|  | Collimators (WP-15) | System design; Performance specification; Costing | BDS(WP-15)/CFS
| WP-16 | QD0 package with anti-solenoid (WP-16) | Component design; Costing; Power estimation | BDS(WP-16)/SCmagnet/MDI
|  | QF1 package (WP-16) | Component design; Costing; Power estimation | BDS(WP-16/SCmagnet/MDI
|  | QD0 vibration test (WP-16) | Performance specification | BDS(WP-16)/SCmagnet/MDI
| MDI | Polarimeters | Performance specification; Costing | BDS(MDI)/Instrumentation/ADI/MDI
|  | Energy spectrometers | Performance specification; Costing | BDS(MDI)/Instrumentation/ADI/MDI
|  | Anti-DID (detector solenoid) | Component design | BDS(MDI)/Scmagnet/MDI
|  | System design of push-pull scheme | System design | BDS(MDI)/CFS/ADI/MDI
|  | System design of Packman | System design | BDS(MDI)/CFS/ADI/MDI
Area systems | Subjects | Items | Deliverables | Related area and technical systems
| BDS optics design and system integration | Optics design of final focus beam line (WP-15) | Beam optics design | BDS(WP-15)
|  | Optics design for QD0 package design (for WP-16) | Beam optics design | BDS/SC magnet/MDI
|  | Optics design for QF1 package design (for WP-16) | Beam optics design | BDS/SC magnet/MDI
|  | Optics design for Crab cavity (for WP-3) | Beam optics design | BDS/SCRF/MDI/ADI
|  | Optics design of beam diagnostic system | Beam optics design | BDS
|  | Optics design of beam collimation system | Beam optics design | BDS
|  | Optics design of mail beam dump line | Beam optics design | BDS
|  | Optics design of tuning beam dump line | Beam optics design | BDS
|  | System design of the beam diagnostics | System design | BDS
|  | System design of Muon collimation | System design | BDS/MDI/ADI
|  | ILC lattice integration | Beam optics design | ADI/BDS
|  | Contact part with ADI for the beam optics issues | Beam optics design | BDS/ADI
|  | Integration of the hardware components in DR | Component counts; Costing; Power, cooling water estimation | BDS/TechnicalSystems
|  | L* and crossing angle | System design | ADI/CFS/MDI/BDS
| BDS beam dynamics and tuning | Correction of higher order optics aberration (WP-15) | Performance specification | BDS(WP-15)
|  | Beam tuning study with machine learning technique (WP-15) | Performance specification | BDS(WP-15)
|  | Tolerance evaluation for each device | Performance specification | BDS
|  | Effect of the ground motion | Performance specification | BDS
|  | Long range static wakefield effect (resisitive wall) | Performance specification | BDS
|  | Vacuum chamber diameter and magnet bore design | Performance specification | BDS
|  | ATF3 beam test (WP-15) | Performance specification | BDS(WP-15)
|  | Short range static wakefield effect (WP-15) | Performance specification | BDS(WP-15)
|  | Short range dynamic wakefield effect (WP-15) | Performance specification | BDS(WP-15)
|  | System desing of the intra-train orbit FB (WP-15) | Performance specification | BDS(WP-15)
|  | Collimation and detector background evaluation (incl. Muon) | Performance specification | BDS/MDI/ADI
|  | Radiation loss evaluation in dump line | Performance specification; System design | BDS/ADI/CFS
|  | S2E simulation (BDS part) | Performance specification; System design | ADI/BDS
|  | Contact part with ADI for the beam dynamics and tuning | Performance specification | ADI/BDS
Technical systems | Subjects | Items | Deliverables | Related area and technical systems
| BDS instrumentation (Hardware) | Cavity BPMs (WP-15) | Performance specification; Costing | BDS(WP-15)/Instrumentation
|  | IP intra-train FB (WP-15) | Performance specification; Costing | BDS(WP-15)/Instrumentation
|  | Upstream intra-train FB (WP-15) | Performance specification; Costing | BDS(WP-15)/Instrumentation
|  | Beam current monitor | Costing | Instrumentation/BDS
|  | Beam size/profile monitors (laserwire) | Performance specification; Costing | Instrumentation/BDS
|  | Polarimeters | Performance specification; Costing | BDS(MDI)/Instrumentation/ADI/MDI
|  | Energy spectrometers | Performance specification; Costing | BDS(MDI)/Instrumentation/ADI/MDI
|  | Laser station for polarimeters and laser wire monitors | System design; Costing; Power, cooling water estimation | Instrumentation/CFS/BDS/MDI
|  | Cabling and monitor station | Component counts; Costing; Power, cooling water estimation | Instrumentation/CFS/BDS
| BDS RF system (Hardware) | Crab cavities, cryostat (WP-3) | Component design; Costing; Power estimation | SCRF(WP-3)/BDS
|  | Crab cavity LLRF (WP-3) | System design; Costing; | SCRF(WP-3)/LLRF/BDS
|  | He transfer for crab cavity | System design; Costing; | SCRF(WP-3?)/BDS
|  | RF source, waveguide for crab cavity | Component design; Costing; Power, cooling water estimation | HLRF/SCRF(WP-3)/BDS
| BDS magnets (Hardware) | QD0 package with anti-solenoid (WP-16) | Component design; Costing; Power estimation | BDS(WP-16)/SCmagnet/MDI
|  | QF1 package (WP-16) | Component design; Costing; Power estimation | BDS(WP-16)/SCmagnet/MDI
|  | QD0 vibration test (WP-16) | Performance specification | BDS(WP-16)/SCmagnet/MDI
|  | Anti-DID (detector solenoid) | Component design | BDS(MDI)/Scmagnet/MDI
|  | He transfer for QD0/QF1 package | System design; Costing | SCmagnet/BDS/MDI
|  | Power supplies, and cabling for SC magnet | Costing; Power, cooling water estimation | SCmagnet/BDS
|  | NC magnets | Costing; Power, cooling water estimation | Magnet/BDS
|  | Beam sweeper for dump | Component design; Costing; Power, cooling water estimation | Magnet/BDS
|  | Muon spoiler and muon wall | Component design; Costing; Cooling water estimation | Magnet/BDS/MDI
|  | Power supplies, and cabling for NC magnet | Component counts; Costing; Power, cooling water estimation | Magnet/BDS
|  | Magnet support | System design; Costing | Alignment/Magnet/BDS
| BDS vacuum system (Hardware) | Vacuum components (pipe, bellows, pump etc.) | Component counts; Costing | Vacuum/BDS
|  | Wakefield minimization for vacuum components (WP-15) | System design; Performance specification; Costing | BDS(WP-15)/Vacuum
|  | Chamber support | System design; Performance specification; Costing | BDS/Vacuum
| BDS CFS and others | Collimators (WP-15) | System design; Performance specification; Costing | BDS(WP-15)/CFS
|  | MPS collimators | System design; Performance specification; Costing | BDS/CFS/MDI
|  | Cooling water system and distribution | System design; Costing; Cooling water estimation | CFS/Magnet/Vacuum/HL RF/BDS
|  | Magnet power supply station | System design | CFS/Magnet/SCmagnet/BDS
|  | System design of device installation procedures | System design | CFS/SCRF/SCmagnet/Magnet/BDS
|  | Cryogenics | System design; Costing; Power, cooling water estimation | Cryo/CFS/SCRF/SCmagnet/BDS
|  | System design of BDS alignment system | System design | Alignment/CFS/BDS
|  | System design of emergency abort | System design | ADI/CFS/BDS
|  | Tuning beam dump | Component design; Costing; Cooling water estimation | Beam dump/CFS/ADI/BDS
|  | Main beam dump | Component design; Costing; Cooling water estimation | Beam dump(WP-17)/CFS/ADI/BDS
|  | System design of push-pull scheme | System design | BDS(MDI)/CFS/ADI/MDI
|  | System design of Packman | System design | BDS(MDI)/CFS/ADI/MDI