## Summary, Ver.0.2, 2021.4.25
ILC Prelab WBS
Draft
Original: |  | Updat;
Version 0.1 | 2021-04-06 | Version 0,2 | 2021-04-26
Benno List, DESY |  | S, Michizono & A, Tananiti |  |  | Blue: K. Yokoya |  |  | Brown: T. Okugi |  |  |  | Black: Y. Yamamoto
[5 empty] | WBS-FTEtable-Sources-vo-KY (210420) |  |  | Hresourece_okugi_20210426 (210423) |  |  |  | ILC-Prelab WBS-V2_SRF_25Apr2021
|  |  | WBS | Area Systems | Sys. Desig & EDR | Accelerator Technologies | [12 empty] | General Services |  | SUM (for Area)
[5 empty] | WBS-T1 | T2 | T3 | T4 | T5 | T6 | T7 | T8 | T9 | T10 | T11 | T12 | T13 | T14 | T15 | T16
[5 empty] | System Design | Area- Specific | Hub/ Infra-Struct. | Acc-Str. (SRF/NRF) | RF Power (HLRF) | Cryogenics | Magnet & PS | Vacuum | Collim. & Dump | Beam Instr. | LLRF/ Control | Installation | Survey- Align. | Common- Others | CE & CFs | Admin.& Management
|  | Japan | WBS-A1 -jp | ADI
|  |  | A2 -jp | Sources
|  |  | A3 -jp | DR
|  |  | A4 -jp | RTML
|  |  | A5 -jp | ML
|  |  | A6 -jp | BDS
SUM (Technology)
|  | Abroad | A1 -ab | ADI
|  |  | A2 -ab | Sources
|  |  | A3 -ab | DR
| , |  | A4 -ab | RTML
|  |  | A5 -ab | ML
|  |  | A6 -ab | BDS
SUM (Technology)
|  | Global | A1 -gl | ADI
|  |  | A2 -gl | Sources
|  |  | A3 -gl | DR
|  |  | A4 -gl | RTML
|  |  | A5 -gl | ML
|  |  | A6 -gl | BDS
SUM (Technolgy)
|  |  | WBS: Acc. Area | A1: Accelerator Design Integration (ADI)
A2: Sources
A3: Damping Ring (DR)
A4: Ring to Main Linac (RTML)
A5: Main Linac (ML)
A6: Beam Delivery Sysrtem (BDS)
|  |  | WBS: Tech. Sys. | T1: System Design | Accelerator Technologies T2: T11: Low Level RF and Control
|  |  |  | T2: Area Specific | Accelerator Technologies T2: T12: Installation
|  |  |  | T3: Hub/Infra-Structure | Accelerator Technologies T2: T13: Survey and Aalignment
|  |  |  | T4: Accelerating Strcture (SRF/NRF) | Accelerator Technologies T2: T14: Common or others
|  |  |  | T5: RF Power (HLRF) | Accelerator Technologies T2: T15: Civil Engineering and Conventional Facilities
|  |  |  | T6: Cryogenics | Accelerator Technologies T2: T16: Administration and Management
T7: Magnet and PS
T8: Vacuum
T9: Collimator and Beam Dump
T10: Beam Instrumentation

## WBS-SRF, Ver.2 2021.4.25
# | Code | Title |  |  | Y1 Global | Y2 Global | Y3 Global | Y4 Global | Global | Global Sum | Y1 JP | Y2 JP | Y3 JP | Y4 JP | JP | JP Sum | 担当 | Scoping statement | Deliverables
1 | 1 | Accelerator Design & Integration | [15 empty] | Design the ILC accelerator as a whole | Key performance figures; integrated lattice; overall machine layout; input to cost estimate; CFS requirements; EDR volume "accelerator design"
2 | 1.1 |  | Accelerator Integration | [14 empty] | Integrate the accelerator design, coordinate work of the accelerator areas and technical system work packages | Integrated ILC lattice; Overall system design; Chapter for EDR
3 | 1.1.1 |  |  | Lattice Integration | [13 empty] | Integrate design contribustions from accelerator areas | Integrated lattice; central lattice repository; treaty point list; overall accelerator foot print; subsystem specifications; overall accelerator parameters
4 | 1.1.2 |  |  | Beam dynamics | [13 empty] | Evaluate the beam dynamics of the ILC accelerator | Start-to-end simulations
5 | 1.1.3 |  |  | Availability and operations | [13 empty] | Determine the expected availability of the accelerator | Availability estimate; operations and maintenance concept; availability specifications for subsystems and components
6 | 1.1.4 |  |  | Commissioning | [13 empty] | Plan the comissioning of the accelerator | Comissioning concept
7 | 1.1.5 |  |  | Accelerator integration management | [13 empty] | Manage the AD&I effort during the Prelab phase | Accelerator design EDR
8 | 1.2 |  | Sources | [14 empty] | Design the electron and positron source systems, with prototypes of critical items | Source system lattices; Sources system design; Sources performance specification; component requirements and specifications; Component counts; Design and costs for sources specific components; Prototypes of critical items; Chapter for EDR
9 | 1.2.1 |  |  | Electron source system design | [13 empty] | Design the electron source system from gun to DR injection | Electron source system lattice; ES system design; ES performance specification; component requirements and specifications; Component counts; Chapter for EDR; Cost estimate for ES specific components
10 | 1.2.2 |  |  | WP04: Electron source | [13 empty] | Design gun and drive laser | ES gun and drive laser design
11 | 1.2.3 |  |  | Undulator positron source system design | [13 empty] | Design the undulator positron source system | Undulator positron source system lattice; UPS system design; UPS performance specification; Chapter for EDR
12 | 1.2.4 |  |  | WP05: Undulator | [13 empty] | Design undulators | Conceptual undulator design
13 | 1.2.5 |  |  | WP06: Rotating target (und. src.) | [13 empty] | Design rotating target for undulator source | Conceptual target design; prototype
14 | 1.2.6 |  |  | WP07: Magnetic focussing (und. src.) | [13 empty] | Design magnetic focussing device for undulator source | Conceptual focussing device design; prototype
15 | 1.2.7 |  |  | E-driven positron source system design | [13 empty] | Design the undulator positron source system
16 | 1.2.8 |  |  | WP08: Rotating target (e driven)
17 | 1.2.9 |  |  | WP09: Magnetic focussing (e driven)
18 | 1.2.10 |  |  | WP10: Capture caviity
19 | 1.2.11 |  |  | WP11: Target replacement
20 | 1.3 |  | Damping Rings | [14 empty] | Design the DR system | DR system lattice; DR system design; DR performance specification; component requirements and specifications; Component counts; Design and costing of DR specific components (RF system, wigglers, kickers); Chapter for EDR
21 | 1.3.1 |  |  | WP12: System design | [13 empty] | Design the damping ring system | DR source system lattice; DR system design; DR performance specification; component requirements and specifications; Component counts; Chapter for EDR
22 | 1.3.2 |  |  | WP13: Collective effects
23 | 1.3.3 |  |  | WP14: Injection / extraction | [13 empty] | Design and prototype DR injection and extraction kickers
24 | 1.3.4 |  |  | DR RF system | [13 empty] | Design DR RF system | indluded in SRF
25 | 1.3.5 |  |  | DR wigglers | [13 empty] | Design DR SC wigglers | indluded in Magnet?
26 | 1.4 |  | RTML | [14 empty] | Design the RTML system | RTML system lattice; RTML system design; RTML performance specification; component requirements and specifications; Component counts; Chapter for EDR
27 | 1.4.1 |  |  | RTML system design
28 | 1.4.2 |  |  | Spin rotators
29 | 1.4.3 |  |  | Emittance measurement and correction
30 | 1.5 |  | Main Linac and Bunch Compressors | [14 empty] | Design the main linac system, including bunch compressors | ML&BC system lattice; ML&BC system design; ML&BC performance specification; component requirements and specifications; Component counts; Chapter for EDR
31 | 1.5.1 |  |  | Main linac system design
32 | 1.5.2 |  |  | Bunch compressor design
33 | 1.6 |  | Beam Delivery System | [14 empty] | Design the beam delivery system and machine detector interface, including extraction line | BDS system lattice; BDS system design; BDS performance specification; component requirements and specifications; Component counts; Chapter for EDR; MDI specification; interrface specifications
34 | 1.6.1 |  |  | BDS system design
35 | 1.6.2 |  |  | Machine Detector Interface
36 | 1.6.3 |  |  | Beam characterisation | [13 empty] | Design emasurement of beam characteristics (energy, intensity, emittance, polarisation)
37 | 1.6.4 |  |  | WP15: Final focus
38 | 1.6.5 |  |  | WP16: Final doublet
39 | 1.7 |  | Magnets & Power Supplies | [14 empty] | Design magnets, kickers and power supplies | Conceptual magnet designs and specifications; magnet and power supply cost estimates (unit and overall costs); power supply concept; cabling design; CFS reqiorements; Chapter for EDR
40 | 1.7.1 |  |  | Normal conducting magnets | [13 empty] | Design all normal conducting magnets
41 | 1.7.2 |  |  | Permanent magnets | [13 empty] | Design all permanent magnets
42 | 1.7.3 |  |  | Kickers | [13 empty] | Design kicker magnets
43 | 1.7.4 |  |  | Magnet power supplies | [13 empty] | Design power supply system
44 | 1.8 |  | Vacuum System | [14 empty] | Design vacuum system | Conceptual layout of all warm vacuum sections; component specifications, counts and cost estimates; CFS requirements; Chapter for EDR
45 | 1.9 |  | Dumps and Collimators | [14 empty] | Design all beam dumps | Engineering layout of main dumps; conceptual layout of other dumps and collimators; Specifications; Cost estimates; CFS requirements; Chapter for EDR
46 | 1.9.1 |  |  | WP17: Main dumps | [13 empty] | Design main dumps, including water treatment system and radiation protection | Main dump engineering design; main dump radiation protection plan; main dump safety assessment
47 | 1.9.2 |  |  | WP18: Photon dump | [13 empty] | Design photon dump of undulator positron source | Photon dump engineering design
48 | 1.9.3 |  |  | Secondary Dumps | [13 empty] | Design all secondary dumps | Consptual design
49 | 1.9.4 |  |  | Collimators
50 | 1.10 |  | Instrumentation | [14 empty] | Design instrumentation system | Overall instrumentation concept; component specifications and conceptual designs; instrumentation cost estimate; CFS requirements; Chapter for EDR
51 | 1.11 |  | Controls and LLRF | [14 empty] | Design the control and LLRF system | Overall control system and LLRF concept; component specifications and conceptual designs; cost estimate; CFS requirements; Chapter for EDR
52 | 1.12 |  | Installation and Supports | [14 empty] | Design the support system, installation procedures | Support conceptual design; installation plan; logistics plan (storage, transport); underground transport concept; Cost estimate; installation chedule; CFS requirements; Chapter for EDR
53 | 1.12.1 |  |  | Installation
54 | 1.12.2 |  |  | Supports and girders
55 | 1.13 |  | Survey and Alignment | [15 empty] | Survey and alignment conceptual design; survey concept; Cost estimate; Survey schedule; CFS requirements; Chapter for EDR
56 | 2 | SRF Technology | [15 empty] | Design and prototype the SRF and HLRF components and subsystems | Key performance figures; design of SRF and HLRF components and systems; input to cost estimation; CFS requirements; Prototype modules; EDR volume "SRF technology"
57 | 2.1 |  | ML and SRF system design (overall management) | [14 empty] | Design complete RF units and cryo strings (for Main Linac, Bunch Compressors and 5GeV boosters in Sources) | Layout of RF units and cryo strings; CFS requirements; Chapter for EDR
58 | 2.2 |  | WP01: Cavity production (Incl. ML DR, & others) | [14 empty] | Demonstrate cavity production readiness | Final cavity design; final surface treatment recipe; testing recipe; cost estimate; performance specification; 120 prototype cavities; Chapter for EDR
59 | 2.2.1 |  |  | SC material | [13 empty] | Define SC material standard | Final material definition; material for 120 prototype cavities
baseline/cost-down material to be decided (before TPP?)
60 | 2.2.2 |  |  | Cavity production/surface-process | [13 empty] | Design cavity
baseline/cost-down surface-process to be decided (before TPP?)
high pressure gas safety regulation
61 | 2.2.3 |  |  | HOM coupler (measurement and tuning?) | [13 empty] | Design HOM coupler / end groups
62 | 2.2.4 |  |  | Helium tank and magnetic shield | [13 empty] | Design helium tank and magnetic shield | Final material definition; material for 120 prototype cavities
|  |  |  | tuner design | [13 empty] | Design tuner
Vertical Test + Success Yield Verification
Infra-structure and Test Facilities: JP
63 | 2.3 |  | WP02: Cryomodule transfer | [14 empty] | Demonstrate cryomodule production readiness | Final cryomodule design; transportation plan; standards for cryomodule production and operation permit; plug compatibility interface soecification; cost estimate; 6 prototype cryomodules; Chapter for EDR
64 | 2.3.1 |  |  | CM Horizontal Test + Degradation Mitigation (before and after transport) | [13 empty] | Provide test facilities | Test capabilities for cavities and cryomodules in all three regions
CM Transport (categorized into 4 items as follows)
Transport design
Mock-up CM transport twice
Global transport
Returning transport
65 | 2.3.2 |  |  | Tuners | [13 empty] | Design tuners | Final tuner design; cost estimate; 60 prototype tuners
66 | 2.3.3 |  |  | Couplers | [13 empty] | Design couplers | Final coupler design; cost estimate; 60 prototype couplers
67 | 2.3.4 |  |  | Quad/BPM Package | [13 empty] | Design cryomodule quad/BPM/corrector packages | Final quad/BPM oackage design; cost estimate; 6 prototype packages
68 | 2.3.5 |  |  | Cold mass and V. Vessel (CM design/fabrication/assembly + Inter-connect) | [13 empty] | Design cryomodule cold mass
high pressure gas safety regulation
Hub-Lab, CM H. Test Facilities, coupler process (Infra: JP)
69 | 2.4 |  | WP03: Crab cavity | [14 empty] | Design crab cavity system | Final crab cavity design; cost estimate; Chapter for EDR
CC design including coupler, tuner etc.
CC model and prototype production
Vertical test including hamonized operation
CC-CM design
WP3: CC Infra-structure (TBC))
70 | 2.5 |  | Interconnects (--> to be included in WP02) | [14 empty] | Design cryomodule interconnects | Cryomodule interconnect design; cost estimate; Chaper for EDR
71 | 2.6 |  | HLRF (Klystrons+Modulator+PDS) | [14 empty] | Design klystrons | Final klystron, modulator, PDS design / specs; cost estimate
72 | 2.7 |  | Modulators (merged to HLRF) | [14 empty] | Design modulators | Final modulator design / specs; cost estimate
73 | 2.8 |  | Power Distribution System (Merged to HLRF) | [14 empty] | Design RF power distribution system | Final power distribution system design / specs; cost estimate; 6 prototype LPDS system
| 2.9 |  | Cryogenics | [14 empty] | Design cryogenic system | Cryogenic system design; cost estimate
75 | 2.10 |  | Mass production (--> to be included in WP01) | [14 empty] | Qualify vendors for mass production | Set of qualified vendors
76 | 3 | Conventional Facilities and Siting
77 | 3.1 |  | Civil Engineering | [14 empty] | Prepare designs ready for CFT of all tunnels, caverns, surface buildings and surface areas | Complete documentation for CFT
78 | 3.2 |  | Electrical Power | [14 empty] | Design electrical power network, from power grid to power outlets | Complete documentation for CFT
79 | 3.3 |  | Water Cooling | [14 empty] | Design water cooling system | Complete documentation for CFT
80 | 3.4 |  | Heating, Ventilation, Air Conditioning | [14 empty] | Design HVAC system | Complete documentation for CFT
81 | 3.5 |  | Site Activation | [14 empty] | Provide site for construction project, ready for ground breaking, including road access, electricity, and water for construction sites, Prepare plan for site infrastructure during construction and operation project (road, railsway and sea access, water, electricity)
82 | 4 | Project Management & Legal Affairs | [15 empty] | Manage the Prelab activities and prepare project management of the construction project. | Management plans and technical solutions for all Systems Engineering and Quality Management processes; Project Implementation Plan
83 | 4.1 |  | Project Management | [14 empty] | Manage the Prelab activities (including preparation of EDRs) and prepare project management of the construction project. | Construction project management plan; Construction project WBS
84 | 4.2 |  | Cost Estimation | [14 empty] | Prepare the cost estimate (cost book) for the construction project | Construction project cost estimate (including HR); cost book; Construction project cost management plan
85 | 4.3 |  | Scheduling | [14 empty] | Prepare a schedule for the construction project | Construction project schedule
86 | 4.4 |  | Project Risk Management | [14 empty] | Manage project risks during the Prelab phase and prepare project risk management for the construction project (in particular measures to handle schedule and cost risks for the central lab and in-kind contributions) | Prelab risk register; Risk management plan; Periodical risk assessments
87 | 4.5 |  | Procurement | [14 empty] | Prepare central procurement procedures for the construction project (i.e. international CFT for SRF equipment) | Procurement plan and directives
88 | 4.6 |  | Logistics | [14 empty] | Prepare logistics plan (transport and storage) for construction project, in Japan and overseas | ,Construction project logistics concept"
89 | 4.7 |  | Human Ressources | [14 empty] | Manage HR during Prelab phase and prepare HR for construction project | Conatruction project hiring plan
90 | 4.8 |  | Legal Affairs | [14 empty] | Prepare MoUs, IKC agreements for construction project, prepare legal structure of central lab? | MoUs; IKC agreements; import permits; planning permits; site acquisition
91 | 5 | Systems Engineering & Quality Management | [15 empty] | Provide Systems Engineering and Quality Management (central and in regional centres) during Prelab phase and prepare Systems Engineering and Quality Management plans with technical solutions for the construction project | ,Management plans and technical solutions for all Systems Engineering and Quality Management processes; Systems Engineering Management Plan"
92 | 5.1 |  | Change Management | [14 empty] | Perform change management during Prelab phase and prepare change management plan for construction project | Prelab and construction project change management plan
93 | 5.2 |  | Requirements Management | [14 empty] | Perform requirements management during Prelab phase and prepare requirements management plan and technical solution for construction project | Requirements database; requirements management plan; requirements database tool
94 | 5.3 |  | Configuration Management | [14 empty] | Develop PBS and prepare configuration management (inclkuding technical solution) for construction project | Construction project PBS (product breakdown structure); Construction project configuration management plan; Configuration database system
95 | 5.4 |  | Interface management | [14 empty] | Prepare interface documentation | Interface definition documents
96 | 5.5 |  | Technical Documentation | [14 empty] | Manage technical design documentation during prelab phase and prepare technical documentation for construction phase (plan and technical implementation) | Technical design documentation (TDD); Documentation plan; Document handling system
97 | 5.6 |  | CAD Modelling | [14 empty] | CAD modelling | CAD integration model; CAD model database; CAD modellling methods and standards
98 | 5.7 |  | Technical Risk Management | [14 empty] | Perform technical risk management during Prelab phase and prepare technical risk management plan for construction project | Technical risk analysis; Technical risk management plan; Periodical risk assessments
99 | 5.8 |  | Quality Management | [14 empty] | Prepare quality management plan for construction project | Construction project quality management plan
100 | 5.9 |  | Standards and Conformance | [14 empty] | Prepare and manage standards for the construction project (design rules, material qualities, applicable international norms and standards) | Register of applicable norms and standards
101 | 6 | Safety and Environment | [16 empty] | Safety and Environment Management Plan
102 | 6.1 |  | Safety and Health Protection | [14 empty] | Define and enforce safety and health protection measures for population and workers throughout the project | Safety and health protection policies and guidelines; requirements for subsystems and components; fire protection plan; evacuation and rescue plan
103 | 6.2 |  | Environmental Protection | [14 empty] | Define and enforce environmental protection measures throughout the project | Environmental protection policies and guidelines; requirements for subsystems and components
104 | 6.3 |  | Radiation Protection | [14 empty] | Define and enforce radiation protection measures throughout the project | Radiation protection plan; standards / requirements for components
105 | 6.4 |  | Earthquake and Disaster Protection | [14 empty] | Define scenarios of natural disasters that the facility needs to survive; provide requirements and guidelines | Earthquake and natural disaster scenarios; Design rules, guidelines, specifications, requirements
106 | 7 | Outreach & Public Relations | [15 empty] | Inform the public about the ILC project | Project web site; brochures; press releases