## WBS Ver.0.3a
Code | Title |  |  |  |  | Scoping statement | Deliverables
1 | Oversight: Accelerator and Technical Design Integration |  |  |  |  | Overview of the ILC accelerator and technical design Integration as a whole | Key performance figures; integrated lattice; overall machine layout; input to cost estimate; CFS requirements; EDR volume "accelerator design"
2.1 |  | A1: Sources
|  |  | T0: System Design |  |  | Design the electron and positron source systems, with prototypes of critical items | Sources system design
Source system lattices
Sources performance specification
component requirements and specifications
Component counts
Design and costs for sources specific components
Prototypes of critical items
Chapter for EDR
Sum of all works other than EDR
2.1a |  | A1a: e- source
2.1a.1 | #REF! |  | T0: System Design
2.1a.1.1 |  |  |  | Optics |  | Design the electron source system from gun to DR injection | Electron source system lattice
2.1a.1.2 |  |  |  | Beam dynamics and tuning |  | Evaluate the beam dynamics of the ILC accelerator | ES system design
2.1a.1.3 |  |  |  | Availability and operations |  | Determine the expected availability of the accelerator | Spin rotator design (icluding possibilities other than SC solenoid such as Wien filter)
2.1a.1.4 |  |  |  | Commissioning |  | Plan the comissioning of the accelerator | ES performance specification
component requirements and specifications
Component counts
Cost estimate for ES specific components
Chapter for EDR
2.1a.2 | #REF! |  | T1: Area Specific
2.1a.2.1a |  |  |  | WP04: Electron source |  | ES gun design | ES gun design
350kV photo-gun
[6 empty] | drive laser design | drive laser design
prototype laser
[6 empty] | cathode design | cathode design
commercialize photocathode production
2.1a.3 | 0 | [5 empty] | Mott polarimeter (to be included in WP4)
|  |  |  | 76 MeV linac (SHB, L-band) |  | Check the design change since TDR
|  |  | T2: Hub/Infra-Structure | N/A
2.1a.4 | #REF! |  | T3a: Accelerating Strcture: SRF
|  |  |  | SRF for 5 GeV SC linac |  | Check the design change since TDR
2.1a.5 | 0 |  | T3b: Accelerating Strcture: NRF
none
2.1a.6 | #REF! |  | T4: RF Power (HLRF)
2.1a.6.1 |  |  |  | HLRF for 5 GeV SC linac |  | Check the design change since TDR
2.1a.7 | #REF! |  | T5: Cryogenics
|  |  |  | Cryogenics for 5 GeV SC linac |  | Check the design change since TDR
2.1a.8 | #REF! |  | T6a: Magnet and PS (SC) |  |  |  | Conceptual magnet designs and specifications; magnet and power supply cost estimates (unit and overall costs); power supply concept; cabling design; CFS reqiorements; Chapter for EDR
2.1a.8.1 |  |  |  | SC quad for 5 GeV SC linac |  | Design all superconducting magnets
2.1a.8.2 |  |  |  | spin rotator solenoid (25Tm) |  | Design power supply system
2.1a.9 | #REF! |  | T6b: Magnet and PS (NC) |  |  | Design NC/PM magnets, kickers and power supplies | Conceptual magnet designs and specifications; magnet and power supply cost estimates (unit and overall costs); power supply concept; cabling design; CFS reqiorements; Chapter for EDR
2.1a.9.1 |  |  |  | Beam transport magnets from 5GeV linac to DR |  | Design all normal conducting magnets
2.1a.10 | #REF! | from Source(x1/2) | T7: Vacuum |  |  | Design vacuum system | Conceptual layout of all warm vacuum sections; component specifications, counts and cost estimates; CFS requirements; Chapter for EDR
|  |  |  | Vacuum for 5 GeV SC linac |  | Check the design change since TDR
|  |  |  | Vacuum for beam transport from 5GeV linac to DR |  | Check the design change since TDR
2.1a.11 | #REF! | from Okugi (x 1/2), excluding WP18 (=4) | T8: Collimator and Beam Dump |  |  |  | Engineering layout of main dumps; conceptual layout of other dumps and collimators; Specifications; Cost estimates; CFS requirements; Chapter for EDR
|  |  |  | 60kW beam dump at 5GeV |  | Dump design
2.1a.12 | #REF! | from Yamamoto (x 1/2) | T9: Beam Instrumentation |  |  |  | Overall instrumentation concept; component specifications and conceptual designs; instrumentation cost estimate; CFS requirements; Chapter for EDR
|  |  |  | BPM for 5 GeV SC linac |  | Check the design change since TDR
|  |  |  | BPM for beam transport from 5GeV linac to DR |  | Check the design change since TDR
2.1a.13 | #REF! | from Yamamoto (x 1/2) | T10: Low Level RF and Control |  |  |  | Overall control system and LLRF concept; component specifications and conceptual designs; cost estimate; CFS requirements; Chapter for EDR
|  |  |  | LLRF for 5 GeV SC linac |  | Check the design change since TDR
2.1a.14 | #REF! | from Yamamoto (x 1/2) | T11: Installation
2.1a.15 | #REF! | from Yamamoto (x 1/2) | T12: Survey and Aalignment
2.1a.16 |  |  | T13: Common (1)
2.1a.17 |  |  | T14: Common (2)
2.1a.18 |  |  | T15: Civil Engineering and Conventional Facilities
2.1a.19 |  |  | T16: Administration and Management
2.1b |  | A1b: Undulator e+
2.1b.1 |  |  | Helical Undulator section
2.1b.1.1 | #REF! |  |  | T0: System Design
2.1b.1.1.1 |  |  |  |  | Optics | Design the undulator positron source system | Undulator positron source system lattice; UPS system design; UPS performance specification; Chapter for EDR
2.1b.1.1.2 |  |  |  |  | Beam dynamics and tuning | Evaluate the beam dynamics of the ILC accelerator | Start-to-end simulations
2.1b.1.1.3 |  |  |  |  | Availability and operations | Determine the expected availability of the accelerator | Availability estimate; operations and maintenance concept; availability specifications for subsystems and components
2.1b.1.1.4 |  |  |  |  | Commissioning | Plan the comissioning of the accelerator | Comissioning concept
2.1b.1.2 | #REF! |  |  | T1: Area Specific
2.1b.1.2.2 |  |  |  |  | WP05: Undulator | Simulation studies with field errors and misalignment | heating of undulators and masks, error effects, orbit correction method, etc.
[6 empty] | Undulator parameter optimization | Otimized parameters such as K, pitch, aperture, etc.
2.1b.1.3 |  |  |  | T2: Hub/Infra-Structure | N/A
2.1b.1.4 | #REF! |  |  | T3a: Accelerating Strcture: SRF
2.1b.1.5 | #REF! |  |  | T3b: Accelerating Strcture: NRF
2.1b.1.6 | #REF! |  |  | T4: RF Power (HLRF)
2.1b.1.7 | #REF! |  |  | T5: Cryogenics
Cryogenics for helical undulator
2.1b.1.8 | #REF! |  |  | T6a: Magnet and PS (SC)
2.1b.1.8.1 |  |  |  |  | SC helical undulator | Design of helical undulator based on WP05 | Drawing of helical undulator
2.1b.1.9 | #REF! |  |  | T6b: Magnet and PS (NC)
Quads in undulator section
2.1b.1.10 | #REF! | from Source(x1/4) |  | T7: Vacuum |  | Design vacuum system | Conceptual layout of all warm vacuum sections; component specifications, counts and cost estimates; CFS requirements; Chapter for EDR
Vacuum in undulator section
2.1b.1.11 | #REF! | from Okugi (x 1/4), excluding WP18 (=4) |  | T8: Collimator and Beam Dump
[5 empty] | Masks in undulator section | Mask design based on WP05
2.1b.1.12 | #REF! | from Okugi (x 1/4) |  | T9: Beam Instrumentation
BPM in undulator section
2.1b.1.13 | #REF! | from Okugi (x 1/4) |  | T10: Low Level RF and Control |  | Design the control and LLRF system | Overall control system and LLRF concept; component specifications and conceptual designs; cost estimate; CFS requirements; Chapter for EDR
2.1b.1.14 | #REF! | from Okugi (x 1/4) |  | T11: Installation
2.1b.1.15 | #REF! | from Okugi (x 1/4) |  | T12: Survey and Aalignment
2.1b.1.16 |  |  |  | T13: Common (1)
2.1b.1.17 |  |  |  | T14: Common (2)
2.1b.1.18 |  |  |  | T15: Civil Engineering and Conventional Facilities
2.1b.1.19 |  |  |  | T16: Administration and Management
2.1b.2 |  |  | 5GeV Positron Booster (incl. transport line to DR)
2.1b.2.1 | #REF! |  |  | T0: System Design
2.1b.2.1.1 |  |  |  |  | Optics | Design the undulator positron source system | Undulator positron source system lattice; UPS system design; UPS performance specification; Chapter for EDR
2.1b.2.1.2 |  |  |  |  | Beam dynamics and tuning | Evaluate the beam dynamics of the ILC accelerator | Start-to-end simulations
2.1b.2.1.3 |  |  |  |  | Availability and operations | Determine the expected availability of the accelerator | Availability estimate; operations and maintenance concept; availability specifications for subsystems and components
2.1b.2.1.4 |  |  |  |  | Commissioning | Plan the comissioning of the accelerator | Comissioning concept
2.1b.2.2 | #REF! |  |  | T1: Area Specific
2.1b.2.2.3 |  |  |  |  | WP06: Rotating target
[6 empty] | Design finalization of the rotating target | Final target design and fabrication of partial model
[6 empty] | Study of magnetic bearings | performance test of bearings
[6 empty] | Fabrication of the full target model | Reduced unit of the full wheel
2.1b.2.2.4 |  |  |  |  | WP07: Magnetic focussing
[6 empty] | Design the pulsed solenoid | Build the power source and test the prototype
[6 empty] | Study of other OMDs | positron yield calculation
[6 empty] | Integrated design of OMD and wheel | Fully assembled wheel with OMD
2.1b.2.2.8 |  |  |  |  | WP11: Target replacement
2.1b.2.3 |  |  |  | T2: Hub/Infra-Structure | N/A
2.1b.2.4 | #REF! |  |  | T3a: Accelerating Strcture: SRF |  | Design and prototype the SRF components and subsystems | Key performance figures; design of SRF components and systems; input to cost estimation; CFS requirements; Prototype modules; EDR volume "SRF technology"
SRF for SC positron booster from 400MeV to 5GeV
2.1b.2.5 | #REF! |  |  | T3b: Accelerating Strcture: NRF |  | Design and prototype the NRF components and subsystems | Key performance figures; design of NRF components and systems; input to cost estimation; CFS requirements; Prototype modules; EDR
NRF for NC positron linac up to 400MeV
2.1b.2.6 | #REF! |  |  | T4: RF Power (HLRF)
2.1b.2.6.1 |  |  |  |  | HLRF for NC positron linac up to 400MeV
2.1b.2.6.2 |  |  |  |  | HLRF for SC positron booster from 400MeV to 5GeV
2.1b.2.7 | #REF! |  |  | T5: Cryogenics
Cryogenics for SC positron booster from 400MeV to 5GeV
2.1b.2.8 | #REF! |  |  | T6a: Magnet and PS (SC)
2.1b.2.8.1
2.1b.2.8.2
2.1b.2.9 | #REF! |  |  | T6b: Magnet and PS (NC)
2.1b.2.9.1 |  |  |  |  | SC quad for SC positron booster from 400MeV to 5GeV
2.1b.2.9.2 |  |  |  |  | SC solenoid for spin rotator (2 sets)
2.1b.2.10 | #REF! | from Source(x1/4) |  | T7: Vacuum
Vacuum for NC positron linac up to 400MeV
Vacuum for SC positron booster from 400MeV to 5GeV
2.1b.2.11 | #REF! | from Okugi (x 1/4), excluding WP18 (=4) |  | T8: Collimator and Beam Dump |  | Design all beam dumps | Engineering layout of main dumps; conceptual layout of other dumps and collimators; Specifications; Cost estimates; CFS requirements; Chapter for EDR
2.1b.2.11.1 | #REF! |  |  |  | WP18: Photon dump | Design photon dump of undulator positron source | Photon dump engineering design
5GeV positron dump (60kW)
2.1b.2.12 | #REF! | from Okugi (x 1/4) |  | T9: Beam Instrumentation |  | Design instrumentation system | Overall instrumentation concept; component specifications and conceptual designs; instrumentation cost estimate; CFS requirements; Chapter for EDR
BPM for NC positron linac up to 400MeV
BPM for SC positron booster from 400MeV to 5GeV
2.1b.2.13 | #REF! | from Okugi (x 1/4) |  | T10: Low Level RF and Control |  | Design the control and LLRF system | Overall control system and LLRF concept; component specifications and conceptual designs; cost estimate; CFS requirements; Chapter for EDR
LLRFfor SC positron booster from 400MeV to 5GeV
2.1b.2.14 | #REF! | from Okugi (x 1/4) |  | T11: Installation
2.1b.2.15 | #REF! | from Okugi (x 1/4) |  | T12: Survey and Aalignment
2.1b.2.16 |  |  |  | T13: Common (1)
2.1b.2.17 |  |  |  | T14: Common (2)
2.1b.2.18 |  |  |  | T15: Civil Engineering and Conventional Facilities
2.1b.2.19 |  |  |  | T16: Administration and Management
2.1c |  | A1c: e-Driven e+
2.1c.1 |  |  | 3GeV Electron Driver
2.1c.1.1 | #REF! |  |  | T0: System Design
2.1c.1.1.1 |  |  |  |  | Optics | Design the e-driven positron source system | E-driven positron source system lattice; Chapter for EDR
2.1c.1.1.2 |  |  |  |  | Beam dynamics and tuning | Evaluate the beam dynamics of the ILC accelerator
2.1c.1.1.3 |  |  |  |  | Availability and operations | Determine the expected availability of the accelerator | Availability estimate; operations and maintenance concept; availability specifications for subsystems and components
2.1c.1.1.4 |  |  |  |  | Commissioning | Plan the comissioning of the accelerator | Comissioning concept
2.1c.1.2 | #REF! |  |  | T1: Area Specific
[5 empty] | RF electron gun cavity | RF electron gun, WG, PU
[5 empty] | Gun solenoid magnet | solenoid magnet, girder, PS
[5 empty] | Cathode system | cathode system, transfer system
[5 empty] | Cathode drive laser | Laser system, synchronization and cotnrol
2.1c.1.3 |  |  |  | T2: Hub/Infra-Structure | N/A
2.1c.1.4 | 0 |  |  | T3a: Accelerating Strcture: SRF |  | N/A
2.1c.1.5 | #REF! |  |  | T3b: Accelerating Strcture: NRF
[5 empty] | 3GeV S-band TW 3m accelerator | TW accelerator
2.1c.1.6 | #REF! |  |  | T4: RF Power (HLRF)
[5 empty] | S-band power unit | S-band PU
2.1c.1.7 | 0 |  |  | T5: Cryogenics |  | N/A
2.1c.1.8 | 0 |  |  | T6a: Magnet and PS (SC) |  | N/A
2.1c.1.8.1 |  |  |  |  | Superconducting magnets | N/A
2.1c.1.8.2 |  |  |  |  | Magnet power supplies | N/A
2.1c.1.9 | #REF! |  |  | T6b: Magnet and PS (NC) |  | Design NC/PM magnets for 3GeV driver, 5GeV booster | Conceptual magnet designs and specifications; magnet and power supply cost estimates (unit and overall costs); power supply concept; cabling design; CFS reqiorements; Chapter for EDR
Quarupole magnet
2.1c.1.10 | #REF! | from Source(x1/4) |  | T7: Vacuum |  | Design vacuum components for 3GeV driver, 5GeV booster | Conceptual layout of all warm vacuum sections; component specifications, counts and cost estimates; CFS requirements; Chapter for EDR
2.1c.1.11 | #REF! | from Okugi (x1/4), excluding WP18 (=4) |  | T8: Collimator and Beam Dump |  | Design all beam dumps | Engineering layout of main dumps; conceptual layout of other dumps and collimators; Specifications; Cost estimates; CFS requirements; Chapter for EDR
[5 empty] | Tune up dump at Injector | bending magnet, beam chamber, dump
[5 empty] | Tune up dump at the driver end | dump design
2.1c.1.12 | #REF! | from Okugi (x1/4) |  | T9: Beam Instrumentation |  | Design instrumentation system for 3GeV driver, 5GeV booster | Overall instrumentation concept; component specifications and conceptual designs; instrumentation cost estimate; CFS requirements; Chapter for EDR
[5 empty] | BPM | BPM, readout electronics
[5 empty] | Screen monitor | Screen monitor, controller, camera
[5 empty] | OTR monitor | OTR monitor
2.1c.1.13 | #REF! | from Okugi (x1/4) |  | T10: Low Level RF and Control |  | Design the control and LLRF system for 3GeV driver, 5GeV booster | Overall control system and LLRF concept; component specifications and conceptual designs; cost estimate; CFS requirements; Chapter for EDR
2.1c.1.14 | #REF! | from Okugi (x1/4) |  | T11: Installation
2.1c.1.15 | #REF! | from Okugi (x1/4) |  | T12: Survey and Aalignment
2.1c.1.16 |  |  |  | T13: Common (1)
2.1c.1.17 |  |  |  | T14: Common (2)
2.1c.1.18 |  |  |  | T15: Civil Engineering and Conventional Facilities
2.1c.1.19 |  |  |  | T16: Administration and Management
2.1c.2 |  |  | 5GeV Positron Booster
2.1c.2.1 | #REF! |  |  | T0: System Design
2.1c.2.1.1 |  |  |  |  | Optics | Design the e-driven positron source system | E-driven positron source system lattice; Chapter for EDR
2.1c.2.1.2 |  |  |  |  | Beam dynamics and tuning | Evaluate the beam dynamics of the ILC accelerator
2.1c.2.1.3 |  |  |  |  | Availability and operations | Determine the expected availability of the accelerator | Availability estimate; operations and maintenance concept; availability specifications for subsystems and components
2.1c.2.1.4 |  |  |  |  | Commissioning | Plan the comissioning of the accelerator | Comissioning concept
2.1c.2.2 | #REF! |  |  | T1: Area Specific
2.1c.2.2.5 |  |  |  |  | WP08: Rotating target (e driven)
[6 empty] | Target stress calculation with FEM | summary of all simulations (heat, stress, etcB)
[6 empty] | Vacuum seal | vacuum seal prototype and vacuum demonstration
[6 empty] | target module | target module prototype, long term operation
Target wheel design
electrical design and control system (done?)
Vacuum design
2.1c.2.2.6 |  |  |  |  | WP09: Magnetic focussing (e driven)
Flux concentrator conductor
[6 empty] | Electrical design | Transmission line design
Electrical connection design
[6 empty] | Flux concentrator system prototyping | fabcication of the FC system and test
powr source (modulator)
Vacuum design
[6 empty] | APS cavity design | RF design
APS cavity prototype
[6 empty] | capture cavity beamloading compensation | loading simulation
[6 empty] | power unit | Power unit design
2.1c.2.2.7 |  |  |  |  | WP10: Capture caviity
APS cavity test with power system
[6 empty] | solenoid prototyping | solenoid magnet
[6 empty] | capture linac prototyping | RF unit porotyping and operation
RF control and netowrk design
BPM
Vacuum design
2.1c.2.3 |  |  |  | T2: Hub/Infra-Structure | N/A
2.1c.2.4 | 0 |  |  | T3a: Accelerating Strcture: SRF |  | N/A
2.1c.2.5 | #REF! |  |  | T3b: Accelerating Strcture: NRF |  | Design for 3GeV driver, 5GeV booster
[5 empty] | 2m L-band TW accelerator | TW accelerators
[5 empty] | 2m S-band TW accelerator | TW accelerators
[5 empty] | L-band 3m TW accelerator (ECS) | accelerator (ECS)s
2.1c.2.6 | #REF! |  |  | T4: RF Power (HLRF)
2.1c.2.6.1 |  |  |  |  | L-band power unit | power units
2.1c.2.6.2 |  |  |  |  | S-band power unit | power units
2.1c.2.7 | 0 |  |  | T5: Cryogenics |  | N/A
2.1c.2.8 | 0 |  |  | T6a: Magnet and PS (SC) |  | N/A
2.1c.2.8.1 |  |  |  |  | Superconducting magnets | N/A
2.1c.2.8.2 |  |  |  |  | Magnet power supplies | N/A
2.1c.2.9 | #REF! |  |  | T6b: Magnet and PS (NC)
2.1c.2.9.1 |  |  |  |  | Solenoid manet surrounding capture cavities
2.1c.2.9.2 |  |  |  |  | Chicane bending magnet | bending magnets
2.1c.2.9.3 |  |  |  |  | Q-magnet | Q-magnets
2.1c.2.10 | #REF! | from Source(x1/4) |  | T7: Vacuum |  | Design vacuum components for 3GeV driver, 5GeV booster | Conceptual layout of all warm vacuum sections; component specifications, counts and cost estimates; CFS requirements; Chapter for EDR
2.1c.2.11 | #REF! | from Okugi (x1/4), excluding WP18 (=4) |  | T8: Collimator and Beam Dump |  | Design all beam dumps | Engineering layout of main dumps; conceptual layout of other dumps and collimators; Specifications; Cost estimates; CFS requirements; Chapter for EDR
[5 empty] | Tune up dump (capture linac) | capture linac
[5 empty] | Tune up dump (booster end) | booster end
2.1c.2.12 | #REF! | from Okugi (x1/4) |  | T9: Beam Instrumentation
[5 empty] | BPM | BPM, readout electronics
2.1c.2.13 | #REF! | from Okugi (x1/4) |  | T10: Low Level RF and Control |  | Design the control and LLRF system for 3GeV driver, 5GeV booster | Overall control system and LLRF concept; component specifications and conceptual designs; cost estimate; CFS requirements; Chapter for EDR
2.1c.2.14 | #REF! | from Okugi (x1/4) |  | T11: Installation
2.1c.2.15 | #REF! | from Okugi (x1/4) |  | T12: Survey and Aalignment
2.1c.2.16 |  |  |  | T13: Common (1)
2.1c.2.17 |  |  |  | T14: Common (2)
2.1c.2.18 |  |  |  | T15: Civil Engineering and Conventional Facilities
2.1c.2.19 |  |  |  | T16: Administration and Management
Common Issue of Positron Source
T1: Area Specific
WP11: Target Maintenance
target region layout
radiation damage evaluation
residual activation after the operation
radiation environment during the operation
target maintenance scenario including accident (mockup test)
[6 empty] | Target module design including structual mechanics | Structual mecahnics analysis
[6 empty] | Target system (Target module, transportation, storage, installation, activation controll) design | Activated air and water control
[6 empty] | Transportation design (Rail, wagon, power, etc) | Transportation system
Storage area
Installation and uninstallation
[6 empty] | Remote seal joint (inflatable seal, etc) | Remote inflatable seal
Safe and secure connector removal and connection
Control radiation exposure of workers
EDR