CALICE SiW ECAL – Beam test preparation
Roman Pöschl
On behalf of the SiW ECAL Groups in CALICE:
        SiW Ecal Meeting – 04/02/2022

---
News and status of prototype
DESY beam test: 7/3/22 – 21/3/22
Proposal: Move beam test to 21/3/22 – 4/4/22
Slot (still) free at DESY
Katja of AHCAL would be available for common running
We would have two more weeks to prepare
Your opinion?
A priori prototype is operational but ...
Running in November with 9.6X0 => Not enough to absorb electron showers
Will exchange 7 2.1mm W plates by 2.8mm W plates and equip 8 layers with 4.2mm W plates
7x0.8+8x1.2X0 = 15.2X0
2.8mm W plates of 20x20cm2 from LLR (+ one 5.6mm W plate)
COBs completed before and after Xmas
Two COBs glued at LPNHE in december
Commissioning ongoing
Report on commissioning at next preparation meeting
One more COB (Slab 28) at IFIC may become available for the beam test
Encapsulated at IFIC
A fourth (encapsulated) one (Slab 32) with 15/16 ASICs back at ICJLab for further debugging
Stack runs currently with two FEV13 included

---
Towards beam test – To do list 4/2/22
Mechanics
2.8mm plates need to be cut to right dimensions
Sent to ATS on Feb. 3Rd, expect back on Feb. 25th
Further news: Positive tests at LLR with water jet cutting, good to know for the future, e.g. for CERN proto
Production of rails (4 for 4.2mm W plates and 7 for 2.8mm W plates)
First set of rails from 3d-printing bent -> To be checked by Alexandre
New aluminum front and side plates under construction at IJCLab workshopm
COBs
Slab 29 and Slab 33 operattional but to be debugged for increased noise in two rows (AVDD) and the noisy ASIC 8 -> Next week
Note in passing that on Slab 28 it is also the Chip 8 that is non-operational
FEV13
Commissioning -> Passports
Operation voltage of stack?
Should be settled while FEV13 are in stack
System
Need to decide which slabs to replace
Need to think about optimal arrangement of slabs

---
Towards beam test – To do list 19/1/22 cont'd
Data acquisition
Integration with AHCAL
Call out for meeting with AHCAL people
Integration with beam telescope -> No priority for March
Data monitoring and DQ checks
Tests for integration with EUDAQ during Adrian's visit to IJCLab (9/2/22 – 18/2/22)
Data management
Data can be buffered on 1 TB local disk and then shipped to cernbox (as last time)
Roman will try to mount disk array onto DAQ computer during October
Several TByte for buffer, maybe useful for local DQ checks
Still open from last TB (shame on me)
Data storage on grid?
What else?

---
DESY Test beam – On site
Unfortunately, the “rule of eight” will still apply at DESY
The teams
Week 7/3/22 – 13/3/22 (21/3/22 – 27/3/22)
Will most likely be an entire Ecal week -> tungsten running
Adrian, Yuichi, Jimmy, Alexandre or Alice + 4 persons from SiW ECAL
Roman around
Week 14/3/22 – 20/3/22 (28/3/22 – 3/4/22)
Combined running -> w/o tungsten
Adrian, Roman, Yuichi (until 30/3/22), Dominique, Jihane (both 26/3/22 – 31/3/22) + two persons for AHCAL (Jiri, Katja)
+ one person from SiW ECAL
First combined tests (26/3/22 – 27/3/22) outside of beam area
Three team members will leave during that week
Have to ask Jiri and Katja whether they can help us with shifts and with dismounting
New survey on availability will be launched today (finally)
Conditions (same as last time)
Participants need have PCR test not older than 48h and be vaccinated (including booster)
Currently only two shifters are allowed in the beam test hall, more during setup
Propose to run two shifts per day 8h-16h, 16h-0h. night shifts should be taken into account to account for time loss
during setup of common running
Coordination (proposal)
Overall responsibility: Roman (1st Week), ? (2nd week)
Run coordination: Adrian (at least first week, depends also on requirements from common running)

---
DESY Test beam – Run plan
1st week
Setup including setup of/with AHCAL (count two days)
Quick commissioning w/o tungsten
DAQ Integration with AHCAL
Further commissioning w/o tungsten and check of common data taking
Hickups may lead to interruptions delays of program
2nd week tungsten program
FEV13 tests?
Several energy points with high statistics
Different positions, e.g. Scan over wafer boundaries

---
Backup