CALICE SiW ECAL – Beam test preparation
Roman Pöschl
On behalf of the SiW ECAL Groups in CALICE:
        SiW Ecal Meeting – 22/02/2022

---
News and status of prototype
DESY beam test: 21/3/22 – 4/4/22
A priori prototype is operational but ...
Running in November with 9.6X0 => Not enough to absorb electron showers
Will exchange 7 2.1mm W plates by 2.8mm W plates and equip 8 layers with 4.2mm W plates
7x0.8+8x1.2X0 = 15.2X0
2.8mm W plates of 20x20cm2 from LLR (+ one 5.6mm W plate)
COBs completed before and after Xmas
Two COBs glued at LPNHE in december
Commissioning ongoing
Report on commissioning at next preparation meeting
One more COB (Slab 28) at IFIC may become available for the beam test
Encapsulated at IFIC
A fourth (encapsulated) one (Slab 32) with 15/16 ASICs back at ICJLab for further debugging
Stack runs currently with two FEV13 included

---
Towards beam test – To do list 22/2/22
Mechanics
2.8mm plates need to be cut to right dimensions
Sent to ATS on Feb. 3Rd, arrival at QTS on Feb. 4th, expect back on Feb. 25th
Plates cut at LLR
Production of rails (4 for 4.2mm W plates and 7 for 2.8mm W plates)
First set of rails from 3d-printing bent -> To be checked by Alexandre
New aluminum front and side plates under construction at IJCLab workshop
COBs
Slab 29 and Slab 33 operattional but to be debugged for increased noise in two rows (AVDD) and the noisy ASIC 8 -> Next week
Note in passing that on Slab 28 (check ID) it is also the Chip 8 that is non-operational
FEV13
Commissioning -> Passports
Operation voltage of stack?
Should be settled while FEV13 are in stack
System
It seems that during novmber running we have lost HV on at least one layer
Dominique expressed idea on how to monitor HV with SL Board, realistic for DESY?
N.B.: New HV cables ordered last week on timr for DESY
MIP at 50 ADC counts,
A mystery, only reasonable explanation is that we've worked with 0.8pF (intead of 1.2pF) feedback capa
in the past (i.e. < 2019)

---
Towards beam test – To do list 22/2/22 cont'd
Data acquisition
Integration with AHCAL
Meeting with AHCAL people
Tests integration with EUDAQ successful (Adrian and Jihane)
Integration with beam telescope -> No priority for March
Data monitoring and DQ checks
EUDAQ see above
New features implemented by Jihane
ADC spectra
Hit maps
xy and yz (=longitudinal profile)
New software now on DAQ PC
Data management
Data can be buffered on 1 TB local disk and then shipped to cernbox (as last time)
Roman will try to mount disk array onto DAQ computer during October
Several TByte for buffer, maybe useful for local DQ checks
Still open from last TB (shame on me)
Data storage on grid?
What else?

---
DESY Test beam – On site
Unfortunately, the “rule of eight” will still apply at DESY
Germany is opening up (all restrictions for e.g. Sports events will be lifted on March 20th) but
so far no sign of consequences at DESY
The teams
Week 21/3/22 – 27/3/22
Will be an entire Ecal week -> tungsten running
Roman, Vincent, Adrian (from 22/3/22) , Yuichi, Jimmy (until 23/3/22), Alice (until 23/3/22), Fabrizio, Jonas
Alice needs training
Week 28/3/22 – 3/4/22
Combined running -> w/o tungsten
Adrian, Roman, Vincent, Dominique, Jihane (both 26/3/22 – 31/3/22), Stephane + two persons for AHCAL (Jiri, Katja)
Yuichi on call but will be around the entire time
First combined tests (26/3/22 – 27/3/22) outside of beam area
Have to ask Jiri and Katja whether they can help us with shifts and with dismounting
Conditions (same as last time)
Participants need have PCR test not older than 48h and be vaccinated (including booster)
Currently only two shifters are allowed in the beam test hall, more during setup
Propose to run two shifts per day 8h-16h, 16h-0h. night shifts should be taken into account to account for time loss
during setup of common running
Coordination (proposal)
Overall responsibility: Roman
Run coordination: Adrian (at least first week, depends also on requirements from common running)

---
DESY Test beam – Run plan
1st week tungsten program
FEV13 tests?
Several energy points with high statistics
Different positions, e.g. Scan over wafer boundaries
2nd week
Setup including setup of/with AHCAL (count two days)
Quick commissioning w/o tungsten
DAQ Integration with AHCAL
Further commissioning w/o tungsten and check of common data taking
Hickups may lead to interruptions delays of program

---
Backup