CALICE SiW ECAL – Beam test preparation
Roman Pöschl
On behalf of the SiW ECAL Groups in CALICE:
        SiW Ecal Meeting – 03/03/2022

---
News and status of prototype
DESY beam test: 21/3/22 – 4/2/22
A priori prototype is operational but ...
Running in November with 9.6X0 => Not enough to absorb electron showers
Will exchange 7 2.1mm W plates by 2.8mm W plates and equip 8 layers with 4.2mm W plates
7x0.8+8x1.2X0 = 15.2X0
2.8mm W plates of 20x20cm2 from LLR (+ one 5.6mm W plate)
COBs completed before and after Xmas
Two COBs glued at LPNHE in december
Commissioning ongoing
Report on commissioning at next preparation meeting
One more COB (Slab 28) at IFIC may become available for the beam test
Encapsulated at IFIC
A fourth (encapsulated) one (Slab 32) with 15/16 ASICs back at ICJLab for further debugging
Stack runs currently with two FEV13 included

---
Towards beam test – To do list 3/3/22
Mechanics
2.8mm plates cut to right dimensions
All plates are at IJCLab (5 from LLR + 7 from ATS)
Production of rails (4 for 4.2mm W plates and 7 for 2.8mm W plates)
All rails are available
COBs
Slab 29 and Slab 33 operational but to be debugged for increased noise in two rows (AVDD) and the noisy ASIC 8 -> Next week
Note in passing that on Slab 28 it is also the Chip 8 that is non-operational
Passports for Slab 29 and 33 created by Yuichi)
FEV13
Now labelled Slabs 34 and 35, Passports created by Yuichi
Operation voltage of stack? Currently all slabs are operated with 150 V
Requires further observation
System
New HV cables mounted last week
HV monitoring with SL Boards can/will be put in place after beam test
Stack assembled with configuration foreseen for DESY (w/o W), see attached excel table
Commissioning started
Remember everything has to be done from scratch due to lower MIP value (some assumptions in commissioning
procedure are not valid anymore
Assembly test with W foreseen for next Monday (7/3/22)

---
Towards beam test – To do list 3/3/22 cont'd
Data acquisition
Integration with AHCAL
Meeting with AHCAL people
Detector operation can be based on EUDAQ client
Server on DAQ PC
Client emulated on DAQ PC, will later run on Linux machine
Possibility for a script based commissioning?
Need to switch to binary format of data
Integration with beam telescope -> No priority for March
Data monitoring and DQ checks
New features implemented by Jihane
ADC spectra
Hit maps
xy and yz (=longitudinal profile)
Automatic recognition of Slab type
Data management
Data can be buffered on 1 TB local disk and then shipped to cernbox (as last time)
Roman will try to mount disk array onto DAQ computer during October
Several TByte for buffer, maybe useful for local DQ checks
Still open from last TB (shame on me)
Data storage on grid?
We are are close to be good to go (packing on 17/3/22 afternoon)
Have to make use of two remaining weeks for exercising assembly with W, get familiar with
new tools and features and understanding of detector performance

---
DESY Test beam – On site
Unfortunately, the “rule of eight” will still apply at DESY
Germany is opening up (all restrictions for e.g. Sports events will be lifted on March 20th) but
so far no sign of consequences at DESY
The teams
Week 21/3/22 – 27/3/22
Will be an entire Ecal week -> tungsten running
Roman, Vincent, Adrian (from 22/3/22) , Yuichi, Jimmy (until 23/3/22), Alice (until 23/3/22), Fabrizio, Jonas
Alice needs training
Week 28/3/22 – 3/4/22
Combined running -> w/o tungsten
Adrian, Roman, Vincent, Dominique, Jihane (both 26/3/22 – 31/3/22), Stephane + two persons for AHCAL (Jiri, Katja)
Yuichi on call but will be around the entire time
First combined tests (26/3/22 – 27/3/22) outside of beam area
Have to ask Jiri and Katja whether they can help us with shifts and with dismounting
Conditions (same as last time)
Participants need have PCR test not older than 48h and be vaccinated (including booster)
Currently only two shifters are allowed in the beam test hall, more during setup
Propose to run two shifts per day 8h-16h, 16h-0h. night shifts should be taken into account to account for time loss
during setup of common running
Coordination (proposal)
Overall responsibility: Roman
Run coordination: Adrian (at least first week, depends also on requirements from common running)

---
DESY Test beam – Run plan
1st week tungsten program
FEV13 tests?
Several energy points with high statistics
Different positions, e.g. Scan over wafer boundaries
2nd week
Setup including setup of/with AHCAL (count two days)
Quick commissioning w/o tungsten
DAQ Integration with AHCAL
Further commissioning w/o tungsten and check of common data taking
Hickups may lead to interruptions delays of program

---
Backup