CALICE SiW ECAL – Beam test preparation
Roman Pöschl
On behalf of the SiW ECAL Groups in CALICE:
        SiW Ecal Meeting – 15/03/2022

---
News and status of prototype
DESY beam test: 21/3/22 – 4/2/22
A priori prototype is operational but ...
Running in November with 9.6X0 => Not enough to absorb electron showers
Will exchange 7 2.1mm W plates by 2.8mm W plates and equip 8 layers with 4.2mm W plates
7x0.8+8x1.2X0 = 15.2X0
2.8mm W plates of 20x20cm2 from LLR (+ one 5.6mm W plate)
COBs completed before and after Xmas
Two COBs glued at LPNHE in december
Commissioning ongoing
Report on commissioning at next preparation meeting
One more COB (Slab 28) at IFIC may become available for the beam test
Encapsulated at IFIC
A fourth (encapsulated) one (Slab 32) with 15/16 ASICs back at ICJLab for further debugging
Stack runs currently with two FEV13 included

---
Towards beam test – To do list 15/3/22
Mechanics
Test assembly with new rails and W plates successful
Thanks to everybody involved!!!
No particular issue but consider transporting those with 2.x2.1mm W already assembled (maybe not possible anymore
when packing on Friday)
COBs
Slab 29 and Slab 33 operational but to be debugged for increased noise in two rows (AVDD) and the noisy ASIC 8
Decoupling capacitances added since last Wednesday, commissioning starts (finally) today
Passports for Slab 29 and 33 created by Yuichi)
FEV13
Now labelled Slabs 34 and 35, Passports created by Yuichi
Operation voltage of stack? Currently all slabs are operated with 150 V
Requires further observation
System
Slabs have been addressed according to layer position (convenient display in user interface)
The address switches on SL Board are not very robust
Will change them after the beam test but will take spare switches with us to DESY
Commissioning since last Friday (COBs replaced for the time being with Slabs 13 and 15 [Layer position 2 and 3])
News?
Logistics
New (recycled) transport boxes (=> no/less cardboard boxes)

---
Towards beam test – To do list 15/3/22 cont'd
Data acquisition
No news since last time
Data monitoring and DQ checks
No news since last time
All in place
News on EUDAQ?
Data management
Disk server (finally) restarted
~6.3 TByte of disk space available (7 TByte when cleaned up)
CentOS 7.9, Windows PC(s) accessible via remote desktop and Windows disk can be mounted
Need to redirect data to disk server
Should become only machine that is in contact with DAQ PC
Disk server should host a script that watches the diskspace on DAQ PC
Should be central device for DQ checks (i.e. All DQ check program should fetch data from diskserver)
Data storage on grid?
Need wiki page for March 2022 running
Need to organise seminar rooms for 9am operations meeting (Mail to Andrea sent)
We are are close to be good to go (packing on 18/3/22 afternoon)
Have to make use of the remaining time to understand the detector performance

---
DESY Test beam – On site
Unfortunately, the “rule of eight” will still apply at DESY
Germany is opening up (all restrictions for e.g. Sports events will be lifted on March 20th) but
so far no sign of consequences at DESY
The teams
Week 21/3/22 – 27/3/22
Will be an entire Ecal week -> tungsten running
Roman, Vincent, Adrian (from 22/3/22) , Yuichi, Jimmy (until 23/3/22), Alice (until 23/3/22), Fabrizio, Jonas
Alice needs training
Week 28/3/22 – 3/4/22
Combined running -> w/o tungsten
Adrian, Roman, Vincent, Dominique, Jihane (both 26/3/22 – 31/3/22), Stephane + two persons for AHCAL (Jiri, Katja)
Yuichi on call but will be around the entire time
First combined tests (26/3/22 – 27/3/22) outside of beam area
Have to ask Jiri and Katja whether they can help us with shifts and with dismounting
Conditions (same as last time)
Participants need have PCR test not older than 48h and be vaccinated (including booster)
Currently only two shifters are allowed in the beam test hall, more during setup
Propose to run two shifts per day 8h-16h, 16h-0h. night shifts should be taken into account to account for time loss
during setup of common running
Coordination (proposal)
Overall responsibility: Roman
Run coordination: Adrian (at least first week, depends also on requirements from common running)

---
DESY Test beam – Run plan
1st week: tungsten program
Several energy points with high statistics
Different positions, e.g. Scan over wafer boundaries
DESY 2021 gives orientation (see attached file)
16 runs at fixed position, 4 runs at fixed energy, 3 runs under angle
O(350kcycles), cycle length?
2nd week: Common running/MIP program
Setup including setup of/with AHCAL (count two days)
DAQ Integration with AHCAL
We may go once again for all 81 calibration points
“Rotated running?”
AHCAL may have “wishes” (-> will ask)
Hickups may lead to interruptions and delays of program
First and second week, need to make tests with high rate a high duty cycles
5-10 kHz at e.g. 2ms acquisition in 10ms cycle (=20% duty cycle)
Need to prepare CERN data taking

---
Backup