## Specification
Parameter | Post-TDR Specification |  | 10Hz Upgrade1,2 | 1 TeV CoM Spec 2 |  |  | Notes | Ref: | 1 CERN-ESU-004, Physics Briefing Book Input for the European Strategy for Particle Physics Update 2020, p168
Beam Energy (GeV) e- | 125 |  |  | 500 |  |  |  |  | 2 ILC250 accelerator, Shin Michizonono for US Snowmass AF-EF-meeting, June 2020, p6
Crossing Angle (mrad) | 14
Installation site (m from IP) | 14
RF Repetition Rate (Hz) | 5 |  | 10 | 4
Number of bunches | 1312 |  | 2625 | 2450 |  |  | Updated by Yokoya-san 19/5/21
Bunch Train Length (ms) | 726.848 |  | 960.75 | 896.7 |  |  | Updated by Yokoya-san 19/5/21
Bunch Spacing (ns) | 554 |  | 366
Beam current (mA) | 5.8 |  | 8.75 | 7.6
Operating Temp (K) | 2
Cryomodule installation length (m) | 3.8 (incorporating gate valves) | [5 empty] | Some additional restrictions expected for highest energy, driven by QF1 cryostat - Okugi-san 6/8/21 Joint-BDS meeting identified reduction needed 16/2/22 Revised assessment by Akira and BDS team, identifies 3.8m incl CM Gate valves, schematic incorporated into IP Interface 19/7/22
Horizontal beam-pipe separation (m) | 0.1967 (centre) ±0.0266 (each end of installation length) | [5 empty] | Updated by Okugi-san 6/8/21
Cavity Frequency (GHz) | 3.9 | 2.6 | 1.3 | 3.9 | 2.6 | 1.3
Total Kick Voltage (MV) | 0.615 | 0.923 | 1.845 | 2.5 | 3.7 | 7.4
Max Ep (MV/m) | 45 |  |  | 45 |  |  | As agreed during Design review workshop #1 8/12/21
Max Bp (mT) | 80 |  |  | 80 |  |  | As agreed during Design review workshop #1 8/12/22
Amplitude regulation/cavity (% rms) | 3.5 (for 2% luminosity drop) | [5 empty] | What is the stability anticipated for the applied kick voltage - Okugi-san 25/5/21
Relative RF Phase Jitter (deg rms) | 0.069
Timing Jitter (fs rms) | 49 (for 2% luminosity drop) | [5 empty] | Cavity-cavity jitter (rms) at arrival time, need to quantify re: frequency contributon, likely continuous?
Max Detuning (kHz) | 240 | 170 | 100 - 180 | 240 | 170 | 100 - 180 | As requested during Design Review Workshop 8/12/21
Beam-cavity jitter (fs rms) | [6 empty] | What tolerance is anticipated - Not so tight - Okugi-san 25/5
Longitudinal impedance threshold (Ohm) | Cavity wakefield dependent | [5 empty] | Clarify approach to define threshold - Not so tight, need time distribution of wakefield - Okugi-san 25/5/21
Trasverse impedance threshold (MOhm/m) (X,Y) | 48.8, 61.7 | [5 empty] | G Burt development paper as issued to WP3 team on 8/8/21
Cavity alignment tolerance (x, y) (mm) | [6 empty] | Likely to be cavity specific - strongly depend on cavity field distribution - Okugi-san 25/5
Cavity field rotation tolerance/cavity (mrad rms) | 5.2 (for 2% luminosity drop) | [5 empty] | Okugi-san 25/5/21
Beam tilt tolerance (H and V) (mrad rms and urad rms) | 0.35, 7.4 (for 2% luminosity drop) | [5 empty] | Okugi-san 25/5/21
Minimum CC beam-pipe aperture size (mm) | >25 (same as FD magnets) | [5 empty] | Clarify expectation re:photon load anticipated - Okugi-san 25/5 Design review workshop #1 8/12/21 concluded that 25mm minimum is more reaslistic specifically for the horizontal plane, most particularly for the 500GeV CoM specs 10sigma sims presented at joint-BDS meeting indicates increased aperture required 16/2/22
Minimum Exraction beam-pipe aperture size (mm) | 20 | [5 empty] | Okugi-san confirmed for both injection/extraction beamlines 6/8/21
Qext | [6 empty] | Beam-loading expected to be low - BDS team
Cavity bandwidth (Hz) | [6 empty] | Will be cavity specific
Input power (kW) | [6 empty] | Will be cavity specific
Cavity dynamic load (W) | [6 empty] | Will be cavity specific
Cryomodule static load (W) | [6 empty] | Will be cavity specific
Cavity aperture (H and V) (mm) | [6 empty] | Any constraints expected - BDS team - same as Row27?
Beam size at CC location (X, Y,Z) (mm,um,um) | 0.97, 66, 300 | [5 empty] | What collision volumes are anticipated - Okugi-san 25/5/21
Beta function at CC location (X, Y) (m,m) | 23200, 15400 | [5 empty] | Okugi-san 28/6/21, confirmed again by Okugi-san 6/8/21
Microphonic effects, cryogenics? | [6 empty] | Are there any driving implications, likely to be cavity specific?
Active positioning expected, tolerance (X,Y) - 2mm indicated? | [6 empty] | Any guidance on this for CM development?
Multipole effects for CC (May take some time if not already available) | [6 empty] | Any other BDS specific impact - BDS team - Wakefield assessments undeway using GdfidL output
CC System operation | assume CW-mode operation | [5 empty] | As agreed during Design Review Workshop 8/12/21

## CC Development Plan
Activity | R&D Plan | Tmescale | [15 empty] | When?
|  | 2021 |  |  |  | 2022 (Yr 1) |  |  |  | 2023 (Yr 2) |  |  |  | 2024 (Yr 3)
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Set CC specifications | T0 + 3m | [16 empty] | 2021-06-24 | bar: 2021 Q2
Bare cavity EM design parameters | bar: 2021 Q3 to 2022 (Yr 1) Q2
Hom damped cavity parameters | bar: 2021 Q3 to 2022 (Yr 1) Q2
HOM coupler development | bar: 2021 Q3 to 2022 (Yr 1) Q2
Mechanical design | bar: 2021 Q4 to 2022 (Yr 1) Q2
1st Workshop review of various design options (cavity, HOMs, couplers) | T0 + 9m | [16 empty] | 2021-12-07 | bar: 2021 Q4
Multipacting assessment | bar: 2022 (Yr 1) Q1 to 2022 (Yr 1) Q2
Tuning solution and pressure analysis | bar: 2022 (Yr 1) Q1 to 2022 (Yr 1) Q2
2nd Workshop review of various design options (cavity, HOMs, couplers, multipacting, tuning) | T0 + 15m | [16 empty] | 2022-06-21 | bar: 2022 (Yr 1) Q2
Decision 1 - cavity shape, HOMs, couplers, multipacting, tuning, pressure stability, fabrication (2 cavities chosen) | T0 + 18m | [16 empty] | 2022-09-27 | bar: 2022 (Yr 1) Q3
Decision 2 - Prototype cavity manufacture and ancillaries (couplers (FPC and HOMs) and tuner) and high power test (1 cavity chosen) | T0 + 36m | [16 empty] | 2024-03-01
Decision 1 (EM Design)
Decision 2 (Protototye)

## R&D Plan
| Milestone | Activity | When? | Duration (Months)? | Who? | Assumptions
| MS-0 | Set CC design specification | T0 + 3m | 3 | All CC groups, plus BDS/MDI/SRF input | What do we set as T0 (23/3)?
| MS-1 | Cavity EM design optimisation | T0 + 18m | 12 | All CC groups
| MS-2 | Coupler EM design optimisation (i.e. LOM, SOM and HOM) | T0 + 18m | 12 | All CC groups
Pre-Lab Phase | MS-3 | Dressed cavity mechanical design with tuner (concept) | T0 + 18m | 6 | All CC groups
| MS-4 | Prelim cavity down-selection process (2off) - Agreed | T0 + 18m | Decision 1 | All CC groups, plus BDS/MDI/SRF input, plus external reviewers
| MS-5 | Input coupler design and prototype validation | T0 + 36m | 24
| MS-6 | High power validation of prototype cavity? | T0 + 36m | 18
| MS-7 | Integrated 'dressed' cavity optimisation | T0 + 36m | 3
| MS-8 | Final Cavity down-selection (choose final solution)? Include input coupler Agreed | T0 + 36m | Decision 2
| MS-9 | Preliminary Crab CM design - confirm integration with beam-line specification | T0 + 48m | 24
| MS-10 | Final CM engineering design prior to production | T0 + 54m | 6 | Engineering Design Report to be completed
| MS-11 | CM assembly design | T0 + 54m | 6
| MS-12 | CM assembly tooling development | T0 + 54m | 6
| MS-13 | Design of CC pCM transport cage and shock damper | T0 + 60m | 6
| MS-14 | CC production, including cavities w/He tank + mag. shield for CM, high-pressure gas regulation, EP/HT/Clean work, including VT | T0 + 72m | 18
| MS-15 | Coupler production including preparation/RF processing readiness (excluding klystron, baking furnace, clean room) | T0 + 72m | 12
| MS-16 | CM production including High-pressure-gas formality, vacuum vessel, cold-mass (cavity-string, coupler/tuner, SCM, etc.) | T0 + 72m | 18
| MS-17 | Manufacture of CC pCM transport cage and shock damper system | T0 + 72m | 12
| MS-18 | Prototype CM (pCM) assembly | T0 + 78m | 12
| MS-19 | Acceptance verification of integrated CM | T0 + 79m | 1
| MS-20 | High power test of prototype CM | T0 + 83m | 3
| MS-21 | RF synchronisation of integrated 2-cavity CM cavities | T0 + 86m | 3
| MS-22 | Transportation validation (ship trans-atlantic and retest) | T0 + 91m | 6
Clarification needed:
Infratsruture, how incorporate (funding and staffing resource)? May need some indications from collaborators (even small expectations can be clarified)
Engineering design report during Pre-Lab, conceptual design, assign resources, include in WBS (resources to clarify)

## Cavity Parameters
Parameter | Elliptical/Racetrack | RFD | DQW | DQW Notes | WOW | QMIR | Units | Nomenclature
Operating frequency | 3.9 | 1.3 | 1.3 |  | 1.3 | 2.6 | GHz
SOM | 5.07 | None | N/A |  | NA | 2.217 | GHz
1st Longitudinal HOM | 3.32 | 2.396 | 2 |  | 1.765 | 3.46 | GHz
1st Transverse HOM | 5.07 | 2.0885 | 2.21 | Vertical | 2.299 | 2.82 | GHz
Ep/Et* | 3.55 | 3.76 | 270.2509 | Assume Et* = Vt/lambda/2 | 3.24 |  |  | Et - clarify eqtn (JD)
Bp/Et* | 8.3 | 6.8 | 461.2903 | Assume Et* = Vt/lambda/2 | 5.75 |  | mT/(MV/m)
Bp/Ep | 8.3 | 1.8 | 1.71 | No ports | 1.77 |  | mT/(MV/m)
G | 164 | 129.54 | 102 |  | 130.9 | 130 | Ω
R/Q | 47.6 | 440.4 | 211 | Circuit | 454.3 acc. def. | 225 | Ω
RtRs | 7830 | 5.70×104 |  | What is assumption for Rs? | 59446 | 13.5 | Ω2 | Assumptions for Rs
Vt per cavity | 0.5 | 1.35 | 0.93 | Computed as total Vcc required for 125 GeV crabbing divided by number of cavities | 1.60 max 1.48 nominal | 0.92 | MV
Ep | 23.05 | 44.2 | 29 | Below 45 MV/m | 45.0 max 41.6 nominal | 40 | MV/m
Bp | 53.9 | 79.6 | 49.5 | Below 80 mT | 79.8 max 73.8 nominal | 75 | mT
Total Vt | 2.5 | 8.1 | 1.86 | This is a requirement, not a DQW parameter | 8 | 3.7 | MV
Total No. of cavities | 5 | 6 | 2 |  | 5 | 4
Active Cavity Length | 77 |  | 117 |  | 168 | 250 | mm
Flange-flange Cavity Length | 177 | 310 | TBD | Further Mech Eng needed | 514 | 500 | mm
Number of cells | 2 | 1 | 1 |  | 1 | 3
Cavity Diameter | 108.6 | 99.4 | 104 |  | 97.2 | 75 | mm
Minimum Aperture | 25 | 25 | 25 |  | 25 | 25 | mm
FPC QL |  | 1.5×107 | 10000000 | 0.5 mm max offset, 50 Hz detuning, Vt = 1.48 MV per cavity for 500 GeV beam crabbing | 3e6 with 0.5mm offset & 200Hz shift | 1000000 |  | List assumptions used
Bandwidth |  | 0.0867 | 130 |  | 200 | 2.6 | kHz
Cavity Input Power |  | 31 | 0.3 |  | 0.85 | 1.5 | kW
Longitudinal Kick Factor kx |  |  | TBD | TBD | 2.71 |  | V/pC
Horizontal Kick Factor kx |  |  | TBD | TBD | 23.3 w/o 1.3GHz, 36.2 w/ | 45 | V/pC/m
Vertical Kick Factor ky |  |  | TBD | TBD | 15.6 | < 0.05 | V/pC/m
Stored Energy W | 0.11 | 0.0037 | 0.0031549 | Assume Q0 = 1e10 | 0.6 nominal | < 0.2 | J | Assume Et 1 MV/m
HOM impedance (Longitudinal) | 29.1 |  | TBD | HOM filter and damper design optimization ongoing | 0.14 | 130 | MΩ
HOM impedance (Transverse) | 22.8 |  | TBD | HOM filter and damper design optimization ongoing | 4.87 vertical 3.65 horizontal | 150 | MΩ/m
First 3 multipole pararameters |  |  | TBD | TBD
Nb material quantity (Kg) |  | 20 | 1.785 | Further Mech Eng needed. Only hollow cavity body and beam ports, no flanges. | 50.2 | 100
Nb material sheet/ingot |  | ingot and tubes | Ingot for main body: 100 mm x 120 mm x 130 mm. Sheets or ingot for ports. | Further Mech Eng needed | sheet | ingot, Ø100

## Multipole Parameters (HL-LHC)
| DQW |  | RFD |  |  | DQW |  | RFD
mT/mn-2 | Re | Im | Re | Im | mT/mn-2 | Re | Im | Re | Im
a2 | 0 | 0 | 0 | 0 | b2 | 6 | -2 | 0 | 0
a3 | 1506 | 27 | 0 | 0 | b3 | 0 | 0 | -522 | -56
a4 | 0 | 0 | 0 | 0 | b4 | 2106 | -539 | -914 | -36
a5 | N/A | N/A | N/A | N/A | b5 | N/A | N/A | N/A | N/A
a6 | N/A | N/A | N/A | N/A | b6 | N/A | N/A | N/A | N/A
Ref: R Calaga (CERN) 13/12/21

## IP Interface Schematic
Provided by Okugi-san and Akira 19/7/22